## Table A-Staffing
Proposal Application
FY2023 National Summer Transportation Institute (NSTI) Program
Table A - Staffing Requirements
State Abbreviation: |  | MD | State Name: | Maryland | State DOT/Pass-Through Entity: |  |  | MDOT SHA
Host Site: |  | Institution of Higher Education (IHE)
Include the personnel details of staff that will be involved in the development, implementation, and delivery of the NSTI project. Provide a narrative description of the duties and responsibilities related to each staff member or position working on the NSTI project and a breakdown of the salary or wage with an estimated amount of time to be billed to the NSTI project. An equitable allocation of cost for salaried employees requires developing an hourly rate and determining the amount of time spent on the project. The NSTI Work Hours and Total Cost will be recorded in Table E-Budget Narrative.
Place an "X" to select the appropriate program type. |  |  | Residential Program | X | Virtual Program |  |  |  | Non-Residential Program
Personnel Assigned (if known) or provide position
| Name |  | Position/Title | Affiliation (Faculty, Contract, Student) | Salary | Salary Hours | Salary Rate | Hourly Rate | Work Hours |  | Total Est. Cost
1 | Jane Smith, Ph.D. |  | Program Director | University Faculty Member | 7270 | 173.33 | 41.9431 |  | 100 |  | 4194.3114
| Narrative: |  |  |  | Full time: Week = 40 Hours & Month = 173.33 Hrs |  |  | Hourly Paid Staff |  | NSTI Hours | Budget Detail
Dr. Smith will be responsible for the development of the program, student recruiting process, hiring and training of staff and full organization of the summer camp, including: day to day operations of the NSTI program, providing management and oversight to ensure the major program elements are implemented effectively and efficiently according to the rules - NSTI Desk Reference Regulations, adhere to all applicable Federal, State laws and University institutional, and departmental policies and procedures. From June and July 2021 she will be working after her regular scheduled hours and on weekends. The PI will also provide the supervision of the students and other project personnel. Work involves significant activities performed at a separate operation and is in addition to her primary assignment. Additional Compensation (ECC) is requested.
2 | John Jones |  | NSTI Program Coordinator | University Faculty Member | 6876 | 173.33 | 39.67 |  | 100 |  | 3966.9994
| Narrative: |  |  |  | Full time: Week = 40 Hours & Month = 173.33 Hrs |  |  | Hourly Paid Staff |  | NSTI Hours | Budget Detail
Mr. Jones will collaborate on developing & implementing program curriculum; collaboration with COE faculty members, & the community partners. Provides programmatic support to students with the project. Assists with field trip organization, selection of speakers & presenters. During the camp, July 11 – 25, he will be working after his regular scheduled work hours and on weekends. Work involves significant activities performed at a separate operation and is in addition to his primary assignment. Additional Compensation (ECC) is requested.
3 | TBD |  | Program Assistant | Univeristy STEM undergrad student |  |  | 0 | 10 | 360 |  | 3600
| Narrative: |  |  |  | Full time: Week = 40 Hours & Month = 173.33 Hrs |  |  | Hourly Paid Staff |  | NSTI Hours | Budget Detail
A University STEM Undergraduate student will be hired to assist in program implementation. The Program Assistant will coordinate each detail of camp activities. Assists with recruitment, accommodation arrangements; communication with schools' officials, students & parents; field trips; opening & closing ceremonies. Assists with all functions of the camp. Assists with data collection & analysis. Provides direct support to the Program Director on daily basis from May through the end of July. Program Assistant will work 30 hours/week x 4 weeks = 120 hours/month x 3 months = 360 hours
4 | TBD |  | 2 Day Time Counselors | University STEM undergrad students |  |  | 0 | 10 | 160 |  | 1600
| Narrative: |  |  |  | Full time: Week = 40 Hours & Month = 173.33 Hrs |  |  | Hourly Paid Staff |  | NSTI Hours | Budget Detail
Supervise the 2023 NSTI minor participants during the day hours. Assist with the group project preparation. Plan leadership, recreational and team building activities. Attend all activities, including field trips. 2 STEM undergraduate students (counselors) will work 40 hours per week for 2 weeks at the rate of $10.00 per hour. 80 hrs x 2 counselors = 160 hours. $10 x 160 hours = $1,600.
5 | [6 empty] | 0 |  |  |  | 0
| Narrative: |  |  |  | Full time: Week = 40 Hours & Month = 173.33 Hrs |  |  | Hourly Paid Staff |  | NSTI Hours | Budget Detail
6 | [6 empty] | 0 |  |  |  | 0
| Narrative: |  |  |  | Full time: Week = 40 Hours & Month = 173.33 Hrs |  |  | Hourly Paid Staff |  | NSTI Hours | Budget Detail
7 | [6 empty] | 0 |  |  |  | 0
| Narrative: |  |  |  | Full time: Week = 40 Hours & Month = 173.33 Hrs |  |  | Hourly Paid Staff |  | NSTI Hours | Budget Detail
8 | [6 empty] | 0 |  |  |  | 0
| Narrative: |  |  |  | Full time: Week = 40 Hours & Month = 173.33 Hrs |  |  | Hourly Paid Staff |  | NSTI Hours | Budget Detail
9 | [6 empty] | 0 |  |  |  | 0
| Narrative: |  |  |  | Full time: Week = 40 Hours & Month = 173.33 Hrs |  |  | Hourly Paid Staff |  | NSTI Hours | Budget Detail
10 | [6 empty] | 0 |  |  |  | 0
| Narrative: |  |  |  | Full time: Week = 40 Hours & Month = 173.33 Hrs |  |  | Hourly Paid Staff |  | NSTI Hours | Budget Detail
Note on A7: Select more than one if applicable.
Note on G9: Enter the regular salary amount for the employee. If the Staff member is an hourly employee, then leave the Salary and Salary Hours blank and enter hourly rate in the appropriate field.
Note on I9: Is the salary paid on a weekly (40 hours), biweekly (80 hours), monthly (173.33 hours), or some other basis? Is the salary for part-time or full-time work? Enter the normal work hours for the applicable period of time.
Note on J9: Salary divided by Salary Hours (G10/I10) to calculate an estimated Hourly Salary Rate.
Note on K9: Enter the hourly rate for non-salaried employees. Leave this blank if salary information is provided.
Note on L9: How many hours will this employee work on the NSTI program? Enter that number here.
Note on N9: Multiply either the Salary Rate (J10) OR Hourly Rate (K10) by the NSTI Work Hours (L10) to calculate an estimated salary/wage cost for the project.

## Table B-IAC
FY2023 National Summer Transportation Institute (NSTI) Program
Table B - Intermodal Advisory Committee (IAC)
State: | Maryland
Host Site: | Institution of Higher Education (IHE)
Host sites are encouraged to establish an Intermodal Advisory Committee (IAC) and select members from a broad spectrum of the transportation community. The FHWA, State DOT, Community Based Organization (CBO), and private industry individuals may participate as members of the IAC.
Name:
Title:
Organization:
Name:
Title:
Organization:
Name:
Title:
Organization:
Name:
Title:
Organization:
Name:
Title:
Organization:
Name:
Title:
Organization:
Name:
Title:
Organization:
Name:
Title:
Organization:
Name:
Title:
Organization:
Name:
Title:
Organization:

## Table C-Partners
FY2023 National Summer Transportation Institute (NSTI) Program
Table C - Partners and Sponsors
State: |  | Maryland
Host Site: |  | Institution of Higher Education (IHE)
Describe any partners, sponsors, and/or other contributors that will support the delivery of the NSTI Program. This includes individuals or entities that provide support through funding, sharing responsibility for delivering the NSTI program, or contributions in providing information and learning opportunities through presentations, field trips, site visits and/or tours. Describe the role and contribution of each partner or sponsor and provide funds or value of donated services and any costs associated with tours or site visits. Any donated funds or value of services should be included in this table and also recorded in the Budget Narrative In-kind Donations or State/Local funds. Costs related to registration fees for tours and site visits should be included in the estimated costs and also in the Budget Narrative Other Participant Support Costs.
1 | Name or Contact | Title | Organization | Donated Funds or Value of Services | Estimated Cost (if any)
| John Doe | Museum Director | State Train Museum |  | 200
Role and Contribution Narrative
Field trip to see State Train Museum
2 | Name or Contact | Title | Organization | Donated Funds or Value of Services | Estimated Cost (if any)
Role and Contribution Narrative
3 | Name or Contact | Title | Organization | Donated Funds or Value of Services | Estimated Cost (if any)
Role and Contribution Narrative
4 | Name or Contact | Title | Organization | Donated Funds or Value of Services | Estimated Cost (if any)
Role and Contribution Narrative
5 | Name or Contact | Title | Organization | Donated Funds or Value of Services | Estimated Cost (if any)
Role and Contribution Narrative
6 | Name or Contact | Title | Organization | Donated Funds or Value of Services | Estimated Cost (if any)
Role and Contribution Narrative
7 | Name or Contact | Title | Organization | Donated Funds or Value of Services | Estimated Cost (if any)
Role and Contribution Narrative
8 | Name or Contact | Title | Organization | Donated Funds or Value of Services | Estimated Cost (if any)
Role and Contribution Narrative
9 | Name or Contact | Title | Organization | Donated Funds or Value of Services | Estimated Cost (if any)
Role and Contribution Narrative
10 | Name or Contact | Title | Organization | Donated Funds or Value of Services | Estimated Cost (if any)
Role and Contribution Narrative

## Table D-Plan
FY2023 National Summer Transportation Institute (NSTI) Program
Table D - Implementation Plan
State: | Maryland
Host Site: | Institution of Higher Education (IHE)
Host sites should describe all tasks necessary to deliver a successful NSTI Program. The implementation plan should outline the steps the host site will take from concept, recruitment of IAC or partners/sponsors, development of a curriculum, promoting the program, review and selection of applicants and final delivery of the National Summer Transportation Institute program. The tasks and timeframes listed should match with the Statement of Work (SOW) submitted by the host site.
Task 1: | Build Implementation Plan
Assigned To: | Program Director
Action Required: | Recruit and Confirm IAC & STI Partners/Sponsors
Timeframe: | 4/1/2023 - 6/1/2023
Task 2: | Sub-Agreement with SDOT
Assigned To: | Program Director & University Sponsored Programs
Action Required: | Begin Implementation Plan
Timeframe: | 4/15/2023 - 7/3/2023
Task 3: | Begin recruitment-develop and distribute materials
Assigned To: | Program Director
Action Required: | Work to develop, design, and distribute applications to targeted students
Timeframe: | 4/15/2023 - 6/19/2023
Task 4: | Preparation for STI
Assigned To: | Program Director, Program Coordinator
Action Required: | Continue Program planning, staff election, hiring professional development/training
Timeframe: | 5/1/2023 - 6/19/2023
Task 5: | Student Selection
Assigned To: | Program Director, Program Coordinator, & Selection Committee
Action Required: | Review/Evaluate Applications, Select & Announce
Timeframe: | 5/1/2023 - 6/19/2023
Task 6: | Complete Staff & Intermodal Committee Selection
Assigned To: | Project Director & Program Coordinator
Action Required: | Complete selection of staff ( instructors, mentors, IAC, and add sponsors as necessary)
Timeframe: | 5/1/2023 - 6/5/2023
Task 7: | Organize and plan proposed activities
Assigned To: | Program Director & Program Coordinator
Action Required: | Coordinate all on-campus or off-campus gathering (for class instruction) and trainings
Timeframe: | 5/1/2023 - 7/3/2023
Task 8: | Campus Arrangements
Assigned To: | Program Director & Program Coordinator
Action Required: | Organize Virtual Programming
Timeframe: | 5/1/2023 - 7/3/2023
Task 9:
Assigned To:
Action Required:
Timeframe:
Task 10:
Assigned To:
Action Required:
Timeframe:

## Table E-Budget
FY2023 National Summer Transportation Institute (NSTI) Program
Table E - Program Budget Narrative Worksheet
GRANT PROGRAM |  | ASSISTANCE LISTING # |  | FISCAL YEAR | STATE | HOST SITE |  |  |  | AC? | PROPOSAL/ MOD DATE
NSTI - Hwy Plng & Const Program |  | 20.205 |  | 2023 | MD | Institution of Higher Education (IHE) |  |  |  |  | 2022-08-31
Total Funding and Contributions
NSTI Funds Requested |  | OJT/SS Funds |  |  | 504(e) Funds Added (NHPP, STBG, HSIP, CMAQ) |  | State/Local Funds |  | In-kind Contribution(s) | Total Cost
50000 |  | 0 |  |  | 0 |  | 338.93 |  | 0 | 50338.93
Budget Summary
Narratives and Cost Details |  |  |  | Cost Breakdown
|  |  |  | NSTI Funds |  | OJT/SS | 504(e) | State/Local | In-kind | Total Cost
Direct Program Costs |  |  |  | 18099.94 |  | 0 | 0 | 0 | 0 | 18099.94
Participant Support Costs |  |  |  | 27375.07 |  | 0 | 0 | 338.93 | 0 | 27714
Indirect Costs |  |  |  | 4524.99 |  | 0 | 0 | 0 | 0 | 4524.99
Total NSTI Program Cost |  |  |  | 50000 |  | 0 | 0 | 338.93 | 0 | 0
Budget Narrative
Narratives and Cost Details |  |  |  | Cost Breakdown
|  |  |  | NSTI Funds |  | OJT/SS | 504(e) | State/Local | In-kind | Total Cost
DIRECT PROGRAM COSTS
Employee Compensation (detail cost of employee hourly/monthly rates and number of hours is provided in Table A-Staffing Requirements)
The direct salary or wages paid to host site employees working directly on delivery of the NSTI program are allowable costs provided they meet the requirements in 2 CFR §200.430(h) regarding determining allowable personnel compensation costs for Institutions of Higher Education (IHE). The salary basis for charges to the NSTI by faculty members during the academic year are allowable at the Institutional Base Salary (IBS), which is the annual compensation paid by an IHE for an individual's appointment. In no event will charges to Federal awards, irrespective of the basis of computation, exceed the proportionate share of the IBS for that period unless specifically requested and in accordance with §200.430(h)(4). This principle applies to all members of faculty at an institution. Charges to the NSTI for salaries and wages must be based on records that accurately reflect the work performed. (See §200.430(i) Standards for Documentation of Personnel Expenses.)
Title/Position |  | Hours | Cost | Distribute costs from Table A-Staffing to the appropriate fund type. | [5 empty] | Total Cost
1 | Program Director | 100 | 4194.3114 | 4194.31 | [5 empty] | 4194.31
2 | NSTI Program Coordinator | 100 | 3966.9994 | 3967 | [5 empty] | 3967
3 | Program Assistant | 360 | 3600 | 3600 | [5 empty] | 3600
4 | 2 Day Time Counselors | 160 | 1600 | 1600 | [5 empty] | 1600
5
6
7
8
9
10
Total Employee Compensation |  |  |  | 13361.31 |  | 0 | 0 | 0 | 0 | 13361.31
Employee Fringe Benefits (provide justification and supporting documentation for any fringe benefit calculations, include cognizant approval)
The costs of employee leave, insurance, pensions, and unemployment benefit plans are allowable costs, but fringe benefits must be allocated to Federal awards and all other activities in a consistent and equitable manner. A fringe benefit rate, if applied, must be approved by the cognizant agency for indirect cost. Identifying the total fringe benefit cost for an employee and identifying the equitable proportion that should be applied to the NSTI should be explained and documented in the Justification/Narrative below. (§200.431 Compensation–Fringe Benefits) Enter the appropriate fringe rate below and it will be applied to the salary entered above to calculate cost. To apply another methodology, describe in the narrative and enter the costs below. If the University will only be claiming the FICA amount (7.65%) for their employees enter that rate below. If claiming another rate, the Fringe Benefit rate approval from the Cognizant Agency for Indirect Costs must be provided to support rates other than the required FICA rate.
Justification/Narrative
Effective FY21, The University will be using the following federally approved pooled fringe benefit rates. Faculty/Professional Staff (including Postdoctoral Scholars) – 29.9%; Classified Staff – 43.5%; Letter of Appointments (Temporary Professional Staff) – 16.4%; Graduate Assistants – 9.5%; Student or Other Hourly – 4.2%. Approval of Fringe Rates is attached.
Title/Position |  | Rate | Cost | NSTI Funds |  | OJT/SS | 504(e) | State/Local | In-kind | Total Cost
1 | Program Director | 29.9% | 1254.0991 | 1254.1 | [5 empty] | 1254.1
2 | NSTI Program Coordinator | 29.9% | 1186.1328 | 1186.13 | [5 empty] | 1186.13
3 | Program Assistant | 4.2% | 151.2 | 151.2 | [5 empty] | 151.2
4 | 2 Day Time Counselors | 4.2% | 67.2 | 67.2 | [5 empty] | 67.2
5
6
7
8
9
10
Total Fringe Benefits |  |  |  | 2658.63 |  | 0 | 0 | 0 | 0 | 2658.63
Advertising & Outreach |  |  |  | NSTI Funds |  | OJT/SS | 504(e) | State/Local | In-kind | Total Cost
Costs of advertising media and corollary administrative costs associated with the recruitment of personnel to support NSTI and advertising costs associated with NSTI program outreach are allowable costs. Advertising media include magazines, newspapers, radio and television, direct mail, exhibits, and the internet. (§200.421 Advertising and public relations)
Justification/Narrative
Advertise in several STEM Newsletters and mailed outreach flyers for the NSTI program.
Newsletter Advertising |  |  |  | 200 | [5 empty] | 200
Direct Mail Cost |  |  |  | 100 | [5 empty] | 100
Total Advertising & Outreach |  |  |  | 300 |  | 0 | 0 | 0 | 0 | 300
Publication & Printing |  |  |  | NSTI Funds |  | OJT/SS | 504(e) | State/Local | In-kind | Total Cost
Publication costs for electronic and print media, including distribution, promotion, and general handling directly related to the NSTI program are allowable. (§200.461 Publication and printing costs.)
Justification/Narrative
Publish and printing outreach flyers for the NSTI program.
Recruitment and Outreach Flyers |  |  |  | 500 | [5 empty] | 500
Total Publication & Printing |  |  |  | 500 |  | 0 | 0 | 0 | 0 | 500
Contractual Services |  |  |  | NSTI Funds |  | OJT/SS | 504(e) | State/Local | In-kind | Total Cost
The costs of contracts to procure goods or services directly in support of the NSTI program are allowable costs.
Justification/Narrative
Total Contractual Services |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
Supplies |  |  |  | NSTI Funds |  | OJT/SS | 504(e) | State/Local | In-kind | Total Cost
Costs incurred for materials and supplies necessary to carry out the NSTI program are allowable. Supplies are any tangible property with a per unit cost of less than $5,000, and this includes computing devices (computers, laptops, tablets). In the specific case of computing devices, charging as direct costs is allowable for devices that are essential and allocable to the performance of the NSTI program. (§200.453 Materials and supplies costs, including costs of computing devices) NOTE: If any computing devices will be a proposed cost in delivering a proposed NSTI Program, the applicant must document the essential need, how the computing devices will be used, and ensure the costs of procuring any computing devices does not significantly impact delivery of the overall NSTI Program initiative. If computing devices will be provided to students, then that is a partcipant support cost and must be included in that section below and not here.
Justification/Narrative
Supplies include: notebooks, pens, pencils, materials needed for group project, paints, and ID cards for counselors and staff members. ID Cards $20 per card x 16 Students = $320
ID Cards $20 x 16 Students |  |  |  | 320 | [5 empty] | 320
Supplies $60 x 16 Students |  |  |  | 960 | [5 empty] | 960
Total Supplies |  |  |  | 1280 |  | 0 | 0 | 0 | 0 | 1280
Travel Costs |  |  |  | NSTI Funds |  | OJT/SS | 504(e) | State/Local | In-kind | Total Cost
Expenses for transportation, lodging, subsistence, and related items incurred by host site employees related to the NSTI program is allowable. Travel must be performed in accordance with the Host Site’s written travel policies. NOTE: Travel costs for participants should NOT be recorded here. This is only employee travel.
Justification/Narrative
Total Travel Costs |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
Other Costs |  |  |  | NSTI Funds |  | OJT/SS | 504(e) | State/Local | In-kind | Total Cost
Enter any other costs not identified. This would included any allowable costs that don't fit the categories above or costs that are unallowable for Federal participation, but may be paid 100% with State/Local/University funds. NOTE: Costs of promotional items and memorabilia, including models, gifts, clothing, and souvenirs are UNALLOWABLE. Costs incurred for promotional items must not be charged to the NSTI Program, but these costs may be paid entirely with non-Federal funds. (§200.421(e)(3) Advertising and public relations) Costs for items provided to students must be included in the Other Particpant Support Costs section below.
Justification/Narrative
Total Other Costs |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
PARTICIPANT SUPPORT COSTS
Transportation and Travel (field trips) |  |  |  | NSTI Funds |  | OJT/SS | 504(e) | State/Local | In-kind | Total Cost
Transportation and travel for participants includes stipends for transportation to and from NSTI location for non-Residential programs. Travel for participants to attend residential programs may be provided if necessary and reasonable for the NSTI program. Any travel for participants to attend field trips would also be included in this section.
Justification/Narrative
3-4 Field Trips: 16 students + 4 counselors, locations: 1. International Airport (air traffic & airport operation), No entry fee; 2. Freeway & Arterial System of Transportation (city traffic control & management), No entry fee; 3. Hospital Trauma Center + Police Department (role of emergency taskforce, deployment operations, traffic and pedestrian safety), No entry fee; 4. Rail & Mass Transit Facility (above ground rail mass transit system), No entry fee; State Train Museum (entry fee) – pending the funding availability. Est. cost $4,500 for 4 three hour trips + a day trip to Train Museum. • $2671 (mini bus) + $1683 (mini bus - one day trip to Train Museum) For a maximum of 4 Students x $750 per student for flights from Northern part of State. Total $3,000
4 three hour trips in Mini Bus |  |  |  | 2332.07 |  |  |  | 338.93 |  | 2671
Day trip to Train Museum in Mini Bus |  |  |  | 1683 | [5 empty] | 1683
Flights for four students x $750 |  |  |  | 3000 | [5 empty] | 3000
Total Participant Transportation and Travel |  |  |  | 7015.07 |  | 0 | 0 | 338.93 | 0 | 7354
Lodging and Facilities |  |  |  | NSTI Funds |  | OJT/SS | 504(e) | State/Local | In-kind | Total Cost
Lodging and facilities costs for residential programs are allowable costs for the NSTI program. Costs should be reasonable and allocable to the NSTI project. Non-residential programs may not charge lodging costs unless an overnight field trip necessitates lodging costs. This must be described in the narrative.
Justification/Narrative
Residential program will provide room and board for students. 10 rooms x $75/day x 14 days=$10,500
Room and Board for Students |  |  |  | 10500 | [5 empty] | 10500
Total Participant Lodging and Facilities |  |  |  | 10500 |  | 0 | 0 | 0 | 0 | 10500
Meals & Subsistence |  |  |  | NSTI Funds |  | OJT/SS | 504(e) | State/Local | In-kind | Total Cost
Meals and Subsistence costs are allowable for residential NSTI programs. Meal costs are NOT allowed with Federal funds in non-residential NSTI programs, unless the meal cost can be justified as being beneficial to the program and participants and would be necessary for the successful delivery of the NSTI program. The normal process would be for non-residential students to provide their own lunches or costs of meals may be provided and paid 100% with non-Federal funds.
Justification/Narrative
Residential program will provide room and board for students. 10 rooms x $75/day x 14 days=$10,500
Meals for Residential Students & Counselors |  |  |  | 9660 | [5 empty] | 9660
Total Participant Meals & Subsistence |  |  |  | 9660 |  | 0 | 0 | 0 | 0 | 0
Other Participant Support Costs |  |  |  | NSTI Funds |  | OJT/SS | 504(e) | State/Local | In-kind | Total Cost
Provide any additional participant support costs necessary for the delivery of the NSTI. These may include registration fees associated with field trips, but may not include food. Costs must be reasonable and necessary for the NSTI and related to transportation. Costs associated with field trips, site visits, and tours will also be provided in Table C-Partners & Sponsors. Other costs for participant support must be described in the narrative. Costs of computer equipment or tablets provided to participants must be recorded in this section. NOTE: If any computing devices will be provided to participants of the NSTI Program, the applicant must document the essential need, how the computing devices will be used, and ensure the costs of procuring any computing devices does not significantly impact delivery of the overall NSTI Program initiative.
Justification/Narrative
Train museum registration fee of $10 for 20 attendees for a total of $200.
State Train Museum Registration Fees $10 x 20 |  |  |  | 200 | [5 empty] | 200
Total Other Participant Support Costs |  |  |  | 200 |  | 0 | 0 | 0 | 0 | 200
INDIRECT COSTS
Indirect or Facilities and Administration (F&A) costs are allowable costs under the NSTI program; however, host sites must have an approved and currently effective indirect cost rate proposal (ICRP) for the indirect costs to be allowable in the budget. The Cognizant Agency for Indirect Cost for Institutions of Higher Education (IHE) is assigned to Department of Health and Human Services (HHS) or the Department of Defense's Office of Naval Research (DOD), normally depending on which of the two agencies (HHS or DOD) provide the most direct Federal funding to the IHE in the most recent three years. Where an IHE only receives Federal funds as a subrecipient, the Pass-Through Entity (PTE), which is the State DOT for the NSTI program, is responsible for determining the appropriate rate in collaboration with the subrecipient, which is either: 1. A negotiated indirect cost rate between the PTE or State DOT and host site (predetermined rate, fixed rate with carry forward adjustment, provisional/final rate) ; or 2. The de minimis rate of 10% of Modified Total Direct Cost (excludes participant support costs) Describe if the host Site will be claiming indirect costs and if so, provide an effective and approved Indirect Cost Rate Agreement from the IHE Cognizant Agency for Indirect Cost. If no agreement exists, indirect costs are not allowable unless the De Minimis rate is used. Indirect rates may be applied only to a Modified Total Direct Cost (MTDC) base as defined in §200.1, which excludes Participant Support Costs. (See §200.332-Requirements for Pass-Through Entities, §200.414-Indirect (F&A) costs, Appendix III to Part 200-Indirect (F&A) Costs Identification and Assignment, and Rate Determination for IHEs)
Rate Type: |  | Predetermined Rate |  |  | Justification/Narrative
University F&A cost is calculated using a predetermined rate as stipulated by DHHS Rate Agreement dated 07/22/2020 (DHHS Audit Agency,Maryland). The on-campus other sponsored program rate of 36% of Modified Total Direct Costs (MTDC) has been effective since 07/01/20. To support the costs for these students, the University has approved a waiver to reduce the F&A rate for the 2023 NSTI to 25% of MTDC. Total Direct Costs: $45,813.94 Modified Total Direct Cost Base: $18,099.94 Indirect Costs at 15%: $4,524.99
Effective Period |  | 7/1/2020-7/31/2023
Approved Rate: |  | 25%
Modified Total Direct Cost (MTDC) Base: |  | 18099.94
Total Indirect Costs (Rate x MTDC) |  | 4524.985
Indirect Cost Fund Allocation |  |  |  | NSTI Funds |  | OJT/SS | 504(e) | State/Local | In-kind | Total Cost
Indirect Costs |  | 4524.985 |  | 4524.99 | [5 empty] | 4524.99
Note on K3: If your project will be using Advanced Construction, please place "X" here.
Note on L3: This is the date the NSTI worksheet is submitted to the State DOT. If there is a modification to an existing submittal, provide the date the modification is submitted.
Note on A16: These totals have conditional formatting and must equal the Total Funding and Contributions above. If the cell is highlighted you must adjust costs in the detail or modify the amounts identified in the Total Funding and Contribution to remain in balance.
Note on E16: The total costs that will be paid with NSTI funds from the detail sections below. This number must match the NSTI Funds requested in Cell B8.
Note on G16: The total costs that will be paid with OJT/SS funds from the detail sections below. This number must match the OJT/SS number in Cell E8.
Note on H16: The total costs that will be paid with 504(e) funds from the detail sections below. This number must match the 504(e) number requested in Cell G8.
Note on I16: The total costs that will be paid with State/Local funds from the detail sections below. This number must match the State/Local Funds number in Cell I8.
Note on J16: The total value of In-kind contributions that will be used towards the project identified in the In-Kind detail sections below. This number must match the In-kind number in Cell J8.
Note on C40: If a rate is entered here, it must be supported with an approval from the Cognizant Agency for Indirect Costs.
Note on A137: Select the rate type that has been approved. (Fixed, Predetermined, Provisional, or De Minimis) If a rate is being charged there must be an approval from the Cognizant Agency for Indirect Costs. If there is no approval, then a de minimis rate may be applied to modified total direct costs, but not to particpant support costs.
Note on A139: The ICRP must be approved for an effective period that includes the delivery period of the NSTI program.
Note on A140: Enter the rate that has been approved by the Cognizant Agency for Indirect Cost for an effective period that includes the delivery time for the NSTI program.
Note on A141: MTDC means all direct salaries and wages, applicable fringe benefits, materials and supplies, services, travel, and up to the first $25,000 of each subaward (regardless of the period of performance of the subawards under the award). MTDC excludes equipment, capital expenditures, charges for patient care, rental costs, tuition remission, scholarships and fellowships, participant support costs and the portion of each subaward in excess of $25,000. Other items may only be excluded when necessary to avoid a serious inequity in the distribution of indirect costs, and with the approval of the cognizant agency for indirect costs.