CATEGORY 100

PRELIMINARY

To be used on areawide projects that cap the bid to 3% or do not include a pay item for mobilization and demobilization.

SECTION 108 — MOBILIZATION AND DEMOBILIZATION

DELETE:  SECTION 108 — MOBILIZATION AND DEMOBILIZATION in its entirety.

INSERT:  The following.

SECTION 108 — MOBILIZATION AND DEMOBILIZATION

108.01 DESCRIPTION.  Construction preparatory and closing (clean-up) operations that include the movement of personnel, supplies, materials, tools, equipment, and incidentals to, within, and away from the project site collectively for the project and for individual work operations; and the establishment and removal/decommissioning of the Contractor’s offices, buildings, and other facilities necessary to commence, continue, and conclude the work. Perform final clean-up as specified in GP-4.09.

108.02 MATERIALS.  Not applicable.

108.03 CONSTRUCTION.  Not applicable.

108.04 MEASUREMENT AND PAYMENT

Mobilization and Demobilization will not be measured but will be paid for at the Contract lump sum price not to exceed 3 percent of the adjusted contract amount.  The adjusted contract amount is defined as the total Contract amount less the lump sum bid for Mobilization and Demobilization.  If the amount bid for this item exceeds 3 percent of the adjusted contract amount, the bid shall be rejected as not responsive.

Payment of the Mobilization and Demobilization item, up to a maximum of 3 percent of the adjusted Contract amount, will be made according to the following payment schedule.

- 50 percent of the Mobilization and Demobilization will be paid in the first monthly estimate after the Contractor has established the necessary facilities.

- 50 percent of Mobilization and Demobilization will be prorated and paid in equal amounts on each of the next five monthly estimates.

Payment of the Mobilization and Demobilization item will not be made more than once, regardless of the fact that the Contractor may have, for any reason, shut the work down on the project or moved their equipment away from the project and then back again.

The cost of all required insurance and bonds will be incidental to this item.

If the Mobilization and Demobilization item is not provided, the cost of mobilization and demobilization, including the required insurance and bonds, will be incidental to the other items specified in the Contract Documents.  The payment will be full compensation for all material, labor, equipment, tools, and incidentals necessary to complete the work.