Terms and Conditions

TC - Section 7 — Payment

TC-7.02 PAYMENT ALLOWANCES FOR STORED MATERIAL

DELETE:  TC-7.02(a) The first sentence of the first paragraph, “For superstructure members… of the applicable Contract item.”

INSERT:  The following.

For superstructure members delivered to the project or in storage at an approved site, an allowance of 100 percent of the material cost plus freight charges as invoiced may be made provided the cost does not exceed 90 percent of the Contract price of the applicable Contract item.

DELETE:  TC-7.02(b) in its entirety.

INSERT:  The following.

(b) For reinforcement steel, piling, pipe, traffic barrier, signs and sign assemblies, form lumber, falsework, temporary structures, and other nonperishable material delivered to the project or in storage at an approved site, excluding aggregates, cement, seed, plants, fertilizer, or other perishable items, an allowance of 100 percent of the invoiced cost of the material plus freight charges to the Contractor may be made provided the cost does not exceed 90 percent of the Contract price of the applicable Contract item.  Such material shall be delivered and stock-piled at the project site or an approved location (TC-7.02(d)) after being tested by the Administration and found to have conformed to the Specifications, if applicable, or to have been accepted under an approved certification program prior to the allowance.

DELETE:  TC-7.02(c) The first paragraph, “No allowance will … the finished construction.”

INSERT:  The following.

(c) No allowance will be made for fuels or other materials that will not structurally assist the construction of a finished work item.

DELETE:  TC-7.02(c) The third paragraph, “Only end product … eligible for prepayment.”