Terms and Conditions

TC – Section 7 — Payments

TC-7.05 PROGRESS PAYMENTS

(a) Current Estimate

DELETE:  Paragraph (2) in its entirety.

INSERT:  The following.

(2) Monthly Estimates.  Each month the Administration will pay the Contractor for the Contract value of the authorized work satisfactorily performed during the preceding calendar month, less variable retainage specified in (3) Variable Retainage.  Retainage will not be released until final payment (unless partially released in a semifinal payment or released to a subcontractor as per TC-7.05(a)(3)(F)).  Current estimates will be based upon the procurement officer’s estimate of satisfactorily performed work (including materials and/or equipment complete in place).  In the instance of lump sum items and each items, the procurement officer’s estimate will either be the percentage of the item satisfactorily performed during the preceding month or as specified in contract documents.  All quantities, estimates, and fractions will be reasonably accurate approximations and are subject to corrections: (a) in subsequent current estimates; (b) in any semi final estimate; and (c) in final payment.  Any or all partial payments may be withheld in the event the Contractor has not complied with current requirements of the Specifications.  Should either the procurement officer or the Contractor be of the opinion that any estimates, quantities, or fractions (either as to an individual current estimate or accumulations thereof) do not represent a reasonably accurate approximation of actual work, then the details questioned will be reviewed.  Any necessary corrections and adjustments will be made in the next current estimate.

Subcontractors

DELETE:  Paragraph (A) in its entirety.

INSERT:  The following.

(A) Sections A-F apply if the contractor has furnished 100 percent payment security and 100 percent performance security.

ADD: The following after paragraph (E).

(F) A subcontractor may submit written notification to the Contractor requesting to have their portion of the retainage released if the following requirements are met.

(1) All tasks assigned to the subcontractor within the subcontractor agreement are satisfied.

(2) All related pay items associated with the subcontractor’s responsibility have had all required documentation for those items submitted and approved by the Administration.

(3) The Contractor has notified the Administration that the subcontractor has fulfilled its contractual obligations, including submitting all required documentation, and has requested that the Administration conduct an Interim Subcontractor Final Inspection.

(4) The Administration has performed the said Interim Subcontractor Final Inspection.  The Administration will verify that all Contract requirements have been satisfied during the Subcontractor Final Inspection, and issue in writing a Subcontractor Accepted for Maintenance letter. Subcontractor Accepted for Maintenance letter does not relieve the Contractor of the responsibility to perform the work to specifications or remedy its latent defects.

(5) All issues, including punch list items, and claims related to the subcontractor’s work are resolved.

When (1)-(5) are met, the Contractor shall verify that the subcontractor’s requested retainage is accurate and then submit, in writing, the subcontractor’s request to release the subcontractor’s portion of the retainage held by the Administration.  The Assistant District Engineer-Construction (ADE-C) or department head shall then perform a subcontractor final inspection to determine if a Subcontractor Final Acceptance for Maintenance is warranted, if the acceptance is approved then the retainage request will be processed as per this specification.  If the Subcontractor Final Acceptance for Maintenance is not granted, a list of outstanding responsibilities shall be provided to the contractor by the Administration for the subcontractor to complete in order to request another follow up Final Subcontractor Inspection.

Once the request is approved by the Administration, the Administration will submit to the Contractor “Subcontractor’s Final Quantities” within 60 days of the approval.  The tabulation shall be accompanied by a statement setting forth:

(a) The eliminated work, changed work and additional work performed under change orders and/or supplemental agreements by the subcontractor;

(b) The authorized extension or adjustments of time;

(c) The number of days that have been charged to date of the subcontractor’s early retainage request;

(d) Any deductions, charges, or liquidated damages that have been made or imposed to date of the subcontractor’s early retainage request.  The Contractor shall have a period of 30 days from the date of receiving the aforementioned tabulations from the Administration, in which:

- To decide whether or not to accept the subcontractor’s final tabulation of final quantities, and

- To notify the Administration, in writing, of the decision.  The Contractor may request an additional period of 30 days in which to notify the Administration of their decision.  In the event the Contractor notifies the Administration that the Contractor or subcontractor protests the final quantities on such basis, the notification shall outline the reasons for said protest.

After all parties have agreed upon the Subcontractor’s Final Quantities, the Administration will begin the process of releasing the subcontractor’s portion of the retainage.  Once the Subcontractor Final Quantities are agreed upon, those items cannot be disputed at a future date and these items are considered finalized unless further work has been performed due to a partial item status or other contractual responsibilities of the Contractor in which further work had to be completed for said item.

The Contractor will have a period of 10 days to submit payment of the released retainage to the requesting subcontractor, after the Contractor has received said payment from the Administration for the subcontractor’s portion of the remaining retainage held.  The Contractor cannot hold additional retainage from the subcontractor after the subcontractor’s final portion of retainage is released.