Category 100

Preliminary

Only used in XB Contracts

section 103 — Engineers Office

103.04 MEASUREMENT AND PAYMENT

DELETE:  The first and second paragraphs “Engineers Office will not…Office specified” and “Payment of 50 percent…necessary to complete the work” in its entirety.

INSERT:  The following.

Engineers Office will not be measured but will be paid for at the Contract lump sum price for the pertinent Engineers Office specified.  Payments will be made in installments as outlined below until the entire Contract lump sum price is exhausted.  No additional payments will be made.

Payment of the Engineers office will be prorated as follows.

- 50 percent of the Contract lump sum price will be payable on the first monthly estimate after the complete installation of the Engineers Office.

- 10 percent will be paid on each of the next 4 monthly estimates.

- The final 10 percent shall not be paid until the office is removed and the area is restored.

Each of the 6 payments will be paid out in equal amounts on each location plus or minus 1 cent per location.  The payment will be full compensation for site preparation, utility costs, all specified furnishings, to provide, equip, clean, maintain, insure, remove and dispose of the office, restore the site, recycling, and for all material, labor, equipment, tools, and incidentals necessary to complete the work.