Category 100

Preliminary

Only used in ID/IQ Contracts

SECTION 104.02 — Maintenance of Traffic (MOT)

104.02.04 MEASUREMENT AND PAYMENT

DELETE:  The first paragraph “Unless otherwise specified, Maintenance of Traffic will not … Payment of the Contract lump sum price will be prorated… will be the number estimated to complete the work.” in its entirety.

INSERT:  The following.

A bid item has been established for the Maintenance of Traffic. Maintenance of Traffic will be measured and paid for at the Contract price per unit day.  Maintenance of Traffic shall be paid once per day per each individual task.   This item has a minimum allowable bid of $X,XXX.00 per day per task and a maximum allowable bid of $X,XXX.00 per day per task.

Minimum and Maximum allowable bid must be filled out and may be different for each office. The values are to be determined by the PM and their office.

The payment will be full compensation for all engineering and work related to the development and application of the TCP(s), as well as all related items of work including furnishing, placement, maintenance, removal, reinstallation, and relocation of devices; and the necessary labor, tools, equipment and incidentals such as lights, Traffic Manager, etc., for which a specific bid item has not been established, to ensure the desired result of a safe and efficient work zone.   Unless an item is found in the schedule of prices, Flagging Operation, Automated Flagger Assistance Devices, Temporary Orange Construction Fence, Cones/Barrels, Barricades, Temporary Barriers and End Treatments, Reflective Markers, Delineators, Temporary Pavement Markings, Arrow Panels, Detours, and Signs for temporary traffic control will be incidental to the Maintenance of Traffic. When bid items have been established for temporary traffic signs, plastic drums, and traffic cones, these items will only be paid once in the contract.  After initial payment, all use and relocation of these items will be incidental to the Maintenance of Traffic item.

The payment will be full compensation for relocating, turning, completely covering, and uncovering or removing and resetting, maintaining in like new condition, and cleaning existing and temporary traffic signs and other traffic control devices.  The payment will include the inventory of all existing pavement markings and the treatment of any other traffic control device not included in these Specifications but necessary for the fulfillment of the Contract requirements and implementation of the approved Traffic Control Plan, and for all material, labor, equipment, tools, and incidentals necessary to complete the work.

Payment will be made for this item using the following guidelines:

- Time charges will begin when the first sign is installed and shall end when the last sign is picked up.

- For partial unit days:

| Time on project | up to 2 hours | between 2 and 4 hours | over 4 hour |
| --- | --- | --- | --- |
| Payment | 0.25 Unit Days (UD) | 0.5 UD | 1.0 UD |

- If night work is scheduled, the contractor will be paid a maximum of 1 UD.  There will not be a UD payment for each calendar day involved in a night shift of work.