Category 100

Preliminary

To be used only on XB Contracts.

SECTION 108 — Mobilization and Demobilization

108.04 MEASUREMENT AND PAYMENT

DELETE:  Subsection 108.04 Measurement and Payment in its entirety.

INSERT:  The following.

108.04 MEASUREMENT AND PAYMENT

Mobilization and Demobilization will not be measured but will be paid for at the Contract lump sum price per location as described in the Item Description.

Payment of the Mobilization and Demobilization item will be made according to the following payment schedule.

- 50 percent of the Mobilization and Demobilization will be paid in the first monthly estimate after the Contractor has started work at a location established in the contract.

- 40 percent of Mobilization and Demobilization will be prorated and paid in equal amounts on each of the next four monthly estimates.

- 10 percent or the remaining balance of Mobilization and Demobilization will be paid in the month following work being completed at the location established in the contract.

Payment of the Mobilization and Demobilization item will not be made more than once, even if the Contractor may have, for any reason, shut the work down on the project or moved their equipment away from the project and then back again.

The cost of all required insurance and bonds will be incidental to this item.

If the Mobilization and Demobilization item is not provided, the cost of mobilization and demobilization, including the required insurance and bonds, will be incidental to the other items specified in the Contract Documents.  The payment will be full compensation for all material, labor, equipment, tools, and incidentals necessary to complete the work.