Category 100

Preliminary

To be used only on ID/IQ Contracts.

SECTION 108 — Mobilization and Demobilization

108.04 MEASUREMENT AND PAYMENT

DELETE:  Subsection 108.04 Measurement and Payment in its entirety.

INSERT:  The following.

108.04 MEASUREMENT AND PAYMENT

Mobilization and Demobilization will not be measured but will be paid for at the Contract lump sum price not to exceed 3 percent of the adjusted contract amount.  The adjusted contract amount is defined as the total Contract amount less the lump sum bid for Mobilization and Demobilization.  If the amount bid for this item exceeds 3 percent of the adjusted contract amount, the bid shall be rejected as not responsive.

A Mobilization/Demobilization payment equivalent to 20 percent of the cost of the work items associated with the first task (excluding any item with a fixed price at bidding) will be paid within the first monthly payment estimate after work has started on that task.  For all tasks after the first one, 5 percent of work items associated with each task (excluding any item with a fixed price at bidding) will be paid within the first monthly payment estimate after work has started on each individual task.

If any remaining amount exists in this item at the end of the Contract, it will be paid out in its entirety with the final contract payment.  If the item is exhausted before the end of the Contract, additional tasks would be assigned with no Mobilization/Demobilization payment because the established item value reached the maximum cap.

Payment of the Mobilization and Demobilization item will not be made more than once for the same task, regardless of the fact that the Contractor may have, for any reason, shut the work down on the task or moved their equipment away from the task and then back again.

The cost of all required insurance and bonds will be incidental to this item.

If the Mobilization and Demobilization item is not provided, the cost of mobilization and demobilization, including the required insurance and bonds, will be incidental to the other items specified in the Contract Documents.  The payment will be full compensation for all material, labor, equipment, tools, and incidentals necessary to complete the work.