CATEGORY 875

UTILITIES

SECTION 875 — UTILITIES STATEMENT

875.01 DESCRIPTION

This Section 875 provides information relevant to performance of utility work by the Contractor and/or the utility owners and identifies specific requirements to be met by the Contractor relating to utility relocations.  The information contained in this Section 875 is to assist the Contractor in developing strategies to manage the activities associated with relocating utilities in a defined manner as well as identifying any existing known utilities within the project limits.

875.02 MATERIALS

Not Applicable.

875.03 CONSTRUCTION

875.03.01 General.

875.03.01.01 Utilities That Potentially Conflict with the Project. The Contractor’s attention is directed to the possible presence of existing underground and overhead water, sewer, gas, telecommunications, electric, and related house connections.  SHA also owns and maintains utilities including, but not limited to,0-6-20 traffic signals, electric, interconnect, fiber optics, automatic traffic counters (ATR’s), CCTV cameras, weather stations, dynamic message boards, street and sign lighting, storm drains. The Contractor’s attention is called to the requirements of Sections; GP-2.04, GP-4.02, GP-5.05, and GP-7.17.

The accuracy of information provided by the SHA in the IFB (Information for Bid) drawings regarding utilities is not necessarily guaranteed.  Refer to 875.03.01.13(a) – Utility Responsibility List for certain additional requirements applicable to the utility work (e.g. schedule constraints).  This information is provided for the Contractors’ use and understanding as the Contractor deems appropriate, subject to verification.  Further investigation as described in 875.03.02.01 is the responsibility of the Contractor upon the Award.  The SHA has not evaluated potential conflicts with appurtenances to utility facilities or service lines.

If information regarding underground utilities contained in the Utility Data proves to be inaccurate, the Contractor may be entitled to an equitable adjustment in accordance with GP-4.05 and GP-5.14, but only if the inaccuracy is material.  Refer to 875.03.01.03 for additional information regarding inaccuracies that will be considered material.  The Contractor, in coordination with the SHA, shall assist in resolving all utility conflicts on the Project.

875.03.01.02 Utility Data.  The Utility Data includes information with respect to existing utilities collected from various sources as defined below:

- IFB Plans. The IFB Plans are the highway construction plans provided by the SHA with the IFB.  Typically, the IFB Plans show a mosaic of the existing utilities within the project limits in conjunction with the proposed highway improvements.  This information is based on information collected from utility owners’ record plans and as-built drawings.

This information is NOT field-verified and is simply for the Contractor’s information.  Except as specified in 875.03.01.03(a)(b), the SHA makes no representation regarding the accuracy of the utility information provided in the IFB Plans.

- Utility Designation Data.  Utility designation data was field-collected using surface technology which identifies the existence of a utility and its horizontal location is accurate to ± 0.5 feet.  Vertical location is not field-verified.  This method is less accurate than 875.03.01.02(c).

- Utility Test Holes or Surveys.  Test hole information was field-collected utilizing necessary equipment to uncover buried utilities at a single point.  Once uncovered, the utility’s horizontal and vertical location was verified.  In some instances, manhole covers were removed, and inverts surveyed identifying a manhole’s location and pipe invert elevations.  This is the most accurate engineering data available but is only accurate to ± 0.1 feet, horizontal and vertical, at the test site along a linear utility.

- Utility Relocation Plans.  The proposed Utility Relocation Plans are provided by the Utility Owner.  Overhead utilities may not have been quantified by the Utility Designation Data and are the responsibility of the individual utility to identify and accurately describe in the Utility Relocation Plans.    Any additional Temporary Construction Easements or rights-of-way requested by the utilities prior to relocation efforts must be identified in the Utility Relocation Plans and identified by SHA and confirmed acquired.  Any advance clearing, grading, grubbing, or preparation of construction entrances necessary for utility relocation must be identified in the Utility Relocation Plans and planned for by the Contractor as first order of business to maintain the Utility Relocation schedule.  Depending on the Contract, the utility work identified in the Utility Relocation Plans may be utility work to be performed by the Contractor, included in the Contract Documents; or by others such as the Utility Owner.  This information is based on information collected from utility owners’ record plans and as-built drawings.

- Utility Responsibility List.  The Utility Responsibility List is an inventory of preliminary determinations made by the SHA regarding potential conflicts between the Project and existing utilities, based on a review of the IFB Plans and the information regarding utilities.  Refer to 875.03.01.13(a)– Utility Responsibility List for more information.

875.03.01.03 Data Considered Materially Inaccurate.  The information regarding utilities in the Utility Designation Data shall be considered materially inaccurate for purposes of GP-4.05 and GP-5.14, only as follows:

- The existence of an underground utility (excluding appurtenances and service lines) that conflicts with the Project shall be considered a material inaccuracy if the utility is not identified at all in the Utility Designation Data.

- Information in the Utility Designation Data (including test hole, designation and Utility Matrix data) regarding the size of an underground utility shall be considered materially inaccurate if the following applies: with regard to any difference (whether larger or smaller) between the utility’s actual inside diameter (the “actual size”), excluding appurtenances and the inside diameter indicated for such utility in the Utility Designation Data (the “stated size”):

- If the utility’s actual size differs from the stated size by 2 or more standard pipe sizes.

- Inaccuracies in the information regarding the location of an underground utility based on test hole and survey data shall be considered material only if: (1) the utility’s actual centerline, at the location of the test hole or survey, is more than two feet distant from the horizontal centerline location shown in that information, and/or (2) any point or feature of the utility at the location of the test hole or survey is more than one foot distant from the elevation shown for that point or feature.  If no elevation is shown for a particular utility, then vertical location is not grounds for finding material inaccuracy with respect to such utility.

- Inaccuracies in information regarding the location of an underground utility based on utility designation information shall be considered material only if the utility’s actual centerline location is more than five feet distant from the horizontal centerline location shown in that information, without regard to vertical location.

- No other inaccuracies in the utility information in the Utility Designation Data shall be considered material.

875.03.01.04 Utility Agreements.  For utility work included in the project, the SHA may have entered into Utility Agreements with certain utility owners addressing various requirements relating to the impacted utilities affecting the Contractor and/or the utility work.  Copies of any Utility Agreements, if any, are set forth in Appendix B to this Section 875.  If, after the Proposal Date, the SHA enters into any additional agreements with utility owners affecting the Contractor and/or the utility work, such agreements shall be added to Appendix B by Change Order.

Comply with all Utility Agreements as well as with any agreements it (the Contractor) enters into with utility owners in connection with the Project.

875.03.01.05 Scope of Utility Work.  Relocation of a Utility may be necessary in order to accommodate the Project for either or both of the following reasons: (a) a physical conflict between the Utility and the Project (including its construction, operation, maintenance or use), and/or (b) an incompatibility between the Project as designed and the Utility based on the requirements of the applicable Utility Standards and/or applicable Governmental Rules (even though there is no physical conflict).  The limits of Relocation of existing Utilities extend as far as is necessary to accommodate or permit construction of the Project in accordance with the foregoing, whether inside or outside the Project right-of-way.  The Contractor’s obligations apply to all utilities impacted by the Project, whether or not the SHA has entered into a Utility Agreement with the affected utility owner(s).

(a) Included in Scope.  The Contractor’s Scope of Work is to insure the final evaluation and confirmation of all utility impacts within the project limits or within the proximity of the project limits with each utility owner.  This scope also includes providing, when necessary, any preliminary work that may facilitate the Utility Relocation work’s provided relocation schedule.  The Contractor’s Utility Coordinator will be required to provide assistance with any Utility Relocation Conflicts that may arise and develop a Conflict Resolution in a reasonable time frame to prevent any relocation delays.  The Contractor’s Work includes all work related to existing utilities that is necessary to accommodate the Project, other than work that the Contract Documents specifically identify as the responsibility of the utility owner or of the SHA.  In general, this includes ensuring that existing facilities and their relocation will be capable of providing service at least equal to that offered by the existing facilities as of the Proposal Date, unless the utility owner has specified a lesser replacement.  Betterments are not included in the work unless otherwise specified pursuant to 875.03.01.11 herein below.  Refer to the General Provisions for additional requirements.

The Contractor’s responsibilities include:

- Designating a Utilities Coordinator to be the single point of contact (SPOC) for all utility-related Project activities;

- Identifying potential Utility Impacts, verifying locations and all other necessary information about utilities, and providing monthly updates of the Progress Schedule reflecting Utility Relocations as specified in 875.03.01.10;

- Constructing Relocations (where applicable) in accordance with the Utility Agreements (if any), this Section 875 and other requirements of the Contract Documents, except where the Utility Owner is assigned such responsibility pursuant to 875.03.01.13(a);

- If the Contractor discovers a utility requiring relocation that was not previously identified in the utility information included in the Utility Data, undertaking the efforts necessary to identify its ownership and all other necessary information about such utility;

All activities and obligations assigned to the SHA and/or to the Contractor in the Utility Agreements, subject to the exceptions set forth in 875.03.01.05(a);

- All activities necessary or determined by the Contractor to be convenient in connection with Incidental Utility Work (Refer to 875.03.02.06(a) for more information.);

- All coordination with utility owners required in connection with the Project or utility work;

- The Contractor’s Utility Coordinator will arrange to have a utility inspector/supervisor available to monitor the work;

- All other utility work specified in the Contract Documents as the Contractor’s responsibility;

- Resolving all Relocation Conflicts between the utilities;

The Contractor has the authority to stop any relocation utility work that may cause personal injury to workers, pedestrians, traffic control, or damage to the environment.

If it is necessary to have utility facilities braced and/or supported at any time during the course of this project, it will be the Contractor’s responsibility to coordinate activities with the utility owner.  Refer to 875.03.02.06(b) for more information.

(b) Excluded from Scope.  The Contractor’s responsibilities do not include any of the following:

- Billing for and collecting any payments due the SHA from the utility owners (However the Contractor shall provide any estimates and invoices, maintain the necessary records therefore, and provide supporting documentation as may be requested by the SHA for any utility related work performed by the Contractor.);

- Paying to any utility owner reimbursement owed by the SHA for work performed by or on behalf of the utility owner or costs incurred by the utility owner in connection with a relocation (provided that the foregoing exclusion shall not limit the Contractor’s obligations to reimburse the SHA for certain payments made by the SHA to utility owners, to indemnify the SHA and/or the utility owners with respect to certain matters, and to repair damage caused to utilities by the Contractor, as specified in the Contract Documents);

- Obtaining access to or rights or interests in property for the benefit of the utility owners (Refer to 875.03.02.09 for more information);

- Providing any insurance exceeding the requirements stated in the Contract Documents or any Agreements that the SHA may have entered into with the Utility Companies;

- Negotiating with utility owners to resolve issues relating to the determination of responsibility for costs of the utility work (as between the SHA and the utility owner); and,

- Any costs necessary by SHA for additional (new) utilities relevant to the project such as new electrical services for signs or communications requests for signs, cameras, or any other permanent or temporary devices.

(c) No Delegation of SHA Rights Under Utility Agreements.  Delegation of responsibilities under the Utility Agreements to the Contractor shall not be deemed to constitute an assignment of the SHA’s rights thereunder, and the SHA expressly reserves its rights thereunder to provide approvals, consents, permissions, satisfactions, agreements and authorizations.  The Contractor shall have no right to collect reimbursement from utility owners for work performed pursuant to the Contract Documents.  The foregoing does not apply to any Betterments or other utility owner projects performed by the Contractor by separate agreement and not included in the work, as described in 875.03.01.11 - Betterments.

875.03.01.06 Standard of Care Applicable to Utility Work.  Contact Miss Utility, as described in 875.03.01.13(b)(1), at least 2 full business days in advance of any work. For SHA owned facilities, contact the appropriate SHA office or division, as described in 875.03.01.13(b)(3), at least 3 business days in advance of any work.

Carry out its work so as to avoid damage and keep Utilities satisfactorily maintained and functional.  Do not move or remove any utility without the utility owner’s written consent unless otherwise directed by the SHA.  At the completion of the work, the condition of all utilities shall be safe and permanent.

If the Contractor is to perform Utility Work as per this Section 875, the Contract Documents, and/or a Utility Agreement, it shall be necessary that the existing facilities remain in service until the new construction is complete and placed in service.  The Contractor will prepare a plan to keep the facilities in service and submit copies to the SHA’s Procurement Officer and the appropriate Utility Owner for review and approval at least 10 business days prior to the start of work.  In addition, when adjustments are required, establishment of lead times are necessary to meet the applicable utility schedule and coordination with the Contractor’s work operation.

If any utilities are damaged, notify the affected utility owners as specified in 875.03.02.02.  (Under the Annotated Code of Maryland Public Utilities Article Title 12).  The utility owners may require the damage caused by the Contractor to be repaired at the Contractor’s expense.  If the Contractor fails to make any required payment within 30 days after the repairs have been completed and Contractor’s receipt of the utility owner’s invoice therefore, the SHA may pay the utility owner from the SHA’s funds and deduct an amount sufficient to cover the cost from any moneys due or that may become due to the Contractor under the Contract.

875.03.01.07 Coordination Requirements.  Provide information as required and maintain close coordination with the SHA and utility owners to achieve timely relocations.  Utility coordination responsibilities of SHA and the Contractor are as follows:

(a) SHA Coordination Requirements.  The SHA remains responsible for coordinating with utility owners regarding payments owing under the Utility Agreements and for collecting any payments owing from utility owners with respect to the Work.  For previously unidentified facilities encountered within the Project, the SHA will be responsible for determining cost responsibility for any necessary Relocations of such facilities (with support from the Contractor as identified herein), and for negotiating payment terms with the utility owners for such Relocations.

(b) Contractor’s Coordination Requirements.  The Contractor is responsible for coordinating its sequence of construction with the utility owners and with utility work to be performed by or on behalf of utility owners.

- Keep utility owners well informed of construction schedules and notify the utility owners at least 3 business days in advance of any work near the utility owners’ facilities (other than on the utility owner’s own facilities), and provide all other notifications to utility owners of utility owner obligations, Contractor activities, etc. as required by the Utility Agreements;

- Keep utility owners well informed of changes that affect their own Utility facilities;

- Give the utility owners at least 14 business days' prior notice of potential impacts to service;

- Ensure that utility owners are involved in making the decisions that affect their own facilities so that utility owners can provide uninterrupted service to customers or to minimize interruption of those services;

- Coordinate the Contractor’s sequence of construction and utility relocations with the temperature, seasonal or other constraints associated with any required outages of utility services.

- Cooperate with the utility owners to solve relocation/installation issues consistent with the scope of the Contractor’s work as otherwise set forth in the Contract Documents and without causing the SHA to incur any unnecessary expense to the Project, or the utility owners;

- Coordinate with those utility owners who perform their own utility work (either with their own forces or through a contractor) by scheduling adequate time to accomplish the utility work;

- Review each utility facility and consider its effect on the Project.  If necessary, physically confirm the presence of underground facilities in areas of potential conflict by test holes or other means/methods prior to the start of work;

- Develop procedures for addressing utility conflicts discovered during construction;

- Develop, negotiate and provide a schedule in coordination with the utility owners for the design and construction of all Relocations.  Identify critical activities and sequences as they affect the utility owners and plan to effectively mitigate impacts;

- Through its designated Utilities Coordinator, coordinate, cooperate, and work with the individuals on the Contractor’s utility contact list (initially, the list set forth in 875.03.01.13, to be updated as new or substitute contacts are identified);

- Notify the SHA in advance of any meeting with a utility owner’s representative scheduled by the Contractor and allow the SHA the opportunity to participate in the meeting.  Also provide to the SHA copies of all correspondence between the Contractor and any utility owner, within seven (7) business days after receipt or sending, as applicable;

- Monitor the progress of utility owner work and notify the SHA if the Contractor has cause to believe that the utility owner will not meet specified time frame(s) for construction, relocation, abandonment, or removal of utility-owned facilities. (which notice shall be provided to the SHA within 24 hours of discovery); and

- Provide support to the SHA as requested.

875.03.01.08 Meetings and Coordination.  Within 30 days of the Notice to Proceed, schedule initial meetings with each utility owner, the Contractor and the SHA and shall schedule subsequent meetings as required.  These meetings are for reviewing all items related to the utility work, including all items which affect the Baseline Progress Schedule, the time required to procure construction material and the periods of time utility service may be interrupted.

Jointly schedule utility meetings with the SHA at least monthly.  The Contractor and the SHA will jointly develop the agenda for these meetings.  All meetings pursuant to this 875.03.01.08 shall include the Contractor’s and the SHA’s key personnel with responsibilities for utilities.  Provide minutes to all participants in accordance with 875.03.02.05 and shall also provide the minutes (or appropriate excerpts) to representatives of affected utility owners not present at the meeting.

875.03.01.09 Initial Progress Schedule and Scheduling Utility Relocation Work.  In accordance with GP 8.04 of the Specifications and as required by Section 109 – Project Schedule, provide an initial Progress Schedule within 30 days after issuance of the initial Notice to Proceed to the SHA showing all proposed Utility Relocations including those to be performed by the Contractor and those relocations to be performed by the Utility Companies or the Utility Company’s subcontractors.  The initial Project Progress Schedule and monthly updates shall allow sufficient time for utility owners to accomplish the tasks and activities for which they are responsible, consistent with any times specified in:

(a) the Utility Agreements;

(b) the coordinated utility work schedules identified in 875.03.01.07(b); and

(c) the utility owners’ schedule constraints described in 875.03.01.13(a).

For any utility relocation work performed by others, concurrent with the Contractor’s work, allow the utility owners time during the contract for the utilities to relocate their facilities including the lead time notifications necessary for the utilities to schedule their relocation work.  For utility pole relocation work, the Contractor may be required to complete clearing and grubbing and grading to within one foot of planned elevation prior to placing new poles, as well as protecting and maintaining existing utility poles at grade.

875.03.01.10 Updating the Project Progress Schedule and Utility Relocation Schedules.  Update and distribute the Progress Schedule with Utility Relocation Schedules monthly to reflect all changed information then known to the Contractor and shall distribute copies for discussion at scheduled utility meetings.  Each Progress Schedule shall be marked to identify changes from the previous version.

Any submittal by the Contractor to vary the sequence of work and/or perform concurrent work in multiple phases differing from any recommended maintenance of traffic phasing, must be accompanied by an updated Progress Schedule reflecting all utility relocations and adjustments.  The Contractor shall be responsible, upon gaining approval, for coordinating utility relocations and adjustments with the affected utility owners, SHA’s Procurement Officer and the District Utility Engineer.  All requirements and lead times as stated in this Section 875, Utility Agreements and elsewhere in the Contract Documents will remain in effect unless written approval from the utility company and the District Utility Engineer is received by the Contractor prior to commencing any requested work.

The Utility Relocation Schedule shall also be inserted into the Project’s CPM Schedule per Section 109.  Where utility owners will design or design and construct any required relocations for their facilities, the Contractor shall account for these utility design timeframes (if any) along with the utility construction timeframes in the Progress Schedule.  Review the Utility Relocation Plans for consistency with the Project and the Contractor’s proposed construction operations.  If the Contractor discovers an inconsistency with the Utility Relocation Plans, notify the SHA immediately upon discovery.

875.03.01.11 Betterments.  Upgrades to or improvements of existing utilities is considered a betterment.

- The original scope of the Work may include Betterments if specified in the Contract Documents.  Betterments may also be added to the Work by Change Order.  Further, the Contractor and the utility owners may enter into separate agreements for design and construction of additional Betterments or utility owner projects not related to a Utility Relocation, through contracts to which the SHA is not a party and has no responsibility, actual or implied, subject to compliance with the SHA’s permitting process.

- Do not proceed with any Betterment that is:

(1) Not specifically approved by the SHA; or

(2) Incompatible with the Project or cannot be performed within the constraints of the applicable Governmental Rules, Governmental Approvals and the Contract Documents, including the Completion Deadlines.  Promptly notify the SHA of any requests by utility owners which the Contractor considers to be Betterments.  If the Contractor and the utility owner disagree as to whether a particular utility owner request or requirement is a Betterment, dispute resolution shall be in accordance with 875.03.01.12.  Keep the SHA informed as to the status of negotiations with Utility Owners concerning such requests, including providing documentation to the SHA as requested by the Procurement Officer.

- Evaluate the impact on the project schedule of proposed Betterments and shall promptly notify the SHA if it determines that any Betterment under consideration would be likely to result in a schedule delay.

875.03.01.12 Failure of Utility Owners to Cooperate.

- Contractor Obligations.  Make diligent efforts to obtain the cooperation of each utility owner as necessary for the Project.  Notify the SHA immediately if:

(1) The Contractor believes that any utility owner would not undertake or permit a Relocation in a manner consistent with the timely completion of the Project;

(b) The Contractor becomes aware that a utility owner is not cooperating in providing needed work or approvals; or

(c) Any other dispute arises between the Contractor and any utility owner with respect to the Project, including any dispute with respect to whether or not a particular utility owner request or requirement is a Betterment.

- SHA Assistance.  After giving notice in accordance with 875.03.01.12(a), continue to diligently pursue the utility owner’s cooperation or to otherwise resolve the dispute.  Such request for assistance shall be accompanied by evidence satisfactory to the SHA showing that the Contractor has made diligent efforts to obtain the utility owner’s cooperation or to otherwise resolve the dispute, but that such efforts have not succeeded.  The SHA shall determine, in its sole discretion, what efforts it will undertake to obtain the utility owner’s cooperation.  Cooperate with the SHA in any efforts to obtain utility owner cooperation and/or to resolve disputes with them including, in connection with any lawsuit or alternate proceedings undertaken by the SHA for such purpose, having the Contractor’s staff and consultants act as witnesses in such lawsuits and proceedings and providing testimony, information, reports, graphs, photos, plans, renderings and similar materials to the SHA’s counsel at the Contractor’s expense.  Any assistance provided by the SHA shall not relieve the Contractor of responsibility for satisfactory performance of the requirements of the Contract Documents and timely completion of all Relocations.

- Incidents of Force Majeure.  Utility Company’s may direct that any Utility Company in-house personnel and/or Utility Company approved contractor personnel (together “Personnel”) performing work on the Utility Company’s Relocation Work be removed from the Project if there should occur exigent circumstances within the Utility Company’s service area, caused by an “Incident Of Force Majeure” or similar Company system-related emergency, including, but not limited to accidental and/or intentional damage to Utility Company’s facilities, such as:

- Major Storm Event

- Floods

- Strikes

- Civil Unrest

- Acts of Terrorism

“Major Storm Event” shall have the definition set forth in COMAR § 20.50.01.03 (B), as amended from time to time (a “Major Storm” resulting in “more than 10 percent or 100,000 whichever is less, of the [local electrical utility’s] customers experiencing a sustained interruption of electric service; and restoration of electric service to these customers takes more than 24 hours”; or 49 CFR § 191.3 (“an event involving release of gas from a pipeline and a death or personal injury involving hospitalization or estimated property damage including the cost of gas loss of $50,000 or more; or an event that is significant in the judgment of the Utility Company”).

It is understood, delays attributable to Incidents Of Force Majeure are beyond the control of the SHA.  Loss of time and any concomitant delay in completion of the Relocation Work caused by such Incidents Of Force Majeure shall be defined as an “Excused Delay”.  The Contractor shall indemnify and hold harmless the SHA against and from any and all liability or claim of liability for delays attributable to Incidents Of Force Majeure.

875.03.01.13 Utility information.

- Utility Responsibility List.  This 875.03.01.13(a) specifies the entity responsible for design and construction of Utility Relocations for each utility owner and any additional specific requirements or conditions.  In the event of any conflict between the following Utility Responsibility List and the terms and conditions of a Utility Agreement, the Utility Agreement shall prevail.  If no Utility Agreement exists covering a particular Relocation activity, the responsibility for the design and construction of that Relocation activity shall be as specified in the Utility Responsibility List.

If required by the applicable Utility Agreement, use only subcontractors approved by the affected utility owner for the utility work, either by inclusion on a pre-approved list or otherwise in accordance with the Utility Agreement. (Refer to Appendix C for a list of subcontractors that have been pre-approved by utility owners.)

| UTILITY NAME Responsibility | Additional Specific Requirements or Conditions |
| --- | --- |
| (Utility Company) 2* | (Utility Company) maintains (Facility type & description) facilities within the limits of the project. The Contractor will relocate existing facilities and install new facilities as part of this contract. Refer to Section (876 – 880) of the special provisions for additional information. |
| (Utility Company) 1 | (Utility Company) maintains (Facility type & description) {aerial and underground facilities (both distribution and transmission) throughout the entire length of this project} and in conjunction with (Any Other Utility Company) will be relocating them (concurrently with) (prior to the start of) the actual construction portion of this job. |
| (Utility Company) |  |

Responsibility Key:

1 - Utility Owner will design and construct

2 - Utility Owner or Consultant will design, Contractor will construct

* Utility owner will perform cable installation and splicing.

(b) Contact Information.

- Miss Utility.  All notifications to the above utility companies and “MISS UTILITY”, at http://www.missutility.net/maryland/, shall be given 2 full business days in advance (The day of notification does not count.) of working in the area of each specifically affected utility.   In compliance with the Annotated Code of Maryland Public Utilities Article Title 12, the notification to “MISS UTILITY “is required whenever any excavating or similar work is performed.

- Utility Owned Facilities.  The following known utility companies may have existing facilities and may have adjustments/installations within the limits of this Contract:

| UTILITY & ADDRESS | CONTACT PERSON | PHONE NUMBER | COMMENTS |
| --- | --- | --- | --- |

- SHA Owned Facilities.  Regarding stake out of SHA-owned facilities (a minimum advance notice of 3 full business days’ is required), please refer to the following:

- TRAFFIC DEVICES: contact the Signal Operations Team at 410-787-7650.

- CHART / ITS (Intelligent Transportation System) DEVICES: contact Communication Division at 410-747-8590.

- ATR DEVICES: contact Traffic Monitoring System Team of the Highway Information Systems Division at 410-545-5509.

- For SHA-owned lighting, contact _________________ at ___-___-____.

875.03.02 construction requirements.

875.03.02.01 Identification of Facilities.  Comply with Title 12 of the Public Utilities Article of the Annotated Code of Maryland to mark utility locations.

As a first order of work, the Contractor shall be responsible for determining the exact location, type, and all other relevant information about each utility in the Project area.  If utilities not previously identified are discovered that may be affected by the Project, notify the SHA within 24 hours of discovery.

In coordination with SHA, take the lead in identifying the affected utility owner.  If a Utility Agreement is in place with the utility owner, the Contractor shall be responsible for providing notifications in accordance with the Utility Agreement.  If the utility owner has not previously entered into a Utility Agreement, the SHA will be responsible for notifying the utility owner and arranging for utility work to proceed, with coordination and other assistance from the Contractor as may be requested by the SHA.

The Contractor is required to contact each utility owner that Miss Utility marks in the field to determine their minimum utility facility clearance.  Document Miss Utility marks in the field by taking pictures and maintaining accurate records.  Infrastructure shall not be placed within the utility owner’s clearances.

The Contractor must adhere to any and all utility owner requirements for vertical and horizontal clearances.

Locate all existing utilities and be responsible for their safety.  Confirmation of existing utilities shall be made by means of safe excavation (non-mechanized non-intrusive digging).  Any form of HAND DIG or SOFT DIG is acceptable for determining vertical and horizontal location of any utility located within the area of disturbance.  All work shall be in accordance with all state and federal guidelines for HAND DIG or SOFT DIG within 18 Inches of any marked utility.

Prior to ordering any storm drain materials, locate and dig test holes on any underground facilities that appear to be in conflict to determine if conflicts exist.  Review the location of the existing and proposed aerial utilities to determine if conflicts exist.  In the event that conflicts may be possible, this information shall immediately be forwarded to the SHA and the Utility for review and resolution.  Material ordered prior to obtaining test pit information will not be considered in any request from the Contractor for any equitable adjustments due to existing utility conflicts.

Underground service connections are typically not shown on the plans.  Therefore, the Contractor must communicate with the utility companies to determine where services exist, dig test holes if necessary and if there are conflicts, contact the SHA and the Utility to determine how the conflict can be resolved.  No compensation will be considered for rework due to failure to follow this procedure.

The locations of the proposed poles shown on the concept plans (Contract drawings), if any, are provided for informational purposes only and are based off the utility company design plans, not the actual as-built locations.  There is no guarantee of the accuracy of the locations and it is the responsibility of the Contractor to determine the actual location of the poles, and to notify the SHA of any discrepancies to avoid any unnecessary pole relocations.

875.03.02.02 Utility Damage.  Locate all existing utilities and all existing SHA owned facilities and be responsible for their safety.  Should any existing utilities or SHA owned facilities be damaged or destroyed due to the operations of the Contractor, the damaged or destroyed components shall be immediately replaced or repaired as necessary to restore the utility or SHA owned facilities to a satisfactory operating condition.

If the Contractor is negligent in complying with 875.03.01.06 - Standard Care Applicable to Utility Work or 875.03.01.13(b) - Contact Information, these repairs or replacements shall be at no additional expense to the SHA or the owner of the utility.

- Utility Owned Facilities.  Immediately report any and all damage to utility facilities to the utility owner and the SHA.  In the event of a water or sewer main break, immediately notify the Maryland Department of the Environment in addition to the owner of the water or sewer facility and the SHA’s Procurement Officer.

- SHA Owned Facilities.  Immediately report any and all damage to SHA owned facilities to the appropriate SHA office or division.

- Utility Damage Report.  The Contractor shall be responsible for completing a Utility Damage Report form to use in the event a utility or SHA owned facility is damaged.  Complete and submit a Utility Damage Report to the Procurement Officer within three (3) working days of damage.  Refer to Appendix “A” for a copy of the report.

875.03.02.03 Standards and Requirements.  All utilities along the Project, whether designed and/or constructed by the Contractor or the utility owner, shall be placed in accordance with applicable Governmental Rules, including the SHA’s utility regulations and policies, Utility Policy Manual and Utility Procedure Manual, the applicable Utility Standards, and any other requirements specified in the Contract Documents.  Unless the SHA advises the Contractor otherwise, the Project will be subject to 23 CFR Part 645 Subpart A (including its requirements as to plans, specifications, estimates, charges, tracking of costs, credits, billings, records retention, and audit) and associated policies.  Notwithstanding the order of precedence set forth in TC3.01, in the event of any conflict within the Contract Documents or between the requirements specified in the Contract Documents and any applicable Utility Standards, additional details and more stringent requirements contained in the lower priority document will control.  Obtain clarification of any unresolved ambiguity prior to proceeding with design or construction.

875.03.02.04 Compatibility.  The Contractor shall be responsible for verifying that upon completion of the Project, each utility facility within the project limits and the SHA’s right-of-way or otherwise affected by or affecting the project is compatible with and interfaces properly with the Project.

875.03.02.05 Construction Records.  Maintain a record of the construction activities for all utility work performed by the Contractor.  Individual files shall include a record of the following information:

- Notification of construction dates;

- Records of meetings with utility owner;

- Record of utility owner inspector present at any time;

- Any revisions to the IFB Plans impacting the utility relocations;

- Any revisions to Utility Relocation Plans;

- Dates of construction completed;

- All other as-built requirements stipulated in the SHA’s Utility Regulations; and

- Any other information required by Utility Agreements.

- Utility Damage Reports.  The Contractor shall be responsible for maintaining copies of the Utility Damage Report form if any utility or SHA owned facility is damaged as part of the Contractors’ Construction Records.  Refer to 875.03.02.02(b)(1) and Appendix “A” for further information on the Utility Damage Report.

875.03.02.06 Additional Utility information and requirements.

- Incidental Relocations.  Make all adjustments to surface utility frame and covers, not limited to manholes, water valves, water meters, gas valves, and gas meters.  The cost of these adjustments shall be incidental to the bid price for the bituminous concrete as per Section 504.04 of the Specifications or the various sidewalk, driveway and curb/gutter work unless the adjustments are twelve (12) inches or greater.  In these cases, the adjustment(s) may be paid for under the pertinent line item(s).  All adjustments shall be done in accordance with the pertinent Utility Owner specifications and Standard Plates.  Contact the pertinent Utility Owner(s) at least 14 business days prior to the adjustment of any utility facility in order to ensure that the locations of all facilities are identified and proper adjustments are made prior to paving.  Request the Utility Owner to accept in writing all adjustments upon completion of work and arrange a field meeting between the Utility Owner, the Contractor, and the SHAs’ Procurement Officer.

Make all adjustments to utility service laterals.  In the event items have not been established for the adjustment and /or relocation of utility service laterals, the cost of these adjustments shall be incidental to the bid price for the work requiring the adjustment. (i.e. Storm Drains)

If vertical adjustments are needed to manholes, valves, or meters that are beyond existing pavement, but within new paved areas, be prepared to perform the necessary work and accept payment under miscellaneous pay items.

- Temporary Relocations.  If it is necessary to have utility facilities braced and/or supported at any time during the course of this project, it will be the Contractor’s responsibility to coordinate activities with the utility owner.  However, as it is impossible to determine how a Contractor will perform certain operations or how much space will be needed to perform those operations, the relocations will be based upon the utility companies’ safety and clearance requirements.  It may be necessary for the Contractor to utilize non-typical procedures in some cases and any associated costs may be incidental to the pertinent items as determined by the SHA.

- Steel Plates.  During the course of construction or relocation of underground utility facilities, it may be necessary to use steel plates for the temporary protection of an open excavated area.  At the sole discretion of and as directed by the SHA’s Procurement Officer, the Contractor shall meet any or all the following requirements (Ref. MDOT- SHA- Standards for Highway and Incidental Structures- Std. No. 104.01-85 & 104.01-86). Maintenance of Traffic signs shall be utilized in accordance with Section 11.07.01(A) Signing Steel Plates.

875.03.02.07 Instructions and Authorizations.  The Contractor shall be responsible for obtaining specific written instructions and authorization from the utility owner for any construction the Contractor performs on behalf of the utility owner.  If the Contractor has reasonable cause to believe that a utility owner performing construction work on the site does not have necessary approvals, or is in violation of the approvals, notify the SHA immediately after discovery.

875.03.02.08 Utility Owner’s Right to Inspect.  The utility owner shall have the right to inspect the work on its facilities performed by the Contractor.  The inspection shall be governed by applicable Utility Standards and the terms of the Utility Agreements.

875.03.02.09 Additional Right-of-Way and/or Easements.  Utility relocations are anticipated to be done within SHA Right-of-Way and within the project limits.  The Contractor is expected to work around the existing utility locations and work around the utilities once they are relocated.

If the Contractor determines that the Utility Relocation Work to be performed by the Contractor cannot be performed within the existing SHA Right-of-Way, demonstrate to the SHA’s satisfaction, the reasons for additional right-of-way or easements, and shall show that no other reasonable means of construction can be performed to eliminate the necessity of additional right-of-way or easements.  Additional right-of-way or easements for Relocation of utilities also can be obtained by the Utility Owner.

875.03.02.10 Guardrail and Signs.  The Contractor may be required to install new and/or adjust existing guardrail and/or signs (Temporary or Permanent) due to: (1) a requirement of the Contract Documents; (2) necessity for Maintenance of Traffic; or (3) necessity for the Contractor to perform the required Contract Work.

Install and/or adjust any guardrail and/or signs so as to take into consideration and not cause damage to any Utility-owned and SHA-owned facilities in areas within the limits of the Project.

875.03.02.11 Contract Provision Buy America.  This section only applies to projects partially or totally financed with Federal funds.

Materials used for the utility work and permanently incorporated into the project, including all materials and products supplied by the Utility Company, shall comply with the Buy America preference requirements in accordance with 23 U.S.C. 313 and 23 CFR 635.410 for iron or steel products and manufactured products, and 2 CFR part 184 for construction materials.

875.04 MEASUREMENT AND PAYMENT

Working around or protecting existing aerial and underground utilities, regardless of ownership (State or public), documenting field designating/markings, furnish and install adapter rings, bracing of overhead utility poles, removal of temporary materials from the adjusted utilities prior to placement of the proposed hot mix asphalt, use of steel plates with spans of less than five feet, removal of steel plate and asphalt wedge and the removal/resetting of guardrail and signs will not be measured for payment and the cost will be incidental to the items specified in the Contract Documents.

- Adjustments to underground vault(s) will not be measured but will be paid as lump sum per each.

- Temporary signs will be measured and paid under the (Temporary Traffic Signs High Performance Retroreflective Sheeting) pay item per square foot.

- Test pit excavation will be measured and paid under the cubic yard item.

- Utility coordination will not be measured but will be paid as a lump sum item.

Appendix “A”

UTILITY DAMAGE REPORT

UTILITY DAMAGE INFORMATION

Exact Location: _____________________________________________________________

_____________________________________________________________

Date & Time of Incident: ______________________________________________________

Reported By: ______________________________

Repaired By: ______________________________

UTILITY OWNER INFORMATION

Utility Owner: ___________________________________

Utility Owner Contact: ____________________________

Time Utility Owner Contacted: _____________________

LOCATOR INFORMATION

Locator Service: _________________________________

Date of Locate Request: __________________________

Locate Expiration Date: __________________________

Locate Log Number: _____________________________

Was Line Marked: _______________________________

Distance from Damage to Mark: ____________________

CONTRACTOR INFORMATION

Name of Supervisor: _____________________________

Name of Foreman: ______________________________

Name of Witness: _______________________________

SIGNATURES

Contractor’s Supervisor: __________________________

Utility Owner: __________________________________

Locator Service: ________________________________

DESCRIPTION OF DAMAGE:

_________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

Appendix “B”

UTILITY AGREEMENT

(If Any)

Appendix “C”

UTILITY COMPANY PRE-APPROVED SUBCONTRACTORS

(If Any)