Category 875

Utilities

SECTION 875 — UTILITIES STATEMENT

875.01 DESCRIPTION

This Section 875 provides information relevant to performance of utility work by the Contractor and/or the utility owners and identifies specific requirements to be met by the Contractor relating to utility relocations.  The information contained in this Section 875 is to assist the Contractor in developing strategies to manage the activities associated with relocating utilities in a defined manner.

875.02 MATERIALS

Not Applicable.

875.03 CONSTRUCTION

875.03.01 General.

875.03.01.01 Utilities That Potentially Conflict with the Project. The Contractor’s attention is directed to the possible presence of existing underground water and sewer (including house connections), gas, underground and overhead telecommunications and electrical utilities.  SHA also owns and maintains utilities including, but not limited to,0-6-20 traffic signals, underground electrical and interconnect, fiber optic cables, automatic traffic counters (ATR’s), (interchange) lighting, storm drains and ditches.  The Contractor’s attention is called to the requirements of Sections; GP-2.04, GP-4.02, GP-5.05, and GP-7.17.

The accuracy of information provided by the SHA in the IFB (Information for Bid) drawings regarding utilities is not necessarily guaranteed.  Refer to 875.03.01.08(a) – Utility Responsibility List for certain additional requirements applicable to the utility work (e.g. schedule constraints).  This information is provided for the Contractors’ use and understanding as the Contractor deems appropriate, subject to verification.  Further investigation as described in 875.03.02.01 is the responsibility of the Contractor upon the Award.  The SHA has not evaluated potential conflicts with appurtenances to utility facilities or service lines.

If information regarding underground utilities contained in the Utility Data proves to be inaccurate, the Contractor may be entitled to an equitable adjustment in accordance with GP-4.05 and GP-5.14, but only if the inaccuracy is material.  Refer to 875.03.01.03 for additional information regarding inaccuracies that will be considered material.  The Contractor, in coordination with the SHA, shall assist in resolving all utility conflicts on the Project.

- Utility Responsibility List.  The Utility Responsibility List is an inventory of preliminary determinations made by the SHA regarding potential conflicts between the Project and existing utilities, based on a review of the IFB Plans and the information regarding utilities.  Refer to 875.03.01.08(a)– Utility Responsibility List for more information.

- Utility Conflict Matrix.  This involves comparing depicted utility information with proposed plans (highway, bridge, drainage, maintenance of traffic, and other).  The resulting Matrix contains columns to record the physical location of each conflict, the name of the utility involved, the nature of the conflict, and the preferred resolution.

875.03.01.02 Utility Agreements.  For utility work included in the project, the SHA may have entered into Utility Agreements with certain utility owners addressing various requirements relating to the impacted utilities affecting the Contractor and/or the utility work.  Copies of any Utility Agreements, if any, are set forth in Appendix B to this Section 875.  If, after the Proposal Date, the SHA enters into any additional agreements with utility owners affecting the Contractor and/or the utility work, such agreements shall be added to Appendix B by Change Order.

Comply with all Utility Agreements as well as with any agreements it (the Contractor) enters with utility owners in connection with the Project.

875.03.01.03 Scope of Utility Work.  Relocation of a Utility may be necessary in order to accommodate the Project for either or both of the following reasons: (a) a physical conflict between the Utility and the Project (including its construction, operation, maintenance or use), and/or (b) an incompatibility between the Project as designed and the Utility based on the requirements of the applicable Utility Standards and/or applicable Governmental Rules (even though there is no physical conflict).

(a) Included in Scope.  The Contractor’s Scope of Work is to insure the final evaluation and confirmation of all utility impacts within the project limits or within the proximity of the project limits with each utility owner.  This scope also includes providing, when necessary, any preliminary work that may facilitate the Utility Relocation work’s provided relocation schedule.

875.03.01.04 Standard of Care Applicable to Utility Work.  Contact Miss Utility, as described in 875.03.01.08(b)(1), at least 2 full business days in advance of any work. For SHA owned facilities, contact the appropriate SHA office or division, as described in 875.03.01.08(b)(3), at least 3 business days in advance of any work.

Carry out its work to avoid damage and keep Utilities satisfactorily maintained and functional.  Do not move or remove any utility without the utility owner’s written consent unless otherwise directed by the SHA.  At the completion of the work, the condition of all utilities shall be safe and permanent.

875.03.01.05 Coordination Requirements.  Provide information as required and maintain close coordination with the SHA and utility owners to achieve timely relocations.  Utility coordination responsibilities of SHA and the Contractor are as follows:

- Contractor’s Coordination Requirements.  The Contractor is responsible for coordinating its sequence of construction with the utility owners and with utility work to be performed by or on behalf of utility owners.

- Keep utility owners well informed of changes that affect their own Utility facilities;

- Coordinate with those utility owners who perform their own utility work (either with their own forces or through a contractor) by scheduling adequate time to accomplish the utility work;

- Review each utility facility and consider its effect on the Project.  If necessary, physically confirm the presence of underground facilities in areas of potential conflict by test holes or other means/methods prior to the start of work;

- Through its designated Utilities Coordinator, coordinate, cooperate, and work with the individuals on the Contractor’s utility contact list (initially, the list set forth in 875.03.01.08, to be updated as new or substitute contacts are identified);

- Notify the SHA in advance of any meeting with a utility owner’s representative scheduled by the Contractor and allow the SHA the opportunity to participate in the meeting.  Provide to the SHA copies of all correspondence between the Contractor and any utility owner, within seven (7) business days after receipt or sending, as applicable;

- Monitor the progress of utility owner work and notify the SHA if the Contractor has cause to believe that the utility owner will not meet specified time frame(s) for construction, relocation, abandonment, or removal of utility-owned facilities. (which notice shall be provided to the SHA within 24 hours of discovery); and

- Provide support to the SHA as requested.

875.03.01.06 Activities Chart Project Schedule and Scheduling Utility Relocation Work.  In accordance with GP 8.04 of the Specifications and as required by Section 109 – Project Schedule, provide an initial Progress Schedule within 30 days after issuance of the initial Notice to Proceed to the SHA showing all proposed Utility Relocations including those to be performed by the Contractor and those relocations to be performed by the Utility Companies or the Utility Company’s subcontractors.

875.03.01.07 Failure of Utility Owners to Cooperate.

- Contractor Obligations.  Make diligent efforts to obtain the cooperation of each utility owner as necessary for the Project.  Notify the SHA immediately if:

  - The Contractor believes that any utility owner would not undertake or permit a Relocation in a manner consistent with the timely completion of the Project;

  - The Contractor becomes aware that a utility owner is not cooperating in providing needed work or approvals; or

  - Any other dispute arises between the Contractor and any utility owner with respect to the Project, including any dispute with respect to whether or not a particular utility owner request or requirement is a Betterment.

875.03.01.08 Utility information.

- Utility Responsibility List.  This 875.03.01.08(a) specifies the entity responsible for design and construction of Utility Relocations for each utility owner and any additional specific requirements or conditions.  In the event of any conflict between the following Utility Responsibility List and the terms and conditions of a Utility Agreement, the Utility Agreement shall prevail.  If no Utility Agreement exists covering a particular Relocation activity, the responsibility for the design and construction of that Relocation activity shall be as specified in the Utility Responsibility List.

| UTILITY NAME Responsibility | Additional Specific Requirements or Conditions |
| --- | --- |
| (Utility Company) 1 | (Utility Company) maintains (Facility type & description) facilities within the limits of the project. The Contractor will relocate existing facilities and install new facilities as part of this contract. Refer to Section (876 – 880) of the special provisions for additional information. |
| (Utility Company) 2 | (Utility Company) maintains (Facility type & description) {aerial and underground facilities (both distribution and transmission) throughout the entire length of this project} and in conjunction with (Any Other Utility Company) will be relocating them (concurrently with) (prior to the start of) the actual construction portion of this job. |
| (Utility Company) 3 |  |

Responsibility Key:

1 - Utility Owner will design and construct

2 - Utility Owner or Consultant will design, Contractor will construct

* Utility owner will perform cable installation and splicing.

(b) Contact Information.

- Miss Utility.  All notifications to the above utility companies and “MISS UTILITY”, at http://www.missutility.net/maryland/, shall be given 2 full business days in advance (The day of notification does not count.) of working in the area of each specifically affected utility.   In compliance with the Annotated Code of Maryland Public Utilities Article Title 12, the notification to “MISS UTILITY “is required whenever any excavating or similar work is performed.

- Utility Owned Facilities.  The following known utility companies may have existing facilities and may have adjustments/installations within the limits of this Contract:

| UTILITY & ADDRESS | CONTACT PERSON | PHONE NUMBER | COMMENTS |
| --- | --- | --- | --- |

- SHA Owned Facilities.  Regarding stake out of SHA-owned facilities (a minimum advance notice of 3 full business days’ is required), please refer to the following:

- TRAFFIC DEVICES: contact the Signal Operations Team at 410-787-7650.

- CHART / ITS (Intelligent Transportation System) DEVICES: contact Communication Division at 410-747-8590.

- ATR DEVICES: contact Traffic Monitoring System Team of the Highway Information Systems Division at 410-545-5509.

- For SHA-owned lighting, contact _________________ at ___-___-____.

875.03.02 construction requirements.

875.03.02.01 Identification of Facilities.  Comply with Title 12 of the Public Utilities Article of the Annotated Code of Maryland to mark utility locations.

As a first order of work, the Contractor shall be responsible for determining the exact location, type, and all other relevant information about each utility in the Project area.  If utilities not previously identified are discovered that may be affected by the Project, notify the SHA within 24 hours of discovery.

The Contractor must adhere to any and all utility owner requirements for vertical and horizontal clearances.

875.03.02.02 Utility Damage.  Locate all existing utilities and all existing SHA owned facilities and be responsible for their safety.  Should any existing utilities or SHA owned facilities be damaged or destroyed due to the operations of the Contractor, the damaged or destroyed components shall be immediately replaced or repaired as necessary to restore the utility or SHA owned facilities to a satisfactory operating condition.

If the Contractor is negligent in complying with 875.03.01.04 - Standard Care Applicable to Utility Work or 875.03.01.08(b) - Contact Information, these repairs or replacements shall be at no additional expense to the SHA or the owner of the utility.

- Utility Owned Facilities.  Immediately report any and all damage to utility facilities to the utility owner and the SHA.  In the event of a water or sewer main break, immediately notify the Maryland Department of the Environment in addition to the owner of the water or sewer facility and the SHA’s Procurement Officer.

- SHA Owned Facilities.  Immediately report any and all damage to SHA owned facilities to the appropriate SHA office or division.

- Utility Damage Report.  The Contractor shall be responsible for completing a Utility Damage Report form to use in the event a utility or SHA owned facility is damaged.  Complete and submit a Utility Damage Report to the Procurement Officer within three (3) working days of damage.  Refer to Appendix “A” for a copy of the report.

875.03.02.03 Additional Utility information and requirements.

(a) Steel Plates.  During construction or relocation of underground utility facilities, it may be necessary to use steel plates for the temporary protection of an open excavated area.  At the sole discretion of and as directed by the SHA’s Procurement Officer, the Contractor shall meet any or all the following requirements (Ref. MDOT- SHA- Standards for Highway and Incidental Structures- Std. No. 104.01-85 & 104.01-86). Maintenance of Traffic signs shall be utilized in accordance with Section 11.07.01(A) Signing Steel Plates.

875.03.02.04 Guardrail and Signs.  The Contractor may be required to install new and/or adjust existing guardrail and/or signs (Temporary or Permanent) due to: (1) a requirement of the Contract Documents; (2) necessity for Maintenance of Traffic; or (3) necessity for the Contractor to perform the required Contract Work.

Install and/or adjust any guardrail and/or signs so as to take into consideration and not cause damage to any Utility-owned and SHA-owned facilities in areas within the limits of the Project.

875.03.02.05 Contract Provision Buy America.  This section only applies to projects partially or totally financed with Federal funds.

Materials used for the utility work and permanently incorporated into the project, including all materials and products supplied by the Utility Company, shall comply with the Buy America preference requirements in accordance with 23 U.S.C. 313 and 23 CFR 635.410 for iron or steel products and manufactured products, and 2 CFR part 184 for construction materials.

875.04 MEASUREMENT AND PAYMENT

Working around or protecting existing aerial and underground utilities, regardless of ownership (State or public), documenting field designating/markings, furnish and install adapter rings, bracing of overhead utility poles, removal of temporary materials from the adjusted utilities prior to placement of the proposed hot mix asphalt, use of steel plates with spans of less than five feet, removal of steel plate and asphalt wedge and the removal/resetting of guardrail and signs will not be measured for payment and the cost will be incidental to the items specified in the Contract Documents.

875.04.01 Temporary signs will be measured and paid under the (Temporary Traffic Signs High Performance Retroreflective Sheeting) pay item per square foot.

Appendix “A”

UTILITY DAMAGE REPORT

UTILITY DAMAGE INFORMATION

Exact Location: _____________________________________________________________

_____________________________________________________________

Date & Time of Incident: ______________________________________________________

Reported By: ______________________________

Repaired By: ______________________________

UTILITY OWNER INFORMATION

Utility Owner: ___________________________________

Utility Owner Contact: ____________________________

Time Utility Owner Contacted: _____________________

LOCATOR INFORMATION

Locator Service: _________________________________

Date of Locate Request: __________________________

Locate Expiration Date: __________________________

Locate Log Number: _____________________________

Was Line Marked: _______________________________

Distance from Damage to Mark: ____________________

CONTRACTOR INFORMATION

Name of Supervisor: _____________________________

Name of Foreman: ______________________________

Name of Witness: _______________________________

SIGNATURES

Contractor’s Supervisor: __________________________

Utility Owner: __________________________________

Locator Service: ________________________________

DESCRIPTION OF DAMAGE:

____________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

Appendix “B”

UTILITY AGREEMENT

(If Any)

Appendix “C”

UTILITY COMPANY PRE-APPROVED SUBCONTRACTORS

(If Any)