## Metadata
Original Planned TIPPs for Balt Harbor TN/TP TMDL IP
M:\2022\162205734.24\Engr\Modeling\Planned TIPPs
AACo_Baltimore Harbor_TIPP_PlannedBMPs_20250318.xlsm
BaCo_Baltimore Harbor_TIPP_ PlannedBMPs _20250318.xlsm
BaCo_Gwynns Falls_TIPP_ PlannedBMPs _20250318.xlsm
BaCo_Jones Falls_TIPP_ PlannedBMPs _20250318.xlsm
AACo_Patapsco River L N Br_TIPP_ PlannedBMPs _20250318.xlsm
BaCo_Patapsco River L N Br_TIPP_ PlannedBMPs _20250318.xlsm
HoCo_Patapsco River L N Br_TIPP_ PlannedBMPs _20250318.xlsm
Original Cost Estimate for Balt Harbor TN/TP TMDL IP
M:\2022\162205734.24\Engr\Modeling
BaltHarborTidal_P6AMT_AllSummary_2025.03.05
Tab: Planned BMP Estimated Cost

## TP TMDLs
TP lbs Remaining (as of FY23 Progress modeling)
TP EOS lbs/yr
Anne Arundel | 525.6232
Baltimore | 503.9981
Carrol | 47.9228
Howard | 29.0813
Full Implementation for Baltimore Harbor Tidal TN TMDL | Reductions TP EOS lbs/yr
| Milestone 1 |  |  | Milestone 2 | Planned | Total - by County | Excess Reduction - by County
| UC Retrofit | Remediated BMPs | MEP Placeholders | Site Selection | Gap Filler
AACo_Baltimore Harbor | 11.47 | 29.0846 | 136.0367 | 388.56 | 1097.31 | 4100.4152 | 3574.792
AACo_Patapsco River L N Br | 0 | 10.0618 | 0 | 1775.16 | 652.7321
BaCo_Baltimore Harbor | 0 | 0 | 0 | 1.99 | 21.27 | 5204.8023 | 4700.8042
BaCo_Gwynns Falls | 0 | 14.5222 | 140.6 | 8.66 | 1753.1216
BaCo_Jones Falls | 0 | 11.8711 | 0 | 82.26 | 1263.3501
BaCo_Patapsco River L N Br | 0 | 0.83523 | 121.38 | 314.66 | 1470.2821
CrCo_S Branch Patapsco | 0 | 13.5479 | 0 | 503.6198 | 0 | 517.1677 | 469.2449
HoCo_Patapsco River L N Br | 0 | 84.2647 | 121.38 | 100.5125 | 186.68 | 854.183 | 825.1017
HoCo_S Branch Patapsco | 0 | 0 | 0 | 361.3458 | 0
Implementation Edited to achieve TP Target | Reductions TP EOS lbs/yr |  |  |  |  | Cost Estimate based on Median Cost/TP ($/LB reduced per year)
| Milestone 1 |  |  | Milestone 2 | Planned | Cost Estimate
| UC Retrofit | Remediated BMPs | MEP Placeholders | Site Selection | Gap Filler
AACo_Baltimore Harbor | 11.47 | 29.08 | 136.04 | 237.44 | 0 | 9750071.0858
AACo_Patapsco River L N Br | 0 | 10.0618 | 0 | 101.62 | 0
BaCo_Baltimore Harbor | 0 | 0 | 0 | 0 | 0 | 8877912.1772
BaCo_Gwynns Falls | 0 | 14.5222 | 140.6 | 0 | 0
BaCo_Jones Falls | 0 | 11.8711 | 0 | 0 | 22.75
BaCo_Patapsco River L N Br | 0 | 0.83523 | 121.38 | 0 | 207.86
CrCo_S Branch Patapsco | 0 | 13.5479 | 0 | 64.74 | 0 | 2546939.0756
HoCo_Patapsco River L N Br | 0 | 84.2647 | 0 | 0 | 0 | 3269462.4496
HoCo_S Branch Patapsco | 0 | 0 | 0 | 0 | 0

## Planned BMP Estimated Cost
SOURCE INFORMATION
Planning Tier | Planned Scenario | County | Watershed | County/Watershed | BMP | Unit | Treatment | IA Credit | TN EOS lbs/yr | TP EOS lbs/yr | Estimated Cost Using IA Credit | Estimated Cost Using TN | Estimated Cost Using TP | Notes | BMP Type | Median Cost/IA Credit ($/LB reduced per year) | Median Cost/TN ($/LB reduced per year) | Median Cost/TP ($/LB reduced per year)
Milestone 1 | MEP Placeholder | Anne Arundel | Baltimore Harbor | AACo - Baltimore Harbor | FPU | Ac Converted | 15.9 | 17.49 | 161.6686 | 14.6567 | 2442331.7541 | 979572.9512 | 568678.1112 | copied reduction from TIPP xlsx | Outfall stabilization | 27245.5924 | 3414.7924 | 7491.5292
Milestone 1 | MEP Placeholder | Anne Arundel | Patapsco R LN Br | AACo - Patapsco R LN Br | FPU | Ac Converted | 0 | 0 | 0 | 0 | 0 | 0 | 0 | copied reduction from TIPP xlsx | Stream Restoration | 60000 | 8684.53 | 18528.75
Milestone 1 | MEP Placeholder | Anne Arundel | Baltimore Harbor | AACo - Baltimore Harbor | OUT | lf | 1785 | 35.7 | 133.875 | 121.38 | 972667.6505 | 457155.3359 | 909321.8177 | copied reduction from TIPP xlsx | Forestation on Previous Urban (Tree Planting) | 139641.6097 | 6059.1425 | 38799.9102
Milestone 1 | Proposed BMPs in GDB: SWM BMP Retrofit | Anne Arundel | Baltimore Harbor | AACo - Baltimore Harbor | Conversion of Existing BMP | DA | 11.38 | 7.75 | 80.7274 | 11.47 | 70000 | 70000 | 70000 | copied reduction and IA credit from SHA gdb; cost is from the MEP Restoration portfolio | Impervious Surface Reduction | 2094656.5847 | 106215.4353 | 703304.4757
Milestone 1 | Remediated BMPs | Anne Arundel | Baltimore Harbor | AACo - Baltimore Harbor | FPU | Ac Converted | 33.6 | 36.96 | 320.8552 | 29.08 | 5161153.8954 | 1944107.3609 | 1128301.3893 | copied reduction from AMT | Chapter 5 Stormwater Sites - New | 351357.7563 | 13721.45 | 79230.738
Milestone 1 | Remediated BMPs | Anne Arundel | Patapsco R LN Br | AACo - Patapsco R LN Br | FPU | Ac Converted | 10.9 | 11.99 | 86.2818 | 10.0618 | 1674302.9006 | 522793.9154 | 390397.6787 | copied reduction from AMT | Source: SHA_BMPCost_RestorationFunding_2025.03.05.xlsx |  |  |  | Row Labels | Sum of TN EOS lbs/yr | Sum of TP EOS lbs/yr | Sum of Estimated Cost Using TP |  | Row Labels | Sum of TN EOS lbs/yr | Sum of TP EOS lbs/yr | Sum of Estimated Cost Using TP
Milestone 2 | Site Selection (Status = Recommended) | Anne Arundel | Baltimore Harbor | AACo - Baltimore Harbor | FPU | Ac Converted | 6.77 | 7.447 | 68.8362 | 6.24 | 1039911.0676 | 417088.6088 | 242111.4398 | copied reduction from TIPP xlsx |  |  |  |  | Anne Arundel | 1353.7597 | 525.7098 | 9750071.0858 | 9750071.0858 | Jones Falls | 396.998 | 34.62 | 1343251.5874
Milestone 2 | Site Selection (Status = Recommended) | Anne Arundel | Patapsco R LN Br | AACo - Patapsco R LN Br | FPU | Ac Converted | 14.69 | 16.159 | 149.3655 | 13.5413 | 2256468.7715 | 905026.8335 | 525401.3492 | copied reduction from TIPP xlsx |  |  |  |  | Baltimore Harbor | 1020.9624 | 414.0267 | 7202259.7579 |  | Milestone 1 | 136.6959 | 11.8711 | 460596.7783
Milestone 2 | Site Selection (Status = Recommended) | Anne Arundel | Baltimore Harbor | AACo - Baltimore Harbor | STRE | lf | 3400 | 68 | 255 | 231.2 | 4080000 | 2214555.15 | 4283847 | copied reduction from TIPP xlsx | BMP Type | Unit | EIA |  | Milestone 1 | 697.1262 | 176.5867 | 2676301.3181 |  | Remediated BMPs | 136.6959 | 11.8711 | 460596.7783
Milestone 2 | Site Selection (Status = Recommended) | Anne Arundel | Patapsco R LN Br | AACo - Patapsco R LN Br | STRE | lf | 1295.305 | 25.9061 | 97.15 | 88.08 | 1554366 | 843702.0895 | 1632012.3 | copied reduction from TIPP xlsx | Outfall stabilization | Per linear foot | 0.02 |  | Milestone 2 | 323.8362 | 237.44 | 4525958.4398 |  | Planned | 260.3021 | 22.7489 | 882654.8091
Milestone 1 | MEP Placeholder | Baltimore | Gwynns Falls | BaCo - Gwynns Falls | FPU | Ac Converted | 15.9 | 17.49 | 144.7669 | 19.2235 | 2442331.7541 | 877163.4569 | 745870.1057 | copied reduction from TIPP xlsx | Stream Restoration | Per linear foot | 0.02 |  | Patapsco R LN Br | 332.7973 | 111.6831 | 2547811.3279 |  | Baltimore Harbor | 1020.9624 | 414.0267 | 7202259.7579
Planned | Gap Filler | Baltimore | Jones Falls | BaCo - Jones Falls | FPU | Ac Converted | 21.22 | 23.342 | 260.3021 | 22.7489 | 3259514.4542 | 1577207.3396 | 882654.8091 | copied reduction from TIPP xlsx | Forestation on Previous Urban (Tree Planting) | Per acre of land cover converted | 1.1 |  | Milestone 1 | 86.2818 | 10.0618 | 390397.6787 |  | Milestone 1 | 697.1262 | 176.5867 | 2676301.3181
Planned | Gap Filler | Baltimore | Patapsco R LN Br | BaCo - Patapsco R LN Br | FPU | Ac Converted | 21.22 | 23.342 | 188.4548 | 25.7926 | 3259514.4542 | 1141874.5953 | 1000752.252 | copied reduction from TIPP xlsx | Impervious Surface Reduction | Per acre of land cover converted | 0.71 |  | Milestone 2 | 246.5155 | 101.6213 | 2157413.6492 |  | MEP Placeholder | 295.5436 | 136.0367 | 1477999.9288
Planned | Gap Filler | Baltimore | Patapsco R LN Br | BaCo - Patapsco R LN Br | STRE | lf | 2677.5 | 53.55 | 200.8125 | 182.07 | 3213000 | 1743962.1806 | 3373529.5125 | copied reduction from TIPP xlsx | Source: MDE's 2021 Accounting Guidance |  |  |  | Baltimore | 1315.1693 | 519.8235 | 8877912.1772 | 8877912.1772 | Proposed BMPs in GDB: SWM BMP Retrofit | 80.7274 | 11.47 | 70000
Milestone 1 | MEP Placeholder | Baltimore | Gwynns Falls | BaCo - Gwynns Falls | OUT | lf | 1785 | 35.7 | 133.875 | 121.38 | 972667.6505 | 457155.3359 | 909321.8177 | copied reduction from TIPP xlsx |  |  |  |  | Jones Falls | 396.998 | 34.62 | 1343251.5874 |  | Remediated BMPs | 320.8552 | 29.08 | 1128301.3893
Milestone 1 | MEP Placeholder | Baltimore | Patapsco R LN Br | BaCo - Patapsco R LN Br | OUT | lf | 1785 | 35.7 | 133.875 | 121.38 | 972667.6505 | 457155.3359 | 909321.8177 | copied reduction from TIPP xlsx |  |  |  |  | Milestone 1 | 136.6959 | 11.8711 | 460596.7783 |  | Milestone 2 | 323.8362 | 237.44 | 4525958.4398
Milestone 1 | Remediated BMPs | Baltimore | Gwynns Falls | BaCo - Gwynns Falls | FPU | Ac Converted | 14.2 | 15.62 | 110.1221 | 14.5222 | 2181201.9439 | 667245.3239 | 563458.3646 | copied reduction from AMT |  |  |  |  | Planned | 260.3021 | 22.7489 | 882654.8091 |  | Gwynns Falls | 388.764 | 155.1257 | 2218650.288
Milestone 1 | Remediated BMPs | Baltimore | Jones Falls | BaCo - Jones Falls | FPU | Ac Converted | 13 | 14.3 | 136.6959 | 11.8711 | 1996875.019 | 828260.0626 | 460596.7783 | copied reduction from AMT | Planned TIPPs |  |  |  | Gwynns Falls | 388.764 | 155.1257 | 2218650.288 |  | Milestone 1 | 388.764 | 155.1257 | 2218650.288
Milestone 1 | Remediated BMPs | Baltimore | Patapsco R LN Br | BaCo - Patapsco R LN Br | FPU | Ac Converted | 1.2 | 1.32 | 6.265 | 0.83523 | 184326.9248 | 37960.3531 | 32406.7196 | copied reduction from AMT | 1. AACo_Baltimore Harbor_TIPP_PlannedBMPs_20240918_TPtarget.xlsm |  |  |  | Milestone 1 | 388.764 | 155.1257 | 2218650.288 |  | MEP Placeholder | 278.6419 | 140.6035 | 1655191.9234
Milestone 1 | Remediated BMPs | Carroll | Patapsco R LN Br | CrCo - Patapsco R LN Br | FPU | Ac Converted | 0.7 | 0.77 | 8.5535 | 0.60268 | 107524.0395 | 51826.6942 | 23383.9796 | copied reduction from AMT | 2. AACo_Patapsco River L N Br_TIPP_ PlannedBMPs _20240918_TPtarget.xlsm |  |  |  | Patapsco R LN Br | 529.4073 | 330.0779 | 5316010.3018 |  | Remediated BMPs | 110.1221 | 14.5222 | 563458.3646
Milestone 1 | Remediated BMPs | Carroll | S Br Patapsco | CrCo - S Br Patapsco | FPU | Ac Converted | 16.4 | 18.04 | 121.7647 | 13.108 | 2519134.6394 | 737789.5549 | 508590.3961 | copied reduction from AMT | 3. BaCo_Baltimore Harbor_TIPP_ PlannedBMPs _20240918_TPtarget.xlsm |  |  |  | Milestone 1 | 140.14 | 122.2152 | 941728.5373 |  | Patapsco R LN Br | 1500.5706 | 526.6284 | 11156668.0589
Milestone 1 | Remediated BMPs | Carroll | S Br Patapsco | CrCo - S Br Patapsco | IMPP | Ac Converted | 0.2 | 0.142 | 2.4177 | 0.43983 | 297441.235 | 256795.4601 | 309331.3862 | copied reduction from AMT | 4. BaCo_Gwynns Falls_TIPP_ PlannedBMPs _20240918_TPtarget.xlsm |  |  |  | Planned | 389.2673 | 207.8626 | 4374281.7645 |  | Milestone 1 | 864.7878 | 217.1444 | 4624972.6451
Milestone 2 | Site Selection (Status = Recommended) | Carroll | S Br Patapsco | CrCo - S Br Patapsco | FPU | Ac Converted | 9.78 | 10.758 | 106.1661 | 11.465 | 1502264.4374 | 643275.275 | 444840.8354 | copied reduction from TIPP xlsx | 5. BaCo_Jones Falls_TIPP_ PlannedBMPs _20240918_TPtarget.xlsm |  |  |  | Carroll | 322.5919 | 78.8855 | 2546939.0756 | 2546939.0756 | MEP Placeholder | 133.875 | 121.38 | 909321.8177
Milestone 2 | Site Selection (Status = Recommended) | Carroll | S Br Patapsco | CrCo - S Br Patapsco | MSWG | DA | 2.74 | 2.77 | 29.91 | 4.51 | 973260.985 | 410408.5681 | 357330.6283 | copied reduction from TIPP xlsx; IA credit from Grass Swale Site Selection in Baltimore Harbor .xlsx | 6. BaCo_Patapsco River L N Br_TIPP_ PlannedBMPs _20240918_TPtarget.xlsm |  |  |  | Patapsco R LN Br | 8.5535 | 0.60268 | 23383.9796 |  | Remediated BMPs | 730.9128 | 95.7644 | 3715650.8274
Milestone 2 | Site Selection (Status = Recommended) | Carroll | S Br Patapsco | CrCo - S Br Patapsco | STRE | lf | 717.12 | 14.3424 | 53.78 | 48.76 | 860544 | 467054.0234 | 903461.85 | copied reduction from TIPP xlsx | 7. CrCo_S Branch Patapsco_TIPP_ PlannedBMPs _20240918_TPtarget.xlsm |  |  |  | Milestone 1 | 8.5535 | 0.60268 | 23383.9796 |  | Milestone 2 | 246.5155 | 101.6213 | 2157413.6492
Milestone 1 | Remediated BMPs | Howard | Patapsco R LN Br | HoCo - Patapsco R LN Br | FPU | Ac Converted | 77.6 | 85.36 | 629.8125 | 84.2647 | 11919807.806 | 3816123.6434 | 3269462.4496 | copied reduction from AMT | 8. HoCo_Patapsco River L N Br_TIPP_ PlannedBMPs _20240918_TPtarget.xlsm |  |  |  | S Br Patapsco | 314.0384 | 78.2829 | 2523555.096 |  | Planned | 389.2673 | 207.8626 | 4374281.7645
[9 empty] | 3621.3334 | 1208.6835 | 55913279.033 | 22525259.448 | 24444384.7882 |  | 9. HoCo_S Branch Patapsco_TIPP_ PlannedBMPs _20240918_TPtarget.xlsm |  |  |  | Milestone 1 | 124.1824 | 13.5479 | 817921.7823 |  | S Br Patapsco | 314.0384 | 78.2829 | 2523555.096
[19 empty] | Milestone 2 | 189.8561 | 64.735 | 1705633.3137 |  | Milestone 1 | 124.1824 | 13.5479 | 817921.7823
[19 empty] | Howard | 629.8125 | 84.2647 | 3269462.4496 | 3269462.4496 | Remediated BMPs | 124.1824 | 13.5479 | 817921.7823
[19 empty] | Patapsco R LN Br | 629.8125 | 84.2647 | 3269462.4496 |  | Milestone 2 | 189.8561 | 64.735 | 1705633.3137
[19 empty] | Milestone 1 | 629.8125 | 84.2647 | 3269462.4496 |  | Grand Total | 3621.3334 | 1208.6835 | 24444384.7882
[19 empty] | Grand Total | 3621.3334 | 1208.6835 | 24444384.7882
Note on H3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Changed from 21.2 to 15.9; added 5.3 ac FPU to Planned (Gap Filler)
Note on H5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Changed from 4,462.5 to 1,785; added 2,677.5 ac FPU to Planned (Gap Filler)
Note on H11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Reduced original site selection treatment
Note on H12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Reduced original site selection treatment
Note on H13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Changed 42.4 to 15.9; added 26.5 to Planned (Gap Filler)
Note on A14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Switched from Milestone 1 (MEP Placeholder) to Planned (Gap Filler)
Note on A15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Changed from Milestone 1 (MEP Placeholder) to Planned (Gap Filler)
Note on A16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Moved lf from Milestone 1 (MEP Placeholder) to Planned (Gap Filler)
Note on H17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Changed 4,462.5 to 1,785; added 2,677.5 to Planned (Gap Filler)
Note on H18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Changed 4,462.5 to 1,785; added 2,677.5 to Planned (Gap Filler)
Note on H27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Reduced original site selection treatment