## Slide 1: Flexible Sequence of Construction for SHA Projects

## Slide 2: Agenda
Registration 8:30-9:00
Opening & Introduction 9:00-9:30
(Ginger Olyniec & Jeff Knaub)
Purpose of SOC (Ginger Olyniec) 9:30-10:00
Building the SOC (Ginger Olyniec) 10:00-10:45
Break 10:45-11:00
Sample Project (Jonathan Brown 11:00-11:30
& Ryan Doran)
Special Situations (Ginger Olyniec) 11:30-1:30
Lunch 12:00-1:00
Break out sessions (Moderators) 1:30-2:45
Break 2:45 – 3:00
Wrap up (All hands) 3:00-3:30

## Slide 3: House-keeping
Silence Phones
Questions at end of Sections and before breaks
Moderator Introductions
Breakout room assignments

## Slide 4
Facilitators FSOC Examples
Kirin Smith (SHA – OHD – HHD)
Gina Goettler (Chief Eng. System – SHA – D5)
Jonathan Brown (Area Engineer – SHA – D3)
Ryan Doran (Area Engineer – SHA – D3)
Virginia Olyniec Chief – SHA – OHD – HHD
Jeffrey Knaub Chief – SHA – OHD - PRD
Barry Smith (Deputy Director – SHA – OHD)
Brandon Scott (SHA – OHD – PRD)
Alicia Brandys (SHA – OHD – PRD)
Tesfa Bogale (SHA – OHD – PRD)
Sonja Hardman (SHA – OHD – PRD)
Natalie DeColli (Consultant – SuYash)
Amanda Barrett (Consultant – RKK)
Laura Ridler (Consultant – SuYash)

## Slide 5: Flexible Sequence of Construction:
Why Change?
Resilient
Notes: Welcome Everyone. Ask the audience if their mornings went according to plan? Share something personal about my morning, call on someone to share the same. Discuss how construction mirrors life and the best laid plans need to be flexible.
JOKE about hating toolkit emails

## Slide 6: resilience:
"an ability to recover from or adjust easily to misfortune or change."
-Merriam-Webster Dictionary
Notes: Discuss my SHA and Regulatory hats. Our responsibility to the public (closing roads/safety for contractors). Discuss the reducing construction timeframes to reduce the risk of experiencing storm events
Transition to Ginger

## Slide 7: Why a Flexible Sequence of Construction
Build resilience into our projects to adapt to unforeseen circumstances
Better plans to control sediment runoff and erosion
Reduce the amount of time earth is exposed and vulnerable to erosion
Preempt change orders

## Slide 8: What is a Sequence of Construction?
COMAR SEC. 26.17.01.07 (Application for Approval of Erosion and Sediment Control Plans)
Clearing and grubbing as necessary for the installation of perimeter controls;
Construction and stabilization of perimeter controls;
Remaining clearing and grubbing within installed perimeter controls;
Road grading;
Grading for the remainder of the site;
Utility installation and connections to existing structures;
Final grading, landscaping, and stabilization; and
Removal of controls and stabilization of resulting disturbances;
"Do the work"
Notes: -COMAR SEC 26.17.01.07, "The Sequence of construction describes the relationship between the implementation and maintenance of erosion and sediment control practices, including permanent and temporary stabilization, grading units, and the various stages or phases of earth disturbance and construction." ​
-(animation 1) COMAR defines these minimum steps be in SOC​
- (animations 2 -4) middle steps can be boiled down to "do work as shown". ​
-Therefore, the minimum requirements for the sequence of construction are fairly minimal. ​
Work is to be performed in coordination with the contractors developed schedule. ​
"do the work" portion item might include the construction of additional ESC devices which are within the perimeter controls. ​
​

## Slide 9
What is the purpose of Erosion and Sediment Control?
Notes: This training is about providing flexibility in the sequence of construction.
The SOC is an integral part of the sediment and erosion control plan
Lets take a step back and ask, "why do we care about erosion and sediment control in the first place?"
The basics are, when we undertake a construction project, the result is a lot of exposed earth. Grading operations, or even just trucks driving over open space areas, cause native soils to be exposed, and therefore become easily moved by storm flows. When storms come, this sediment can end up being migrated by the stormwater onto downstream properties (click for photo 1), into public roadways and storm drain systems (click for photo 2), and into those systems downstream channels (click for photo 3). Those downstream channels ultimately connect with larger waterways (click for photo 4) and can lead to sedimentation within our natural resources (click for photo 5).

## Slide 10: How does sediment transport impact downstream property owners?
Notes: The photo on the left is an extreme case which took place after a hurricane. However, the case still holds; sediment transport onto downstream properties can cause property damage, lessen property value, and hurt property owners. As shown on the left, sediment migration into storm drain systems can result in clogging of storm drain systems and unsafe roadway conditions due to roadway flooding; and even if the systems do not clog, it just pushes that sediment further downstream, which causes issues for the receiving waterways.

## Slide 11: How does sediment transport impact downstream waterways?
Notes: Sediment runoff causes nutrient loads in downstream waterways​
Kills of fish & native animals​
ESC protects the environment

## Slide 12: How do we keep sediment from leaving the site?
Notes: 2011 MDE ESC Manual and SHA ESC Field Manual has many options​
divert offsite clearwater flows ​
filter water to remove sediment before it leaves the site or before it enters a storm drain system ​
direct all the dirty water to one area and let sediment settle​
direct it to a filtering device​
Mainly, DON’T LET SEDIMENT LEAVE SITE

## Slide 13: What are the consequences for failure?
Work stoppage
Fines
Legal action
Notes: From a legal sense, there are multiple possible outcomes to not controlling sediment on our site (beyond the social and environmental impacts already discussed in previous slides). They include those listed above.
WORK STOPPAGE: MDOT's (Quality Assurance) QA division is responsible for visiting active construction sites and creating reports that assess whether E&SC is being conducted and enforced properly. When a poor E&SC grade is issued by QA, the contractor is given 72 hours to correct the issue; however, If corrective actions are not taken in a timely manner, SHA can order a stoppage of work which can have major schedule impacts. Inadequate design consequences...
FINES: If the issues causing sediment control not to be in compliance are not resolved, SHA can fine the contractor in the form of liquidated damages. This happens at a price/day that the project is not in compliance. These costs are in addition to whatever costs the contractor incurs in order to bring the site back up to E&SC standards, so can quickly add up. Additionally, when ESC IS performed correctly, there are "incentives payments" given to the contractor... so when its done incorrectly, you lose the incentives AND have to pay damages – a double loss.
LEGAL ACTION: Legal action can be taken as a last resort in accordance with the permits.
None of these are good for the overall project budget and schedule and can be avoided through smart ESC design and contractor implementation.

## Slide 14: "But I'm not a contractor... how is this my problem?"
Notes: Designers, MDOT, and contractor are a team​
Worry less about which responsibility is whose and more about the greater goals​
Aim to create designs that are easier to apply in real life​
Avoid errors and omissions

## Slide 15
DESIGNER
CONTRACTOR
Sequence of Construction
PROJECT
SUCCESS!
Determine
construction means/methods
RESPONSIBILITY
BREAKDOWN:
Provide
constructed
product
Design E&S controls Prevent Sediment
From leaving site
Plan Creation
Meeting requirements
& guidelines
(AASHTO/PRD/ETC.)
Notes: Designer and Contractor responsibilities build on each other toward a final product​
Designers: design ESC and create plans​
Contractors: implement ESC in field/minimize source erosion​
Designers: write SOC​
Contractors: determine means/methods (taking the plans and making them a reality)​
Designers: ensure plans meet requirements​
Contractor: provide constructed product​

## Slide 16: What is a successful project?
Notes: Performing ESC correctly leads to positive outcomes​
(photo 1) more efficient construction​
Efficient construction is #1 way to minimize sediment transport​
Lowers time earth is exposed​
(photo 2) shorter construction duration​
Get people back onto the roads quicker​
Less disruption of daily routines​
(photo 3) cleaner waterways​
Recreation, fishing

## Slide 17: What are the problems with the Commonly used ESC Sequence of Construction?
Limits Contractor's flexibility
High number of toolkit modifications
QAD is required to enforce EVERYTHING in the Sequence as part of Delegated Authority from MDE
Construction Issues/Stops
Schedule delays
Contractor claims
Notes: The main complaint with the current SOC approach is that it limits the contractors flexibility when building from a set of plans. By having so many steps, Designers are dictating exactly how the project needs to be built, and the order in which construction activities are taking place.
This can easily spiral into a series of events following the path laid out here. When the contractor is held to a specific sequence, they need QAD's approval to perform activities out of order. This leads to them submitting toolkit mods, which need to be reviewed/approved through a process that can be time consuming. This in turn leads to construction stops, schedule delays, and possibly contractor claims.

## Slide 18: Common Sequence of Construction
QAD HAS TO ENFORCE ALL OF THIS, INCLUDING ORDER!
Notes: This is the length of a typical sequence​
Very specific language, listing specific construction orders​
QAD MUST ENFORCE THE ORDER OF ALL THESE MANY STEPS​
Can cause issues if there are any unforeseen issues in the field

## Slide 19
How did we get here: ​ A History Lesson
Notes: HOW DID WE GET HERE​
Historically, SOC's used to be much shorter​
Developers were disturbing 60+ acres at once​
Led to requiring more detail as to what could be disturbed when​
Eventually led to highly prescriptive sequence, shown above

## Slide 20: How does this cause issues? An example:
Early step in sequence calls for pipes to be installed
Pipe is on backorder and cannot be obtained from supplier
Contractor cannot move on to other work, as sequence specifies pipes need to be installed first. They submit a toolkit mod to change the sequence.
While waiting for review of mod, construction is stopped
Schedule is delayed, and contractor asks for an extra to cover unanticipated costs
Notes: ​
"Pipes" in this example could easily be swapped out for any other type of material/activity​
goal of changing sequence is to provide more flexibility/stop these types of delays ​
Still need to ensure E&SC is performed​
There are situations where pipe may really need to be first (IE used for diversion)​
We need to use our judgement for when more info is needed

## Slide 21: LESSONS LEARNED
Avoid tying ESC sequence to MOT phases
Constructability Issues
Concurrent utility/developer work conflicting with ESC SOC
Notes: Tying ESC to MOT: ​
We want ESC to make sense based on work areas available from MOT phasing​
The sequence of MOT is not enforced by an external entity (like QAD for ESC)​
MOT can change in the field; ​
If ESC is dependent on MOT phasing, it might cause field conflicts​
​
Constructability Issues: ​
Constructability review should be common practice​
Engineers writing sequences don't always have extensive construction experience​
Can cause construction issues and limit contractors means/methods​
Our responsibility is to ensure ESC is provided on plans – leave "how its built" to contractor ​
​
Concurrent utility/developer work:​
Utilities aren't always relocated timely, or correctly​
Surrounding developers schedules may slide​
Writing a prescriptive sequence ties the contractors hands if any of these issues come up​
Flexible sequence would allow you to move to another area without needing a mod

## Slide 22
Terminology
Phase(s) or Phasing: a distinct period in a series of events or a process of change or development​. Construction Phasing: Allows a project to be completed in distinct segments rather than all at once. ​
MOT Phasing: Establishes temporary conditions to keep the travel ways safe during construction and maintenance or utility work. ​NOT ESC​
Work Areas: sub-areas within each project to simplify erosion and sediment control sequencing.​
  Clarifies when an area is available for work to commence.​
  Constraints are more easily identified and shown on specific plan sheets, not in the Sequence of Construction. ​
  Areas are designated based on geography or drainage pattern.​
  Not all projects will require work areas.​
Stage: A sub-work area.​ Stages are used for complicated sequencing that requires sub-work areas

## Slide 23: How do we re-think writing the SOC?

## Slide 24: WHAT IS FLEXIBILITY
Notes: we want to give the contractor options. ​
one small hiccup, shouldn't shut down work on the project ​
if something unexpected comes up, the sequence should not cause an impediment. ​
we need a new way to approach writing our ESC sequences.

## Slide 25: Roadmap to Project Success:
Show, don't tell
"Work Areas" rather than "Phasing“
Emphasize constructability
If it isn't directly related to sediment control, DO NOT INCLUDE IT!
Use Active voice (not passive)
Notes: We need to break our SOC habits using the following roadmap​
​
Show, don't tell: ​
show what you need on the plans clearly, communicate the necessary constraints​
Let contractor decide how to build​
Communicate end product clearly on plans instead of in sequence​
​
"Work Areas" rather than "Phasing": ​
Having multiple phases in the sequence makes them longer by nature​
Instead of "phases" look for "work areas"​
Should correspond with different geopraphic regions that can all be built at once​
If ESC is in place for a work area, work can take place whenever​
​
Emphasize constructability:​
have someone with construction expertise reviewing your plans AND sequence. ​
If it isn't directly related to sediment control, DON’T INCLUDE IT IN SEQUENCE​
ask yourself, "does this step help keep sediment from leaving the site?" ​
If the answer is "no", you don't include the step​
​
Use active, not passive, voice: ​
This adds clarity to what you are trying to communicate in your sequence, and who is responsible for each step.

## Slide 26: Benefits:
Shorter construction duration
Fewer field modifications
More ability for contractor to work efficiently
Notes: Decreased construction duration, ​
limiting time earth is disturbed; less opportunity for sediment to leave the site.​
Fewer field modifications,​
Prevent construction delays/additional PRD reviews.​
Allow contractor to work efficiently ​
They can choose order of work as long as they comply with sequence/plans​
​
- rethink what NEEDS to be in a sequence of construction, and ONLY including those items.

## Slide 27: What "Basic Steps" are the bare minimum?
  QAD notification per Erosion and Sediment Control General Notes Sheet, Note 2
  Stakeout LOD and Clear/Grub for installation of perimeter controls before earth disturbance occurs
  Perform work as communicated in contract documents: give allowance for work to occur in any order/concurrently, with ESC in place whenever possible
  Stabilization of DA/cleaning of upstream storm pipes prior to BMP installation, with QAD approval
  Final stabilization of site when removing ESC devices with QAD approval. Stabilize any areas disturbed by removal of sediment controls.
Notes: Here is out general "bare minimum" SOC. Even this can be further simplified, as the First bullet is not needed because of updated E&S GN sheets note 2, and we already reference QAD approval to start the work in step 2.

## Slide 28: What is the purpose of a sequence of construction?
To ensure sediment controls are in place before earth is disturbed
NOT to dictate
Means and Methods
Notes: - PURPOSE of SOC to ensure that sediment control HAPPENS. ​
The controls need to be in place before the earth is disturbed​
The point of the sequence is NOT to dictate the order or methods in which the work is performed.​
Approaching the sequence from an overly prescriptive mindset has led to issues

## Slide 29
Identify Drainage Patterns
Where does water enter construction
Where does water leave construction
Quantify Flows
On-site DAs
Offsite DAs
Minimize Flows over Disturbed Ground
Divert Offsite flows
Filter onsite Flows
Identify Drainage patterns of Concern
Crossing other Drainage Areas
Receiving Large offsite Flows
Very close to Sensitive Areas
Identify Critical Steps In Sequence
Clear-water Diversions
Outline Sequence of E&SC Controls
DO NOT INCLUDE ANY OTHER SEQUENCE ITEMS
Finish Writing SOC
Work Areas can have Separate SOC
Be sure to include all Critical steps
Filtering Practices
Determine Work Areas
By Discrete DA
By Discharge Point
By Controls
Plan For Success
Notes: Identify Drainage areas
Quantify flows
Minimize flows over disturbed ground
Identify drainage patterns of concern
Determine work area
Identify critical steps in the SOC
Outline SOC
Write…

## Slide 31
Where does water enter and leave the construction area?
What are the drainage areas?
Are there "offsite areas" that divide the construction?
What are logical work areas? Do certain activities need to happen to manage the water?
Notes: Rethink project in terms of water and sediment management
Do you have large offsite drainage areas
Do concentrated flows enter or leave the construction zone
Are work areas small and constrained by property lines

## Slide 32: Work Areas: How do we select them?
Work Area 1
Work Area 2
Work Area 3
Notes: Work areas assessed based on geography/drainage areas​
Once ESC is in place for a work area, work can be performed at any time​
​
Example: I-70 with a wide median​
All drainage flows to stream, boundaries shown in red​
Top Right: all area drains to culvert/pump around ​
Call this ZONE 1​
Top Left, similar situation – all area drains to culvert​
Call this ZONE 2​
Bottom, everything drains toward sediment trap​
Call this ZONE 3​
​
work zones but it will differ from project to project. ​
consider the "work zones" BEFORE placing and selecting your ESC devices to maximize contractor flexibility. ​
group areas to make sure that all areas are covered by an ESC device.

## Slide 33: EXAMPLES: How can we provide flexibility?

## Slide 34: Do the Work
This Step incudes the following for EACH work area:
Install Stabilized Construct Entrance if Required
Install perimeter Sediment and Erosion Controls
Perform Work in Work Area
Stabilize all disturbed areas
Install SWM practices (if required)
Final Stabilization
With QAD Permission, remove perimeter controls for the work area

## Slide 35: Items that Should be Considered
Any activity that changes drainage patterns​
Relocation or location of stock piles and staging areas​
Relocation or location of new stabilized construction entrances​
Installation of ESD practices and protection of these practices​
Sediment basin construction, removal, conversion​
Sheet flow to silt fence that changes to concentrated flow​
Stream and clear water diversions​
Dewatering​
Temporary blockages of stormwater conveyance (pipes, inlets, channels)​
Transitioning from overland flow to storm drain system control​
Flushing the storm drain system into ESC prior to final SWM;​
Zones of perimeter controls when there are shifts in drainage areas, or overlaps in limits of disturbance (LOD) or drainage areas.​

## Slide 36: BREAK

## Slide 37: PG1065184
Powder Mill Road in Beltsville, MD
1.35-mile urban reconstruction project
Improvements included:
  Curb/gutter
  Storm drain
  ADA sidewalks
  Concurrent utility relocations
Notes: Contract PG1065184 was one of the first projects to undergo the Flexible Sequence approach in 2019 through collaboration between MDOT SHA PRD, HHD, QAD, District 3 Construction, and the design team to produce a sequence which provided flexibility but still ensured erosion and sediment controls were maintained.
The project in Beltsville consisted of 1.35 miles of urban intersection improvements along Powder Mill Road. Proposed improvements include mill and overlay, concrete curb and gutter, ADA compatible sidewalks, drainage improvements, and stormwater management facilities.
As you can see from the aerial and street view, project site is located along a developed urban corridor. There were a number of utility conflicts/relocations required as part of project scope, including concurrent utility work to relocate Verizon overhead utility poles as well as water main relocation within the project limits.

## Slide 38: PG1065184 SOC Mindset Change
Prescriptive SOC: Required contractor to construct project in a very specific order.
Flexible SOC: Focused SOC on ESC restrictions and procedures needed to maintain ESC compliance.
Consider where concurrent work can be allowed
Notes: The original sequence was very long and prescriptive, requiring the contractor to construct the project in a very specific order. There were a number of Verizon utility pole relocations that were supposed to be relocated before this SHA contract but those relocations were behind schedule, creating potential delays with the original sequence of construction for this contract.
Flexible SOC Approach: Make sequence of construction clear, concise, and as flexible as possible for the contractor given the specific job constraints.
Brainstorm session between SHA HHD, PRD, District 3, and Office of Construction (OOC) to review project overall and determine which work areas can be completed with QAD approval to complete as much work as possible without waiting for Verizon Utility Pole relocations. Special attention was paid to work areas where work could happen concurrently (at the same time) versus work that was required to be completed within specific order.

## Slide 39: Get from here.....
to here!
Notes: Ultimately, by incorporating all these common-sense changes, we can get from here (click for simplified sequence) to here!

## Slide 40
ORIGINAL SOC
Tied to MOT Phasing
Specific ESC Plan Sheets Dependent on Verizon Utility Relocation
Notes: The original erosion and sediment control sequence of construction was restrictive, linked to the maintenance of traffic phases, and conflicted with Verizon’s proposed relocation. The goal was to revise the sequence quickly to obtain permit modifications before the project was advertised to avoid any schedule delays.
This method dictates the contractor's construction order without adding any room for the construction order to change without requiring a toolkit modification. In addition, the SOC does not allow for concurrent work.

## Slide 41: PG1065184 Revised SOC
Step 1
Notify QAD per ESN-01 Note 2. Stakeout LOD/Install TOCF
Step 2
Clear & Grub for Perimeter Controls, Install ESC Perimeter Controls
Step 3
Install remaining ESC measures in each work area
Step 4
Complete project work (noting which items can be completed concurrently if applicable)
Project specific notes can be called out on ESC plan sheets
Step 5
Once all contributing drainage areas are permanently stabilized, construct BMPs with QAD approval.
Step 6
Permanent stabilization/QAD approval
Notes: Revised sequence is not tied to MOT plan/phasing and also allows for concurrent work. This revised SOC allows the contractor to continue working in another area if there is a location where the anticipated utility pole relocations to be completed by others have not been completed yet. This revised SOC met the goals of providing contractor flexibility on work order, allowing concurrent work, and simplifying sequence steps.
Sequence of Construction Approach:
Step 1: Stakeout LOD/install temporary orange construction fence. In some cases, there may be a general note that indicates if the LOD should be staked out all at once or if it’s OK to do in phases.
Step 2: Clear and grub to install perimeter controls. In some cases this direction will include the whole project, in others, it may be by phase, or it may be at the contractors discretion. If it’s not the whole project, we would emphasize that all controls need to be in before beginning work in each work area. This step might also include tree root pruning.
Step 3: Clear and grub to install remaining controls as work progresses.
Step 4: Perform work accommodating the any project specific constraints.
Step 5: Specific Instructions for SWM facilities to prevent sediment laden water from draining to them during construction. Note this approach from 2019 contract called out each individual BMP, but moving forward the SWM facilities should be referenced overall and specific BMP numbers should not be called out individually.
Step 6: Permanent stabilization.

## Slide 42: Get from here.....
to here!
Notes: Ultimately, by incorporating all these common-sense changes, we can get from here (click for simplified sequence) to here

## Slide 43: Original Sequence
Notes: This slide shows the original Sequence of Construction Prior to Simplification. The original sequence of construction consisted of two phases. Phase One consisted of 12 steps, and phase two consisted of 11 steps. In phase one, the contractor would have had to start on eastbound Maryland 212A at Pine St. and perform the work sequentially to US Route 1. The contractor would have had to install E&S perimeter controls, then install storm drain pipe and inlets specifically as called out in the sequence, then construct concrete, curb and gutter and sidewalk and stabilize the area before moving on to the next section. In phase two, the contractor would have had to start on westbound Maryland 212A at Pine St. and perform the work sequentially to US Route 1. Similar to phase one, the contractor would have had to install Erosion and Sediment controls, perimeter controls, storm drain pipe and inlets specifically as called out in the sequence. Then constructed concrete curb and gutter and sidewalk, and then stabilized the area before moving on to the next section.

## Slide 44: Detailed Analysis Point 3-4 and Effects
Notes: So this slide here shows steps three and four of the original sequence of construction prior to simplification. Now, as you can see, the steps are very detailed and tell the contractor what pipes and drainage structures that have to be installed and the order of installation. Any deviation in the order of work in these steps and the contractor would be considered to be out of sequence. And this could potentially result in a non-compliance from MDOT SHA Quality Assurance Program.

## Slide 45: Flexible Sequence after Edits
Notes: This slide shows the flexible sequence of construction as advertised, and if you compare that to what I just showed you originally, you're talking 11 and 12 steps for each phase, down to seven (7) steps for both phases of construction.

## Slide 46: FLEXIBLE SEQUENCE
Notes: This is just a blow up of the simplified sequence of construction. You could see it was 7 steps and these steps focus strictly on erosion and sediment control and did not dictate to the contractor how the project was to be built. How this worked was basically once the E & S controls were installed to wherever the contractor wanted to work. The contractor could perform that work. This sequence allowed for the work in each area to be performed concurrently and in any order. and the E & S plans did not change.

## Slide 47: Installation of Pipe and Structure à Pipe Run from I-12/1 to I-11/1 (Start of Work ES1-1)
Notes: So this slide shows you the original sequence of construction and it required the contractor to start at Pine St. and make their way east on the project. So the very first inlet that would have been installed is I-11/1. I-12/1 is the second inlet that needed to be installed. I-11/1 one is the first one here on the corner. Basically about 20 feet of pipe needed to be installed per the first sequence. The next thing that needed to be installed was I-3/1, then followed by the storm drain pipe that connects the two inlets.

## Slide 48: First Conflict BG&E Electrical Cable
RFI
Requested clarification on sizes of pipe converging to inlets and BGE electrical line. RCP cannot be installed due to this interference.
Notes: In doing so, we discovered that there were two (2) electric lines, one right here in between I-11/1 one and I-12/1, and the second piece was right here in between I-3/1 and I-11/1. In order to do any of this work. As you can see in this blow up all these electric lines, the red lines are the existing utility lines that were in the way running parallel. They were supposed to have been lowered to 8 feet, but the electrical contractor decided to put them at 2 1/2 feet deep. So that would have been modification #1 within the first three days of the project.

## Slide 49: Second Conflict à BG&E Electrical Cable
RFI
High voltage BGE electric line that is in direct conflict of the 18-inch RCP at STA 106+30. Miss Utility marking renewed recently.
CONSTRUCTION DELAY AVOIDED DUE TO FLEXIBLE SEQUENCE OF
CONSTRUCTION
Notes: Modification 2 was avoided by using flexible sequence of construction. Otherwise, project would have been delayed until modification was approved or utility was relocated.

## Slide 50: Installation of Pipe and Structure à Pipe Run from I-3/1 to I-7/1
Notes: Afterwards, once that got that cleared up, the contractor would have been able to install I-12/1 and I-11/1, and the piece of pipe between the two inlets, next was the installation of inlet (I-3/1) and then about 45 feet of RCP Pipe. They started on the next section for the sequence and as soon as they started on the next portion of the storm drain system, guess what???

## Slide 51: Second Conflict à BG&E Electrical Cable
RFI
High voltage BGE electric line that is in direct conflict of the 18-inch RCP at STA 106+30. Miss Utility marking renewed recently.
Notes: There was another electrical line that we found 20 feet away from I-3/1 that we encountered. It was determined that the high voltage BG&E line would have to be lowered. It would have required our second modification within 50 feet of starting the project.

## Slide 52: Third Conflict à Communication Cable
RFI
A Communication Conduit was found while we were doing the water house connection. No marking tape was found, and the pipe was at a depth of 3 feet.
During the subsequent storm water pipe installation, additional communication cables were encountered that inhibited completion of the pipeline installation.
CONSTRUCTION DELAY AVOIDED DUE TO FLEXIBLE SEQUENCE OF
CONSTRUCTION
Notes: Modification 3 was avoided by using flexible sequence of construction. Otherwise, project would have been delayed until modification was approved or utility was relocated.
The Construction Project Engineer stated using the flexible sequence of construction approach saved approximately 2 years of construction. The traditional approach would have put the entire project on hold during these RFIs and created a delay during the utility relocation, but the contractor was able to work on other areas while these RFIs were resolved because of the flexible ESC sequence.

## Slide 53: Installation of Pipe and Structure à Pipe Run from I-3/1 to I-7/1
Notes: After the contractor spent time getting that resolved, they could have moved to the next area of work. Unfortunately, we encountered another conflict.

## Slide 54: Third Conflict à Communication Cable
RFI
A Communication Conduit was found while we were doing the water house connection. No marking tape was found, and the pipe was at a depth of 3 feet.
During the subsequent storm water pipe installation, additional communication cables were encountered that inhibited completion of the pipeline installation.
Notes: This conflict was only 30 feet away and would have required another modification, because the contractor found a communication cable and that would have been our third modification within 100 feet of starting the project. And that would have been 3 modifications in a row just to modify the sequence. Because we were able to have a flexible sequence, when we encountered our first electrical line we skipped to the next set of inlets for installation. The contractor only needed to make sure the proper E&S controls prior to starting working, and then just kept moving forward as these issues were resolved. This allowed the contractor not to experience any delays as a result of having to submit and wait for modifications to the sequence to be approved.

## Slide 55: Third Conflict à Communication Cable
RFI
A Communication Conduit was found while we were doing the water house connection. No marking tape was found, and the pipe was at a depth of 3 feet.
During the subsequent storm water pipe installation, additional communication cables were encountered that inhibited completion of the pipeline installation.
CONSTRUCTION DELAY AVOIDED DUE TO FLEXIBLE SEQUENCE OF
CONSTRUCTION
Notes: Modification 3 was avoided by using flexible sequence of construction. Otherwise, project would have been delayed until modification was approved or utility was relocated.
The Construction Project Engineer stated using the flexible sequence of construction approach saved approximately 2 years of construction. The traditional approach would have put the entire project on hold during these RFIs and created a delay during the utility relocation, but the contractor was able to work on other areas while these RFIs were resolved because of the flexible ESC sequence.

## Slide 56: Installation of Pipe and Structure à Pipe Run from I-3/1 to I-7/1
Notes: So this slide shows you the original sequence of construction and it required the contractor to start at Pine St. and make their way east on the project. So the very first inlet that would have been installed is I-11/1. I-12/1 is the second inlet that needed to be installed. I-11/1 one is the first one here on the corner. Basically about 20 feet of pipe needed to be installed per the first sequence. The next thing that needed to be installed was I-3/1, then followed by the storm drain pipe that connects the two inlets.

## Slide 57: Special Design Considerations

## Slide 58: Should I add more detail?
Special existing conditions (i.e., environmental concerns)
Project-specific conditions relating to design
In the past, any out-of-the-norm condition on your project site would lead to more detail in the sequence. Here are some reasons why that additional information might not be needed!
Notes: In the past, special site conditions would result in more detail in sequence​
Environmental, site issues, stormwater management
Here are some reasons this might not be needed​

## Slide 59: SIMPLIFICATION ISSUE:
Some projects will require review for MD Code 378 or Dam Safety
MDE currently requires more detail for MD Code 378 sequences
Notes: Some projects will require review for 378 or Dam Safety
MDE may make comments requiring more detail within the SOC

## Slide 60: SIMPLIFICATION SOLUTION:
A separate SOC for the MD Code 378/Dam Safety portion can be developed and shown on the appropriate SWM/Drainage sheet.
Notes: A separate SOC for only the MD 378/Dam Safety portion can be developed and shown on the appropriate SWM/Drainage sheet. This will ensure that the dam safety/378 related work will not hold up other parts of construction based on sequencial requirements.

## Slide 61
Additional Requirements:
Anti-degradation Checklist (Submitted to HHD for projects over 1 acre of LOD)
Tier II Review by MDE (coordinated by EPD)
Show Tier II boundary on the plans
"Accelerated Stabilization" - decided on case-by-case basis
NOT NEEDED IN SEQUENCE!
Notes: Covered by note 10 on general note sheet​
Additional requirements (ANIMATION 1)​
Anti-degradation checklist if over 1 acre​
Tier 2 review by MDE​
Show tier 2 boundary on the plan​
Accelerated stabilization may be required (same-day stab, redundant controls. Etc.)​
If all this is done, you don't need detail in sequence!​
​

## Slide 62
Additional Requirements:
If multiple stream usages present, ensure each usage is in a distinct "Work Area"
Use IV-P
Use III-P
NOT NEEDED IN SEQUENCE!
Notes: Stream closure watersheds are covered under note 24 of the ESC General Notes Sheets. This note shows the timeline restrictions for in-stream usage
Additional requirements (ANIMATION 1)​
If multiple stream usages, group work areas within a specific stream use (animation 2)​
Gives contractor flexibility to schedule work around closures​
If all this is done, you don't need detail in sequence!​

## Slide 63: Wetlands and Waterways
Additional Requirements:
11 standard notes from MDE website to be included on applicable project plan sheets
NOT NEEDED IN SEQUENCE!
Notes: Covered by note 9 on general note sheet​
Additional requirements (ANIMATION 1)​
Show 11 standard MDE notes for with in wetlands/waterways​
If all this is done, you don't need detail in sequence!

## Slide 64: HAZMAT and Contaminated Soils
This should be handled in a Specification which will be project-specific, developed in coordination with OMT/HHD.
Additional Requirements:
  Add following plan note:
  REMOVE AND DISPOSE OF CONTAMINATED SOILS (AND GROUNDWATER) ENCOUNTERED DURING EXCAVATION FROM STA (XX+XX – XX+XX) PER THE GUIDELINES OUTLINED IN THE SPECIFICATION
NOT NEEDED IN SEQUENCE!
Notes: Covered in an OMT specification​
Additional requirements (ANIMATION 1)​
If specific area of contaminated soil known, can add note to plan​
If all this is done, you don't need detail in sequence!

## Slide 65: Historical and Cultural Areas
Discussed in IFB SP 100 – Cultural Resources/Archeological Features
Label areas of concern on the plans
NOT NEEDED IN SEQUENCE!
Notes: Covered in IFB (animation 1) SP 100​
Additional requirements (ANIMATION 2/3)​
Label area on plan so contractor knows where this spec applies in the field​
Note should direct the contractor to the spec, and tell contractor who to call​
If all this is done, you don't need detail in sequence!

## Slide 66: High Groundwater & Dewatering
Dewatering for stormwater management facility construction is part of measurement and payment specification for Section 316; for locations where there is high groundwater visible on the soil borings a note on the plans will help contractor make an accurate bid.
Additional Requirements:
Add following note:
  "PROJECT SOIL BORINGS INDICATE HIGH GROUNDWATER. PLAN CONSTRUCTION ACTIVITIES ACCORDINGLY TO ACCOUNT FOR ANY DEWATERING NEEDED."
NOT NEEDED IN SEQUENCE!
Notes: Covered by 316 spec
Additional requirements (ANIMATION 1)
  Add note to plan notifying contractor of high groundwater, for bidding purposes
If all this is done, you don't need detail in sequence!

## Slide 67: Other Special Conditions/Notes:
Storm Drain Construction
  WHEN CONSTRUCTING STORM DRAIN SYSTEMS, ENSURE POSITIVE FLOW IS MAINTAINED
Define NOAA 3-day dry weather forecast
  NOAA 3-DAY DRY WEATHER FORECASTS ARE “DRY” WHEN THE PROBABILITY OF PRECIPITATION DURING EACH OF THE THREE CONSECUTIVE DAYS IS LESS THAN 20%
Definitions can be added to plan -
NOT NEEDED IN SEQUENCE!
Notes: For these conditions, notes can be added to the plan​
Storm drain: don't need to constrained "downstream to upstream" as long as we require positive drainage​
​
NOT NEEDED IN SEQUENCE
“Dry weather period” means a forecasted period with a maximum chance of precipitation of 20 percent each day, as determined by the National Oceanic and Atmospheric Administration (NOAA), for a specified number of consecutive days for the region (ZIP code) in which the project is located.
Reference: https://www.roads.maryland.gov/OHD2/Part_A_Sediment_and_Stormwater_Guidelines.pdf

## Slide 68: STABILIZATION: Let's Talk About It!
Notes: Divisive topic​
Focusing on definitions here​
Focusing on VEGETATED areas​
​

## Slide 69: How Does Stabilization Relate To Flexible SOC?
Using a Flexible Sequence requires clear, concise information be conveyed on the plans
To clearly communicate information in areas where stabilization is needed, we must have a unified understanding of the definition of different types of "Stabilization" and which usage is appropriate
Notes: WHY?​
Flex SOC requires clear communication on plans​
Clear communication requires agreement on what terms mean
​

## Slide 70: TEMPORARY STABILIZATION
Category of stabilization used in long-term construction operations, for areas that will be re-disturbed at a later point in the construction process.
This type of stabilization uses items in Section 704
NOTE: TEMPORARY VEGETATION CANNOT BE IN PLACE LONGER THAN 6 MONTHS!
INCREMENTAL STABILIZATION
TEMPORARY STABILIZATION
Notes: First, lets delve into the different types of "temporary stabilization". These methods are used in long-term construction projects where you might work an area and then need to leave it and come back at a later point in the construction process (think, rough grading before final grade is installed). These types of stabilization use the seeding/mulch mixes shown in section 704 and can only be left in place for 6 months. If you think the area in question may need to be left for more than 6 months, you will need to specify a different type of seed/mulch! Its also important to note that this type of stabilization takes place at the end of a given phase, and is left in place until a future phase. When being actively worked, there will be E&SC measures in place within these areas, so end of day temporary stabilization should not be required.
"TEMPORARY STABILIZATION" is the umbrella term for all short-term stabilizations using these planting items. The sub-types of stabilization are incremental and "temporary" (confusingly)

## Slide 71: TEMPORARY STABILIZATION
Used in phased construction for areas that will be re-disturbed over time
Notes: Temporary stabilization is used in areas of phased construction that will be re-disturbed.
Think of rough-grading in a "temporary swale" which will be converted to a "grass swale" at the end of the construction process.
Temporary stabilization can be installed at the end of a given phase to make an area "stable" until it will next be disturbed.
these areas need to have E&SC in place during the time they are being actively worked and use seed/mulch mixes that
Can only be in place for 6 months. Info on the specific methods used are found in the E&SC manual in section B-4-4. (animate) this photo shows an area where temporary stabilization has been applied through seed, straw and tack.
Additionally, erosion control blankets can be used as "temporary stabilization" in areas where a fill slope is installed. In these areas, even if there is ESC at the base of the slope, you might want to provide an erosion blanket so that if it rains, it doesn't damage your newly established grading.

## Slide 72: PERMANENT STABILIZATION
Establishes the final landscaped condition
Areas where permanent stabilization has been installed should not be re-disturbed
FINAL STABILIZATION
SAME-DAY
STABILIZATION
Notes: PERMANENT- only for ares that WONT be disturbed again​
FINAL and SAME DAY

## Slide 73: FINAL STABILIZATION
Used at end of construction within a given work area
Establishes final landscaped condition
During construction, E&SC needs to be provided in these areas
Notes: At the end of construction activities in work area. ​
When work in that area is finished, besides final removal of E&SC devices. ​
During construction, E&SC measures still needs to be provided in these areas ​
can only be removed once the area is "permanently stabilized" (we'll define later)

## Slide 74: SAME-DAY STABILIZATION
Used at end of construction within a given work DAY
Establishes final landscaped condition
NO additional E&SC measures needed in these areas. Final planting is installed at the end of the day, rendering them "stable".
Include the following note on the plans:
  PERMANENTLY STABILIZE AREAS IDENTIFIED FOR SAME DAY STABILIZATION BY THE END OF EACH WORKDAY. LIMIT DISTURBED AREAS TO ONLY WHAT IS WORKED THAT DAY. DO NOT RE-DISTURB AREAS OF SAME DAY STABILIZATION.
Notes: Same-day stabilization is perhaps the most discussed and confusing of these terms. This type of stabilization takes place as a form of E&SC, in limited/small regions where all proposed work can be performed AND planted to the final landscaped condition within 1 day. These areas should not be re-disturbed after final planting is installed. When this is used on a project as part of the E&SC design, the following note should be used.
"IS there a limit to SDS area?" This is very project dependent. How much a contractor can get done in a day depends on the type of work being done. All designers should be having someone with construction experience review their ESC design to ensure that SDS areas are feasible and constructible.

## Slide 75: Is there a size limit for same day stabilization areas?
Notes: Question we know you are all thinking
project dependent
depends on the type of work being done
someone with construction experience should review their ESC design to ensure that SDS areas are feasible and constructible.
Examples show good/bad usages
  Linear Projects
  Utilities
  Cleaning ditches
  Signal Installations

## Slide 76: SAME DAY STABILIZATION
Notes: This example shows a situation in which SDS is not an appropriate ESC measure. You can see that the original design had water sheet flowing to silt fence, with SDS as a secondary measure

## Slide 77: SAME DAY STABILIZATION
Notes: As part of a modification the grading in the area was changed to be channelized flow. ​
SF was no longer an appropriate measure. ​
Instead of adding an appropriate E&SC measure, SF was removed and SDS was used as the only measure for the entire area. ​
The disturbed area (3.19 acres) is much too large to be constructed in one day ​
showing SDS as only control risks contractor disturbing more area than they can stabilize in a day​
Especially problematic due to DSwetlands and waterways ​

## Slide 78: SAME DAY STABILIZATION
Notes: - from contract PG6245171 (US 1 – College Avenue/Regents Drive to MD 193 (University Boulevard). ​
smaller, distinct areas for which work will be done quickly. ​
For narrow linear type projects (i.e. fiber optic/sidewalk) you will cause more disturbance providing ESC than just doing the work with SDS.​
same day stabilization footprint proposed is approximately 30' x 500'.

## Slide 79: SAME DAY STABILIZATION
Notes: from contract XX1745185 (19-PR-0049) for the interchange lighting improvements along I-70 at MD 122. ​
linear disturbance is appropriate for same day stabilization since there is limited area disturbed along the roadway​
only area that can be stabilized in a single day will be disturbed in a single day​
stabilized area will be permanently stabilized (not re-disturbed later on in project).​
​
LOD width 25' x approximate length​

## Slide 80: ADDITIONAL STABILIZATION TERMS
"Apply permanent stabilization"
  The process of planting/landscaping your site... When you have planted 100% of the vegetated areas, you have "applied permanent stabilization"
"Establishing stabilization"
  Your site has been planted, and is currently growing
"Permanently stabilized"
  95% stabilization of VEGETATED areas... not of the TOTAL DRAINAGE AREA (i.e., If your drainage area is 90% IA and 10% grass, you still need that 10% that is grass to be at 95% growth)
Notes: Read above

## Slide 81: SWM FACILITY INSTALLATION
"Install stormwater management facilities to final grades/ install filter media once drainage area is deemed to be permanently stabilized by QAD with concurrence from the as-built engineer."
Notes: rough grading can occur at any point​
filtration media should not be installed until all drainage areas are "permanently stabilized" ​
include the following not as a second to last step in your flexible construction sequence. ​
The involvement of the as-built engineer in deciding when "permanent stabilization" has been achieved is encouraged​
as-built engineer is ultimately responsible for ensuring that the facility is installed properly and functions long term. ​

## Slide 82: How do you construct a stormwater facility without re-disturbing the area?
Notes: 95% stabilization of vegetated areas required for SWM installation
95% stabilization does not include areas that are needed for access to construct the facility
Example: a bioswale built off the roadway shoulder will require that the grass between the shoulder and the facility be driven over in order to install SWM media
  would not be required that the grass between the shoulder and the facility be "95% stable" before installing media, as it will just be re-disturbed in order to access the facility.

## Slide 83: SEE YOU AFTER LUNCH!

## Slide 84: FLEXIBLE SEQUENCING EXAMPLES
More examples of times when you do NOT need to add more details to your sequence!

## Slide 85: DISCLAIMER:
"The Examples You Are About To See Are True. The Consultants Names Have Been Changed To Protect The Innocent"
Notes: If you see an example of a project you worked on in this presentation don't take it personally
We are all doing our best and learning
This applies to the previous same-day stabilization examples as well
Following examples are projects that tried to provide flexibility in SOC
We are highlighting what was done well, and what could have been better

## Slide 86: Temporary storm drain system Plan Notes
SIMPLIFICATION
OPPORTUNITY:
Notes: contract FR6755181 US 15 at Mt. Zion Road/Elmer Derr Road Ridesharing Facility ​
You can see, SOC is fairly flexible. Calls for work to be done while meeting certain "constraints"​
We'll show some ways it could have been further edited to allow flexibility​
Sequence of construction Step 3 of Sequence of Construction shown above​
Temporary storm drain to divert clearwater away from the proposed SWM facility location.​
Next slide shows this was also a plan note

## Slide 87: Temporary storm drain system Plan Notes
SIMPLIFICATION
OPPORTUNITY:
Notes: plan sheet screenshot includes highlighted note at the inlet where the temporary storm drain is required (see highlighted text box). ​
Since note was on the plan and only applies to this one location on the project, does not need to be in sequence​
Additional Simplification Opportunity: If Temporary storm drain applies to multiple areas or phases of a project, General temporary storm drain note would be appropriate on the plans.

## Slide 88: Inlets/Pipes being installed and/or blocked until later phase
SIMPLIFICATION
OPPORTUNITY:
Notes: Contract PG1065184 (which we discussed at length earlier)​
included proprietary bioretention BMPs ​
Directing sediment laden water into the bioretentions would compromise the integrity ​
addressed by a general note on the SOC Step 7 above about temporarily blocking the inlets inflowing to all SWM facilities until the facilities are constructed and all upstream areas permanently stabilized.​

## Slide 89: SIMPLIFICATION OPPORTUNITY: PG1065184
Notes: See Contract PG1065184 Flexible Sequence above
Any opportunity to further simplify?
Solution: Note 6
  Each BMP ID doesn't need to be listed individually (info already on SWM sheets)
  Note could be further simplified to "PRIOR TO CONSTRUCTING SWM FACILITIES AND BIORETENTION INLET OPENINGS..."
  (MAKE CLEAR THAT THE REASON WE DON’T WANT TO LIST THEM IS CAUSE YOU WANT TO AVOID FORGETTING TO LIST ONE AND IT CAUSING AN ISSUE)

## Slide 90: SIMPLIFICATION OPPORTUNITY:
Notes: This example is from the ESC plan sheets on contract PG1065184 (one of the first contracts to undergo the simplified sequence of construction project). These notes were repeated on each individual ESC plan sheet in the contract. Review and determine if all notes are required.
Note 1 can be removed from each individual plan sheet. This reference to the overall sequence of construction is not required on each individual plan sheet.
Note 4 can be removed. ESC is not related/tied to the maintenance of traffic, so they should not be linked to each other.
Note 6 can be deleted.
Recommend pulling notes 2, 5, and 6 to project specific ESC general notes instead of being repeated on each plan sheet.

## Slide 91
Locations where detailed notes on specific plan sheets preferred instead of detailed SOC instruction
Plan Notes
SIMPLIFICATION
EXAMPLE PG7825284:
Notes: Plans may require notes for instead inserting information in SOC
Contract PG7825284 Phase 3 ESC existing grate inlet EX-I-32 that will be modified to proposed double K Inlet
Example plan note requires contractor to change inlet protection type after drainage improvement (AGIP to MSIP)
SOC note 2 requires inlet protection as perimeter
SOC note 3 requires inlet protection installation after new drainage structures installed
For this very specific situation where drainage structure type changes, a plan note on the individual sheet is more helpful than a sequence of construction step for clarity

## Slide 92
EXAMPLE: MO5935870
Notes: MO5935870; Kensington Parkway Intersection Reconstruction
Work included sidewalk reconstruction, storm drain, stormwater management
Sequence seen above – all work is contained within step 3, with constraints listed there
First we can highlight how step 3a is handled through additional plan notes

## Slide 93
FLEXIBLE SEQUENCE EXAMPLE: MO5935870
Notes: notes on blocking inlets were added to plans
Notes were also added to clarify other areas wherein construction required extra detail
Since this information is included on the plans, did it need to be in the sequence?

## Slide 94
Could these "Constraints" be Plan Notes?
Notes: In this early version of a FSOC, the "perform work" step was given constraints within the sequence
This approach is not "wrong", but since it puts the detail in the sequence instead of on the plans, it could lead to it being enforced in order in the field
Plans are part of contract documents so are just as "enforceable" as SOC
We'll show some alternate ways that these "constraints" could have been included as plan notes on the following slides
this detail about blocking flow to the trench drain upstream of an ESD facility was added as a "constraint" in the sequence

## Slide 95
Block flow to TD-402 until construction of ESD 3-2 is complete
FLEXIBLE SEQUENCE EXAMPLE: MO5935870
Notes: notes on blocking inlets could have been added to plans
Would have allowed constraint to be removed from sequence

## Slide 96: Inlets/Pipes being installed and/or blocked until later phase
SIMPLIFICATION
OPPORTUNITY:
Notes: Contract PG1065184 was one of the first contracts to utilize flexible sequence of construction. In an effort to provide adequate information for the contractor, the sequence of construction was revised and there were additional plan notes added to each individual ESC plan sheets (see notes on the right side of slide from ESC plan sheet).
Lesson Learned: Redundant information on plan set is not encouraged. Since note 6 was already included in the overall sequence of construction, it does not need to be called out at each specific location on the ESC plan sheets. This note could be removed if we were working on this plan set now. It has potential to become confusing if notes are inconsistent or missed one inlet but included for others.

## Slide 97: BREAKOUT SESSIONS:
Not sure where to go? Look at your badge!
AFTER LUNCH GO TO BREAKOUT ROOMS

## Slide 98: Situations where design materials (fill, etc.) from previous phasing may be needed for later phases
SIMPLIFICATION ISSUE:
Notes: WA4515180 I-70 over Crystal Falls: In this example, ESC phasing was set up in such a way that the fill from one side of the temporary roadway construction could be re-used on the other side of the road. This would require that the construction be done in sequence. However, in an attempt to give the contractor flexibility, concurrent grading operations were allowed in the sequence (see step 4). In that case, the contractor could ask for an extra for the additional fill to construct both sides simultaneously. If allowing this flexibility, perhaps we add a note dictating that the contractor choosing a different sequence will be at their cost, not SHA's.
Additionally, this project was phased in a way which encouraged the replacement of the WB bridge first, as it was more deteriorated and had holes actively forming in the bridge deck. Due to the line in the sequence allowing the contractor to perform steps "concurrently or in any order", the contractor has opted to construct the EB bridge first. Is there a way to allow flexibility in situations like this while also prioritizing public safety?
(Activity: have participants go over this situation and come up with note/solution to the materials issue.)
Moderator Response: For safety issues, collaboration with construction/field personnel will be helpful in deciding where the line is as far as when it is necessary to have a specific sequence for each specific project, such as safety reasons, that dictate order.

## Slide 99
4. WITH APPROVAL FROM THE ENGINEER AND SHA QAD, CONTRACTOR MAY CONSTRUCT EASTBOUND AND WESTBOUND TEMPORARY ROADWAYS CONCURRENTLY AT NO ADDITIONAL COST TO THE ADMINISTRATION. NOTE THAT QUANTITIES PRESENTED ON THESE PLANS ARE REPRESENTATIVE OF THE SPECIFIC DESIGN SHOWN; ALL REQUIRED EROSIONS AND SEDIMENT CONTROL SHALL BE INSTALLED AND APPROVED BY SHA QAD AS IN CONCURRENT GRADING OPERATIONS.
SOLUTION:
Notes: WA4515180 I-70 over Crystal Falls: In this example, ESC phasing was set up in such a way that the fill from one side of the temporary roadway construction could be re-used on the other side of the road. This would require that the construction be done in sequence. However, in an attempt to give the contractor flexibility, concurrent grading operations were allowed in the sequence (see step 4). In that case, the contractor could ask for an extra for the additional fill to construct both sides simultaneously. If allowing this flexibility, perhaps we add a note dictating that the contractor choosing a different sequence will be at their cost, not SHA's.
Additionally, this project was phased in a way which encouraged the replacement of the WB bridge first, as it was more deteriorated and had holes actively forming in the bridge deck. Due to the line in the sequence allowing the contractor to perform steps "concurrently or in any order", the contractor has opted to construct the EB bridge first. Is there a way to allow flexibility in situations like this while also prioritizing public safety?
(Activity: have participants go over this situation and come up with note/solution to the materials issue. For safety issues, collaboration with construction/field personnel will be helpful in deciding where the line is as far as when it is necessary to have a specific sequence for safety reasons.) *TALK TO OFFICE OF CONSTRUCTION ABOUT THIS ONE

## Slide 100: Example Project – MD 190 Intersection Improvements
Breakout groups will spend ~30 minutes simplifying the SOC for this project
Notes: This project involved pedestrian safety improvements along MD 190 near Pyle Road. Proposed work included sidewalk installation, retaining wall design, lighting upgrades, and stormwater management. As you can see, some of the approaches we've discussed in this training were used in the design of the E&SC (ie. Using "work areas")

## Slide 101: Coordination with projects taking place concurrently in the same project area
Notes: This sequence already allows for some flexibility by allowing for concurrent work and the use of "work areas". However, there is further room to simplify! Take some time to break into groups of ~5 and see if you can figure out ways to streamline the sequence of construction by removing unnecessary or redundant information. Moderators will be circling the room to help guide the conversation.

## Slide 102: Coordination with projects taking place concurrently in the same project area
GNGN
Direct Contractor to General Note #2
Redundant with note 1.
7. WHERE TREE ROOT PRUNING IS SPECIFIED (SEE LANDSCAPE PLANS), PERFORM TREE ROOT PRUNING
CONCURRENTLY WITH INSTALLATION OF CONTROLS.
8. WORK IN EACH CONSTRUCTION AREA MAY BE PERFORMED CONCURRENTLY AND IN ANY ORDER.
POSITIVE SURFACE RUNOFF AND STORM DRAIN FLOWS MUST BE MAINTAINED, AND THE SPECIFIED
CONTROLS MUST BE INSTALLED.
9. IN AREAS WHERE HIGHLY EROSIVE SOILS EXIST, STABILIZE WITH SSM IMMEDIATELY UPON
COMPLETING GRADING.
10. PERFORM GRADING AS SHOWN IN THE HATCHED AREAS USING "SAME DAY STABILIZATION"
METHOD. SSF WITHIN GRADING LIMIT SHALL BE ADJUSTED AS NEEDED DURING CONSTRUCTION.
ALL DISTURBED AREA WITHIN HATCHED AREAS SHALL BE STABILIZED VIA FINAL PLANTING
METHODS AT THE END OF EACH WORK DAY.
ARE ANY STEPS REDUNDANT WITH GENERAL NOTES/WOULD WORK BETTER AS A PLAN NOTE?
Tree root pruning, and general sequence items 3 and 4 should be plan notes.
Same-day stabilization pattern definition should be plan note.
No need to call out these "additional areas" as they are covered by previous steps/note 10
PER GENERAL NOTE 2
Notes: We'll start by discussing "general notes". The updates to the ESC general notes contain a lot of information that used to be included in the sequence and can now be removed.
(animate) for instance, step 1 is redundant with note 2 of the general notes which informs the contractor to notify QAD
Some of the information is also redundant to the project specific general notes given on the left; such as instructing to clear and grub in steps 1 of construction areas 1 and 2
(animate)
Further, some information that does not have to do with construction sequencing and would be better as a note. (animate) such as steps referencing tree root pruning and highly erosive soils.
Lastly, defining the SDS area can be a general note and not a sequence step.

## Slide 103
SEQUENCE OF CONSTRUCTION
THE CONTRACTOR SHALL NOTIFY SHA'S QUALITY ASSURANCE DIVISION PER GENERAL NOTE 2
STAKEOUT LOD AND INSTALL TOCF. THE CONTRACTOR SHALL REFERENCE THE LANDSCAPE PLANS FOR LIMITS OF TOCF.
CONSTRUCTION AREA 1 (SEE ES-02 AND ES-03)
INSTALL ESC IN CONSTRUCTION AREA 1, EXCEPT THAT INLET PROTECTION GIP 02-2 SHALL BE INSTALLED IMMEDIATELY AFTER INLET I-1 IS INSTALLED, AND PST 02-1 SHALL BE INSTALLED PRIOR TO THE CONTRUCTION OF THE BIO-SWALE.
PERFORM PROPOSED CONSTRUCTION AS SHOWN ON THE PLANS EXCEPT FOR THE CROSS HATCHED AREA ON ES-02.
PRIOR TO CONSTRUCTING BSW 1-1, PERMANENTLY STABILIZE ALL DISTURBED AREAS DRAINING TO FACILITY. CONSTRUCT AND PERMANENTLY STABILIZE BSW 1-1. WITH THE APPROVAL OF QAD, REMOVE PST 02-1, COMPLETE THE REMAINING BSW 1-1 CONSTRUCTION, AND PERMANENTLY STABILIZE THOSE AREAS.
DURING A 3-DAY NOAA DRY WEATHER FORECAST, WITH THE APPROVAL OF THE QAD, REMOVE GIP 02-1. PERFORM PROPOSED CONSTRUCTION AS SHOWN IN THE CROSS HATCHED AREAS ON ES-02.
PERMANENTLY STABILIZE ALL REMAINING DISTURBED AREAS. WITH THE APPROVAL OF QAD, REMOVE ESC MEASURES AND PERMANENTLY STABILIZE THOSE AREAS.
CONSTRUCTION AREA 2 (SEE ES-02 AND ES-03)
INSTALL ALL SSF IN CONSTRUCTION AREA 2.
PERFORM PROPOSED CONSTRUCTION AS SHOWN ON THE PLANS. ANY DISTURBANCE WITHIN THE HATCHED AREA SHALL BE STABILIZED AT THE END OF EACH WORK DAY.
PERMANENTLY STABILIZE ALL REMAINING DISTURBED AREAS. WITH THE APPROVAL OF QAD, REMOVE ESC MEASURES AND PERMANENTLY STABILIZE THOSE AREAS.
GNGN
We show same day stabilization pattern on plans; there's no reason these areas need to be constructed last
NOTES
ONLY MINOR CLEARING AND GRUBBING SHALL OCCUR FOR THE INSTALLATION OF THE EROSION AND SEDIMENT CONTROL (ESC) MEASURES, AND ALL ESC MEASURES AND DEVICES SHALL BE IN PLACE AND FUNCTIONING PROPERLY FOR EACH CONSTRUCTION PHASE PRIOR TO MASS CLEARING AND GRUBBING OF THE WORKING AREA FOR THAT PHASE AND COMMENCING ANY CONSTRUCTION ACTIVITIES.
MAINTAIN ALL SEDIMENT CONTROL PRACTICES ACCORDING TO THE MARYLAND 2011 STANDARDS UNTIL THE ENTIRE SITE IS STABILIZED.
CLEAR AND GRUB AND PROCEED RO CONSTRUCTION ACCORDING TO THE SEQUENCE SPECIFIED ON THE MAINTENANCE OF TRAFFIC (MOT) PLANS.
UNLESS NOTED OTHERWISE, THE CONTRACTOR SHALL USE PORTABLE SEDIMENT TANKS OR SUMP PITS TO DEWATER AREAS OF TRAPPED SEDIMENT LADEN WATER DURING CONSTRUCTION. ALL DEWATERING SHALL BE DISCHARGED TO A STABLE OUTFALL APPROVED BY THE SHE QUALITY ASSURANCE DIVISION (QAD).
UTILITIES AND STORM DRAINS SHOWN ON THE EROSION AND SEDIMENT CONTROL PLANS ARE FOR THE GUIDANCE OF THE CONTRACTOR ONLY. ALL UTILITIES SHALL BE CONSTRUCTED AS SHOWN ON THE ROADWAY PLANS.
CONTRACTOR SHALL LOCATE THE STAGING AND STOCKPILING AREAS UPON SHA QAD'S APPROVAL. CONTRACTOR IS RESPONSIBLE FOR PROVIDING ANY ADDITIONAL EROSION AND SEDIMENT CONTROLS FOR STAGING AND STOCKPILE AREAS AS REQUIRED BY THE SHA QAD.
WHERE TREE ROOT PRUNING IS SPECIFIED (SEE LANDSCAPE PLANS), PERFORM TREE ROOT PRUNING CONCURRENTLY WITH INSTALLATION OF CONTROLS.
WORK IN EACH CONSTRUCTION AREA MAY BE PERFORMED CONCURRENTLY AND IN ANY ORDER. POSITIVE SURFACE RUNOFF AND STORM DRAIN FLOWS MUST BE MAINTAINED, AND THE SPECIFIES CONTROLS MUST BE INSTALLED.
IN AREAS WHERE HIGHLY ERODIBLE SOILS EXIST, STABILIZE WITH SSM IMMEDIATELY UPON COMPLETING GRADING.
PERFORM GRADING AS SHOWN IN THE HATCHED AREAS USING "SAME DAY STABILIZATION" METHOD. SSF WITHIN GRADING LIMIT SHALL BE ADJUSTED AS NEEDED DURING CONSTRUCTION. ALL DISTURBED AREA WITHIN HATCHED AREAS SHALL BE STABILIZED VIA. FINAL PLANTING METHODS AT THE END OF EACH WORK DAY.
ARE THERE ANY STEPS THAT PROVIDE A TIMING RESTRICTION THAT ISN'T NECESSARY?
SEQUENCE OF CONSTRUCTION
EROSION AND SEDIMENT CONTROL
We specify removal of all ESC measures in step 5 so calling out GIP 02-1 and PST 02-1 is not necessary
Notes: Next was can look through for any items referencing specific timing on activities that doesn't provide value.
For instance, the sequence here implies that same day stabilization areas should be installed after or at a different time than the areas draining to ESC devices. (animate) There isn't a reason for this and it doesn't add value, so that language can be removed.
Additionally, removal of specific ESC devices is called out in some steps, while there is a general step (5) which details how to remove ESC devices (animate) – since this information is redundant, the individual callouts can be removed.

## Slide 104
SEQUENCE OF CONSTRUCTION
THE CONTRACTOR SHALL NOTIFY SHA'S QUALITY ASSURANCE DIVISION PER GENERAL NOTE 2
STAKEOUT LOD AND INSTALL TOCF. THE CONTRACTOR SHALL REFERENCE THE LANDSCAPE PLANS FOR LIMITS OF TOCF.
CONSTRUCTION AREA 1 (SEE ES-02 AND ES-03)
INSTALL ESC IN CONSTRUCTION AREA 1, EXCEPT THAT INLET PROTECTION GIP 02-2 SHALL BE INSTALLED IMMEDIATELY AFTER INLET I-1 IS INSTALLED, AND PST 02-1 SHALL BE INSTALLED PRIOR TO THE CONSTRUCTION OF THE BIO-SWALE.
PERFORM PROPOSED CONSTRUCTION AS SHOWN ON THE PLANS.
PRIOR TO CONSTRUCTING BSW 1-1, PERMANENTLY STABILIZE ALL DISTURBED AREAS DRAINING TO FACILITY. WITH QAD APPROVAL, CONSTRUCT AND PERMANENTLY STABILIZE BSW 1-1.
PERMANENTLY STABILIZE ALL REMAINING DISTURBED AREAS. WITH THE APPROVAL OF QAD, REMOVE ESC MEASURES AND PERMANENTLY STABILIZE THOSE AREAS.
CONSTRUCTION AREA 2 (SEE ES-02 AND ES-03)
INSTALL ALL SSF IN CONSTRUCTION AREA 2.
PERFORM PROPOSED CONSTRUCTION AS SHOWN ON THE PLANS. ANY DISTURBANCE WITHIN THE HATCHED AREA SHALL BE STABILIZED AT THE END OF EACH WORK DAY.
PERMANENTLY STABILIZE ALL REMAINING DISTURBED AREAS. WITH THE APPROVAL OF QAD, REMOVE ESC MEASURES AND PERMANENTLY STABILIZE THOSE AREAS.
GNGN
Already specified in plan note
NOTES
ONLY MINOR CLEARING AND GRUBBING SHALL OCCUR FOR THE INSTALLATION OF THE EROSION AND SEDIMENT CONTROL (ESC) MEASURES, AND ALL ESC MEASURES AND DEVICES SHALL BE IN PLACE AND FUNCTIONING PROPERLY FOR EACH CONSTRUCTION PHASE PRIOR TO MASS CLEARING AND GRUBBING OF THE WORKING AREA FOR THAT PHASE AND COMMENCING ANY CONSTRUCTION ACTIVITIES.
MAINTAIN ALL SEDIMENT CONTROL PRACTICES ACCORDING TO THE MARYLAND 2011 STANDARDS UNTIL THE ENTIRE SITE IS STABILIZED.
CLEAR AND GRUB AND PROCEED RO CONSTRUCTION ACCORDING TO THE SEQUENCE SPECIFIED ON THE MAINTENANCE OF TRAFFIC (MOT) PLANS.
UNLESS NOTED OTHERWISE, THE CONTRACTOR SHALL USE PORTABLE SEDIMENT TANKS OR SUMP PITS TO DEWATER AREAS OF TRAPPED SEDIMENT LADEN WATER DURING CONSTRUCTION. ALL DEWATERING SHALL BE DISCHARGED TO A STABLE OUTFALL APPROVED BY THE SHE QUALITY ASSURANCE DIVISION (QAD).
UTILITIES AND STORM DRAINS SHOWN ON THE EROSION AND SEDIMENT CONTROL PLANS ARE FOR THE GUIDANCE OF THE CONTRACTOR ONLY. ALL UTILITIES SHALL BE CONSTRUCTED AS SHOWN ON THE ROADWAY PLANS.
CONTRACTOR SHALL LOCATE THE STAGING AND STOCKPILING AREAS UPON SHA QAD'S APPROVAL. CONTRACTOR IS RESPONSIBLE FOR PROVIDING ANY ADDITIONAL EROSION AND SEDIMENT CONTROLS FOR STAGING AND STOCKPILE AREAS AS REQUIRED BY THE SHA QAD.
WHERE TREE ROOT PRUNING IS SPECIFIED (SEE LANDSCAPE PLANS), PERFORM TREE ROOT PRUNING CONCURRENTLY WITH INSTALLATION OF CONTROLS.
WORK IN EACH CONSTRUCTION AREA MAY BE PERFORMED CONCURRENTLY AND IN ANY ORDER. POSITIVE SURFACE RUNOFF AND STORM DRAIN FLOWS MUST BE MAINTAINED, AND THE SPECIFIES CONTROLS MUST BE INSTALLED.
IN AREAS WHERE HIGHLY EROSIVE SOILS EXIST, STABILIZE WITH SSM IMMEDIATELY UPON COMPLETING GRADING.
PERFORM GRADING AS SHOWN IN THE HATCHED AREAS USING "SAME DAY STABILIZATION" METHOD. SSF WITHIN GRADING LIMIT SHALL BE ADJUSTED AS NEEDED DURING CONSTRUCTION. ALL DISTURBED AREA WITHIN HATCHED AREAS SHALL BE STABILIZED VIA. FINAL PLANTING METHODS AT THE END OF EACH WORK DAY.
ARE THERE ANY STEPS THAT WOULD WORK BETTER AS PLAN NOTE?
SEQUENCE OF CONSTRUCTION
EROSION AND SEDIMENT CONTROL
Notes: Next, as discussed earlier, a way to remove items from the SOC is to include plan callouts detailing if an items construction is contingent on another item. For this project, that was already done in the form of notes 1 and 2 on sheet ES-02 (animate). However, the info was still included in the sequence. These references can be removed as they are already covered by a plan note. (animate)

## Slide 105
SEQUENCE OF CONSTRUCTION
THE CONTRACTOR SHALL NOTIFY SHA'S QUALITY ASSURANCE DIVISION PER GENERAL NOTE 2
STAKEOUT LOD AND INSTALL TOCF. THE CONTRACTOR SHALL REFERENCE THE LANDSCAPE PLANS FOR LIMITS OF TOCF.
CONSTRUCTION AREA 1 (SEE ES-02 AND ES-03)
INSTALL ESC IN CONTRUCTION AREA 1
PERFORM PROPOSED CONSTRUCTION AS SHOWN ON THE PLANS.
PRIOR TO CONSTRUCTING BSW 1-1, PERMANENTLY STABILIZE ALL DISTURBED AREAS DRAINING TO FACILITY. WITH QAD APPROVAL, CONSTRUCT AND PERMANENTLY STABILIZE BSW 1-1.
PERMANENTLY STABILIZE ALL REMAINING DISTURBED AREAS. WITH THE APPROVAL OF QAD, REMOVE ESC MEASURES AND PERMANENTLY STABILIZE THOSE AREAS.
CONSTRUCTION AREA 2 (SEE ES-02 AND ES-03)
INSTALL ALL SSF IN CONSTRUCTION AREA 2.
PERFORM PROPOSED CONSTRUCTION AS SHOWN ON THE PLANS. ANY DISTURBANCE WITHIN THE HATCHED AREA SHALL BE STABILIZED AT THE END OF EACH WORK DAY.
PERMANENTLY STABILIZE ALL REMAINING DISTURBED AREAS. WITH THE APPROVAL OF QAD, REMOVE ESC MEASURES AND PERMANENTLY STABILIZE THOSE AREAS.
NOTES
ONLY MINOR CLEARING AND GRUBBING SHALL OCCUR FOR THE INSTALLATION OF THE EROSION AND SEDIMENT CONTROL (ESC) MEASURES, AND ALL ESC MEASURES AND DEVICES SHALL BE IN PLACE AND FUNCTIONING PROPERLY FOR EACH CONSTRUCTION PHASE PRIOR TO MASS CLEARING AND GRUBBING OF THE WORKING AREA FOR THAT PHASE AND COMMENCING ANY CONSTRUCTION ACTIVITIES.
MAINTAIN ALL SEDIMENT CONTROL PRACTICES ACCORDING TO THE MARYLAND 2011 STANDARDS UNTIL THE ENTIRE SITE IS STABILIZED.
CLEAR AND GRUB AND PROCEED TO CONSTRUCTION ACCORDING TO THE SEQUENCE SPECIFIED ON THE MAINTENANCE OF TRAFFIC (MOT) PLANS.
UNLESS NOTED OTHERWISE, THE CONTRACTOR SHALL USE PORTABLE SEDIMENT TANKS OR SUMP PITS TO DEWATER AREAS OF TRAPPED SEDIMENT LADEN WATER DURING CONSTRUCTION. ALL DEWATERING SHALL BE DISCHARGED TO A STABLE OUTFALL APPROVED BY THE SHE QUALITY ASSURANCE DIVISION (QAD).
UTILITIES AND STORM DRAINS SHOWN ON THE EROSION AND SEDIMENT CONTROL PLANS ARE FOR THE GUIDANCE OF THE CONTRACTOR ONLY. ALL UTILITIES SHALL BE CONSTRUCTED AS SHOWN ON THE ROADWAY PLANS.
CONTRACTOR SHALL LOCATE THE STAGING AND STOCKPILING AREAS UPON SHA QAD'S APPROVAL. CONTRACTOR IS RESPONSIBLE FOR PROVIDING ANY ADDITIONAL EROSION AND SEDIMENT CONTROLS FOR STAGING AND STOCKPILE AREAS AS REQUIRED BY THE SHA QAD.
WHERE TREE ROOT PRUNING IS SPECIFIED (SEE LANDSCAPE PLANS), PERFORM TREE ROOT PRUNING CONCURRENTLY WITH INSTALLATION OF CONTROLS.
WORK IN EACH CONSTRUCTION AREA MAY BE PERFORMED CONCURRENTLY AND IN ANY ORDER. POSITIVE SURFACE RUNOFF AND STORM DRAIN FLOWS MUST BE MAINTAINED, AND THE SPECIFIES CONTROLS MUST BE INSTALLED.
IN AREAS WHERE HIGHLY ERODIBLE SOILS EXIST, STABILIZE WITH SSM IMMEDIATELY UPON COMPLETING GRADING.
PERFORM GRADING AS SHOWN IN THE HATCHED AREAS USING "SAME DAY STABILIZATION" METHOD. SSF WITHIN GRADING LIMIT SHALL BE ADJUSTED AS NEEDED DURING CONSTRUCTION. ALL DISTURBED AREA WITHIN HATCHED AREAS SHALL BE STABILIZED VIA. FINAL PLANTING METHODS AT THE END OF EACH WORK DAY.
SEQUENCE OF CONSTRUCTION
EROSION AND SEDIMENT CONTROL
Change to "as specified in contract documents"
Change to "necessary" since "minor" is a vague term
ANY OTHER ITEMS THAT CAN BE REMOVED?
Notes: Lastly, we want to make sure we are correctly directing the contractor to the location where the information they are looking for is located. Some information is not located on the plans but rather in the specifications (think about the "Cultural Resources/Archeological Features" spec we talked about earlier in the "special environmental concerns" section. Since the information isn't always ONLY on the plans, we want to make sure we reference all areas the contractor might need to look in the sequence – therefore, we want to adjust "as shown on plans" to "as specified in contract documents"
We also want to make sure that we are clearly communicating with our sequence; since the word "minor" in step one invites questions (ie. What constitutes "minor" clearing and grubbing?) we will change this word to "necessary".

## Slide 106
SEQUENCE OF CONSTRUCTION
THE CONTRACTOR SHALL NOTIFY SHA'S QUALITY ASSURANCE DIVISION PER GENERAL NOTE 2
STAKEOUT LOD AND INSTALL TOCF. THE CONTRACTOR SHALL REFERENCE THE LANDSCAPE PLANS FOR LIMITS OF TOCF.
CONSTRUCTION AREA 1 (SEE ES-02 AND ES-03)
INSTALL ESC IN CONSTRUCTION AREA 1
PERFORM PROPOSED CONSTRUCTION AS SPECIFIED IN CONSTRUCTION DOCUMENTS.
PRIOR TO CONSTRUCTING BSW 1-1, PERMANENTLY STABILIZE ALL DISTURBED AREAS DRAINING TO FACILITY. WITH QAD APPROVAL, CONSTRUCT AND PERMANENTLY STABILIZE BSW 1-1.
PERMANENTLY STABILIZE ALL REMAINING DISTURBED AREAS. WITH THE APPROVAL OF QAD, REMOVE ESC MEASURES AND PERMANENTLY STABILIZE THOSE AREAS.
CONSTRUCTION AREA 2 (SEE ES-02 AND ES-03)
INSTALL ALL SSF IN CONSTRUCTION AREA 2.
PERFORM PROPOSED CONSTRUCTION AS SPECIFIED IN CONSTRUCTION DOCUMENTS. ANY DISTURBANCE WITHIN THE HATCHED AREA SHALL BE STABILIZED AT THE END OF EACH WORK DAY.
PERMANENTLY STABILIZE ALL REMAINING DISTURBED AREAS. WITH THE APPROVAL OF QAD, REMOVE ESC MEASURES AND PERMANENTLY STABILIZE THOSE AREAS.
GNGN
NOTES
ONLY NECESSARY CLEARING AND GRUBBING SHALL OCCUR FOR THE INSTALLATION OF THE EROSION AND SEDIMENT CONTROL (ESC) MEASURES, AND ALL ESC MEASURES AND DEVICES SHALL BE IN PLACE AND FUNCTIONING PROPERLY FOR EACH CONSTRUCTION PHASE PRIOR TO MASS CLEARING AND GRUBBING OF THE WORKING AREA FOR THAT PHASE AND COMMENCING ANY CONSTRUCTION ACTIVITIES.
MAINTAIN ALL SEDIMENT CONTROL PRACTICES ACCORDING TO THE MARYLAND 2011 STANDARDS UNTIL THE ENTIRE SITE IS STABILIZED.
CLEAR AND GRUB AND PROCEED TO CONSTRUCTION ACCORDING TO THE SEQUENCE SPECIFIED ON THE MAINTENANCE OF TRAFFIC (MOT) PLANS.
UNLESS NOTED OTHERWISE, THE CONTRACTOR SHALL USE PORTABLE SEDIMENT TANKS OR SUMP PITS TO DEWATER AREAS OF TRAPPED SEDIMENT LADEN WATER DURING CONSTRUCTION. ALL DEWATERING SHALL BE DISCHARGED TO A STABLE OUTFALL APPROVED BY THE SHE QUALITY ASSURANCE DIVISION (QAD).
UTILITIES AND STORM DRAINS SHOWN ON THE EROSION AND SEDIMENT CONTROL PLANS ARE FOR THE GUIDANCE OF THE CONTRACTOR ONLY. ALL UTILITIES SHALL BE CONSTRUCTED AS SHOWN ON THE ROADWAY PLANS.
CONTRACTOR SHALL LOCATE THE STAGING AND STOCKPILING AREAS UPON SHA QAD'S APPROVAL. CONTRACTOR IS RESPONSIBLE FOR PROVIDING ANY ADDITIONAL EROSION AND SEDIMENT CONTROLS FOR STAGING AND STOCKPILE AREAS AS REQUIRED BY THE SHA QAD.
WHERE TREE ROOT PRUNING IS SPECIFIED (SEE LANDSCAPE PLANS), PERFORM TREE ROOT PRUNING CONCURRENTLY WITH INSTALLATION OF CONTROLS.
WORK IN EACH CONSTRUCTION AREA MAY BE PERFORMED CONCURRENTLY AND IN ANY ORDER. POSITIVE SURFACE RUNOFF AND STORM DRAIN FLOWS MUST BE MAINTAINED, AND THE SPECIFIES CONTROLS MUST BE INSTALLED.
IN AREAS WHERE HIGHLY ERODIBLE SOILS EXIST, STABILIZE WITH SSM IMMEDIATELY UPON COMPLETING GRADING.
PERFORM GRADING AS SHOWN IN THE HATCHED AREAS USING "SAME DAY STABILIZATION" METHOD. SSF WITHIN GRADING LIMIT SHALL BE ADJUSTED AS NEEDED DURING CONSTRUCTION. ALL DISTURBED AREA WITHIN HATCHED AREAS SHALL BE STABILIZED VIA. FINAL PLANTING METHODS AT THE END OF EACH WORK DAY.
SEQUENCE OF CONSTRUCTION
EROSION AND SEDIMENT CONTROL
WE END UP WITH...
Notes: By making these edits, we are left with a final product that is similar to our "stock sequence", as well as some general notes and plan callouts which give the contractor guidance on how to perform Constuction activities.

## Slide 107: Example Project – BMP Retrofit
Notes: This project involved BMP 130220 retrofit of existing dry extended detention pond to a wet detention pond. This facility is located between MD 100 and the off-ramp to MD 103. Proposed work included expanding the pond footprint to provide a wet pool, inflow stabilization, riser replacement, emergency spillway grading, and permanent stabilization.
This plan view was developed using the detailed sequence of construction. The flexible sequence of construction approach may require additional labels or details on the plan view for clarity. What revisions to the plan view or additional labels could be added to the plan view as part of the flexible sequence of construction approach.

## Slide 108: Example Project – MD 190 Intersection Improvements
Notes: This bullet is specifically meant to discuss situations where you have a project which needs to be submitted to a separate ESC reviewing agency for approval. Similar to the discussion about MDE, these agencies may require specific items be included in the SOC. This is the SOC from the Bay Bridge AET conversion project, which includes the "estimated time to complete" as outlines by AASCD in their ESC requirements. This addition was made at direct request of AASCD. Additionally, I have pulled an excerpt from their ESC checklist which highlights special details they want added to the sequence in areas where a stream crossing is being added/sediment traps are being used.
(NOTE: if HHD or PRD have any examples where sequence changes were made due to input by other agencies they would be welcome! Was thinking MNCPPC would be a good example, but I do not have any state projects in my roster that required that coordination)
((Rahul to get a project that he did for Jonathan Brown; also ask David Black about MD 97 Bypass if they had any E&S examples of changes. This would be a good example of a situation where you can add it to the breakout session and have people talk about how to approach it. In breakout sessions, make sure we are guiding people to think about “what is the best approach that can address the concern without polluting the main sequence?))

## Slide 109: Coordination with projects taking place concurrently in the same project area
ORIGINAL SEQUENCE: ASSUME THIS IS NOT AN MD CODE 378 EMBANKMENT
Notes: This sequence was drafted for an MD 378 facility and did not include any flexibility. For this example, assume the facility is not an MD 378 embankment and attempt to simplify!
Take some time to break into groups of ~5 and see if you can figure out ways to streamline the sequence of construction by removing unnecessary or redundant information. Moderators will be circling the room to help guide the conversation.

## Slide 110: Coordination with projects taking place concurrently in the same project area
MOT sequence of construction should not be referenced on ESC plans
ARE ANY STEPS THAT ARE NOT RELEVANT TO EROSION AND SEDIMENT CONTROL?
NOTE 4. TRAFFIC BARRIERS NOT RELATED TO ESC
NOTE 1: OTHER PERMITS PART OF CONTRACT SPECIFICATIONS. NOT RELATED TO ESC
NOTE 19: ROADWAY ITEMS NOT RELATED TO ESC. PART OF NOTE IS NOT APPLICABLE
Notes: We'll start by considering if any items are not relevant to erosion and sediment control.
(animate) For instance, MOT sequence of construction is not related to ESC sequence and should not be referenced on ESC plans.
(animate) note 4 for traffic barrier location is also not related to ESC and can be removed.
(animate) Note 1 related to permits is part of contract specifications and can be removed from ESC sequence.
(animate) Note 19 text regarding roadway safety features is not related to ESC.

## Slide 111: Coordination with projects taking place concurrently in the same project area
ARE ANY STEPS REDUNDANT WITH GENERAL NOTES/WOULD WORK BETTER AS A GENERAL NOTE?
REVISE TO:
NOTIFY QAD PER ESN-01 NOTE 2. STAKEOUT LOD AND INSTALL TOCF.
Notes: We'll continue by discussing "general notes". The updates to the ESC general notes contain a lot of information that used to be included in the sequence and can now be removed.
(animate) For instance, Notes 2 & 3 are redundant with note 2 of the general notes which informs the contractor to notify QAD (was REC at the time of this project).
(animate) Step to Stakeout LOD required.
(animate) Define clear and grub as required for access and installation of perimeter controls.
(animate) Then install perimeter ESC Controls.
(animate) Original sequence defined each small work step that wasn't order dependent. Instead, simplify sequence by stating to "complete the work as shown on the plan".

## Slide 112: Coordination with projects taking place concurrently in the same project area
CAN ANY STEPS BE FURTHER REVISED FOR FLEXIBLE SEQUENCE?
CLEAR AND GRUB FOR ACCESS AND PERIMETER CONTROLS. INSTALL PERIMETER ESC CONTROLS.
INSTALL REMAINING ESC IN EACH WORK AREA PRIOR TO COMPLETING WORK.
COMPLETE THE WORK AS SHOWN IN THE CONTRACT DOCUMENTS.
APPLY PERMANENT STABILIZATION AND REMOVE ESC MEASURES ONCE PERMANENTLY STABILIZED PER QAD APPROVAL.
Information from steps 9, 16 and 17 can be repurposed into plan notes
REVISE TO:
NOTIFY QAD PER ESN-01 NOTE 2. STAKEOUT LOD AND INSTALL TOCF.
Notes: What information can be further simplified?
When we look at steps 5-18, there is some good information contained – LOD stakeout, ESC installation, ect. But there is a lot of unnecessary detail that can be pulled out as well. We recommend replacing these steps with the following:
(animate) Step to Stakeout LOD required.
(animate) Define clear and grub as required for access and installation of perimeter controls.
(animate) Then install perimeter ESC Controls.
(animate) Original sequence defined each small work step that wasn't order dependent. Instead, simplify sequence by stating to "complete the work as shown on the plan".

## Slide 113: Coordination with projects taking place concurrently in the same project area
ORIGINAL SEQUENCE
SEQUENCE OF CONSTRUCTION
NOTIFY QAD PER ESN-01 NOTE 2. STAKEOUT LOD AND INSTALL TOCF.
CLEAR AND GRUB FOR ACCESS AND PERIMETER EROSION AND SEDIMENT CONTROL INSTALLATION. INSTALL PERIMETER ESC CONTROLS IMMEDIATELY PER QAD APPROVAL.
INSTALL REMAINING ESC CONTROLS IN EACH WORK AREA PRIOR TO BEGINNING WORK.
PERFORM PROPOSED CONSTRUCTION AS SHOWN IN CONTRACT DOCUMENTS. THE EMERGENCY SPILLWAY WORK AREA WORK CANNOT BE COMPLETED DURING A FORECASTED SEVERE WEATHER EVENT.
PERMANENTLY STABILIZE ALL REMAINING DISTURBED AREAS. WITH THE APPROVAL OF QAD, REMOVE ESC MEASURES AND PERMANENTLY STABILIZE THOSE AREAS.
EROSION AND SEDIMENT CONTROL NOTES
ONLY NECESSARY CLEARING AND GRUBBING SHALL OCCUR FOR THE INSTALLATION OF THE EROSION AND SEDIMENT CONTROL (ESC) MEASURES, AND ALL ESC MEASURES AND DEVICES SHALL BE IN PLACE AND FUNCTIONING PROPERLY FOR EACH CONSTRUCTION WORK AREA PRIOR TO MASS CLEARING AND GRUBBING OF THE WORKING AREA AND COMMENCING ANY CONSTRUCTION ACTIVITIES.
MAINTAIN ALL SEDIMENT CONTROL PRACTICES ACCORDING TO THE MARYLAND 2011 STANDARDS UNTIL THE ENTIRE SITE IS STABILIZED.
ENSURE THE POND IS DRY PRIOR TO THE START OF ANY EXCAVATION. CONTRACTOR TO USE SUMP PIT AS REQUIRED TO CLEAN SEDIMENT LADEN WATER BEFORE DISCHARGING DOWNSTREAM.
CONTRACTOR SHALL USE GRAVITY FLOW TO DIVERT WATER FROM ALL INFLOW DITCHES AROUND THE EXISTING POND USING CLEAR WATER DIVERSION PIPES.
REVISED FLEXIBLE SEQUENCE
Notes: By making these edits, we are left with a final product that is similar to our "stock sequence", as well as some general notes and plan callouts which give the contractor guidance on how to perform Constuction activities.

## Slide 114: Example Project – BMP Retrofit
Notes: The flexible sequence of construction approach may require additional labels on the plan view for clarity. Consider the following revisions to the plan view for the flexile sequence of construction approach:
Adding flow arrows to the clear water diversion pipes
Revise diversion fence to have positive drainage to outlet (and adjusted LOD accordingly)
Revise from silt fence downstream of emergency spillway to sandbag diversion/filter bag since there is concentrated flow at this location
Revise label to specify the proposed control structure replacement

## Slide 115: Questions & Answers