## Directions
Directions for Using the RTP Construction Project Schedule Template
This schedule template is designed for Recreational Trails Program (RTP) Construction Projects. Additional guidance for each task is organized by project phase on the Program, Design, and Construction tabs.
How to Complete the Schedule
Enter the Month and Year the Sponsor expects each task to be completed.
Use the Notes column to explain any factors that could affect the timeline (Seasonal constraints, County specific requirements, etc.).
Customize the schedule to reflect the specific scope and circumstances of the proposed project.
Schedule Review Criteria
The most competitive applications include a realistic and comprehensive schedule that accounts for all phases of work and considers project-specific challenges.
Important Reminders
This schedule will serve as the baseline for the project after award, but all dates are subject to change as the project progresses.
For more information please refer to the Recreational Trails Program Manual.

## Schedule Template
RTP Construction Schedule Template
Phase | Task | Schedule (Month, Year) | Notes
Application | Submit Application | April 2026
Program | Project Awarded | October 2026
Program | Kickoff Meeting
Program | Begin Drafting MOU
Program | Sponsor Signs MOU
Program | SHA Signs and Executes MOU
Program | National Environmental Policy Act (NEPA) Approval
Program | Right of Way (ROW) Certification
Program | Receive Other Approvals as Needed
Program | Confirm Accuracy of Project Scope and Cost Estimate
Program | Federal Authorization
Design | 30% Design (as applicable)
Design | SHA 30% Design Review (as applicable)
Design | 60% Design (as applicable)
Design | SHA 60% Design Review (as applicable)
Design | 90% Design (as applicable)
Design | SHA 90% Design Review (as applicable)
Design | 100% Design
Design | SHA Design Review
Construction | Procurement Package
Construction | Request DBE goal
Construction | SHA Review and Approval
Construction | Notice to Advertise (NTA)
Construction | Advertise for Construction
Construction | Concurrence in Award (CIA)
Construction | Notice to Proceed (NTP)
Construction | Active Construction and Submitting Reimbursement Requests
Construction | Final Inspection
Construction | Project Closeout

## Program
Program Phase Schedule Template Explanation
Task | Responsibility | Explanation | Estimated Time Range | Notes
Project Awarded | SHA | The Notice of Award serves as the starting date from which subsequent milestones are measured. The Notice of Award is sent to the Sponsor in the Fall. | Fall
Kickoff Meeting | SHA | Scheduled within one month of the Notice of Award. The Sponsor meets with the assigned Program Liaison to review project scope, Federal/State requirements, and next steps. | Within 1 month after the Project Award
Begin Drafting MOU | SHA | The MOU drafting and review timeline varies depending on complexity of the project. SHA prepares the draft MOU and the Sponsor reviews and comments. | 2 weeks after the kickoff meeting
Sponsor Signs MOU | Sponsor | SHA provides electronic copies of the MOU for signature. The Sponsor returns a signed copy to SHA. | 2 weeks
SHA Signs and Executes MOU | SHA | SHA circulates the MOU to various signatories and returns the executed MOU to the Sponsor | 2 to 3 weeks after receiving the sponsor-signed MOU.
National Environmental Policy Act (NEPA) Approval | Sponsor | The SHA NEPA Liaison will work with the Sponsor to navigate the NEPA Approval process. The timeline varies by project scope and will not be fully known until NEPA is initiated. To initiate NEPA, the Sponsor must have: - Project location map showing the site and limits of disturbance. - Scope of work - Area of Potential Effect (APE), including direct physical impacts and indirect impacts such as noise or visual intrusions. - List of potentially significant historic structures or archaeological resources. - List of effects on historic resources eligible or listed on the National Register of Historic Places. These details allow SHA and FHWA to determine the level of NEPA documentation required (Categorical Exclusion, Programmatic CE, Environmental Assessment) and begin coordination with resource agencies. | Consider if the project has any of the elements listed to the right. If the project does not have any of those considerations, write 3 months into the schedule. If the project has many elements listed to the right, write 4 to 5 months in the schedule. | Does the project scope contain or impact any of the following? The presence or impact of these items may add time to the NEPA Approval process. -Sensitive resources such as wetlands, waterways, floodplains, rare/threatened/endangered species, or critical areas (e.g., Chesapeake Bay Critical Area). - Historic properties requiring Maryland Historical Trust (MHT) review and Section 106 compliance. - Section 4(f) resources (parks, recreation areas, wildlife refuges), specifically negative impacts or impeded access to Section 4(f) resources that may require avoidance analysis or mitigation. - Permitting needs (e.g., U.S. Army Corps of Engineers, Maryland Department of Environment). - Public involvement requirements if the project has significant community impacts. ***Agency response times, which typically take 30–60 days per coordination cycle, can be longer if additional studies or mitigation plans are needed.
Right of Way (ROW) Certification | Sponsor | The SHA Local Public Agency (LPA) ROW Coordinators will work with the Sponsor to navigate the ROW process. If the Sponsor owns all of the land, estimate two weeks to complete the ROW Certification Letter. If the Sponsor does not own the land, estimate six to nine months minimum to coordinate with the landowner(s) and the SHA Office of Real Estate. | Varies
Receive Other Approvals as Needed | Sponsor | The timing varies depending on the necessary permits and reviews. (e.g. location specific permits) | The applicant should identify potential approvals needed in the notes section and estimate the time range.
Confirm Accuracy of Project Scope and Cost Estimate | Sponsor | The Sponsor will confirm the accuracy of the scope and cost estimate before the procurement request. Any changes in the project scope and/or ROW will require a NEPA reevaluation and/or ROW re-certification. | As needed
Federal Authorization | SHA | SHA is required to request authorization from FHWA to obligate funds towards a specific project. The Construction procurement cannot begin before the project receives federal authorization. | 1 to 3 months
|  | Total time for the Program phase: | 7 - 18 months

## Design
Design Schedule Template Explanation
RTP Construction Schedules should clearly note the current stage of design plans being submitted with the application. Additionally, note if the remaining design work will be completed in-house, an existing consultant, or a constultant to be procured. A NEPA Document for preliminary design will need to be completed prior to any design activities undertaken as part of the proposed project.
Task | Responsibility | Explanation | Estimated Time Range
30% Design (as applicable) | Sponsor | If the project began with 30% design already completed, this step is skipped. Sponsor will develop design plans up to 30% of full design. Timeline may vary and depends on complexity of project scope. | 4 to 6 weeks, or longer
SHA 30% Design Review (as applicable) | SHA | If the project began with 30% design already completed, this step is skipped. Design plans will be shared with SHA for review by various offices, and comments will be returned to the Sponsor to address with the next design submittal. | 4 to 6 weeks
60% Design (as applicable) | Sponsor | If the project began with 60% design already completed, this step is skipped. The Sponsor further deveops the plans to 60% design. They also respond to SHA's previous review feedback in a point-by-point response letter. Timeline may vary and depends on complexity of project scope. | 1 month
SHA 60% Design Review (as applicable) | SHA | If the project began with 60% design already completed, this step is skipped. Design plans and the point-by-point response letter will be shared with SHA for review by various offices, and comments will be returned to the Sponsor to address with the next design submittal. | 4 to 6 weeks
90% Design (as applicable) | Sponsor | If the project began with 90% design already completed, this step is skipped. The Sponsor develops the plans to 90% design. Timeline may vary and depends on complexity of project scope. | 1 month
SHA 90% Design Review (as applicable) | SHA | If the project began with 90% design already completed, this step is skipped. Design plans will be shared with SHA for review by various offices, and comments will be returned to the Sponsor to address. | 1 month
100% Design | Sponsor | The Sponsor develops the 100% design, cost estimates, and a point-by point response letter (if applicable). Timeline may vary and depend on complexity of project scope. | 1 month
SHA Design Review | SHA | SHA reviews the 100% design plan submission and comments will be returned to the Sponsor to address and resubmit. | 4 to 6 weeks
|  | Total time for the Design phase: | 3 - 10 months

## Construction
Construction Phase Schedule Template Explanation
Task | Responsibility | Explanation | Estimated Time Range
Procurement Package | Sponsor | The Sponsor should identify the type of procurement that fits the project's cost estimate. Record the procurement type in the notes section. Small procurement includes three cost categories, Category I: <$5,000 Category II: $5,000 to $14,999 Category III: $15,000 to $50,000 Projects over $50,000 are required to complete Competitive Sealed Bidding (CSB). Sponsors interested in utilizing the Conservation Corps for construction should write this in the Schedule Template Notes column. | Category I or II: 2 weeks to develop the procurement package. Category III or CSB: 1 month to develop the procurement package.
Request DBE goal | SHA | If the project is over $50,000, determine the Disadvantaged Business Enterprise (DBE) requirements by submitting the RFP materials to the SHA Procurement Review Group who will identify a DBE goal. On October 3, 2025, the US Secretary of Transportation issued an Internal Final Rule that makes significant changes to the DBE program. At this time, all DBE goals are set at 0% while business are re-certified according to the Rule. However, once re-certification is complete, DBE goals will once again be identified for TAP projects. For now, no time needs to be added for 0% DBE goals. Once DBE goals are reestablished, 1-2 months should be added to the project schedule | 0 weeks
SHA Review and Approval | SHA | Submit procurement package to SHA for review and approval. The timeline depends on the number of comments and rounds of revision. | Category I, II: 2 weeks Category III or CSB: 4 to 6 weeks
Notice to Advertise (NTA) | SHA | The NTA is issued when the Procurement Package completes all Federal and State requirements. | 1 week
Advertise for Construction | Sponsor | Category I: Sponsor solicits at least two vendors. Offers can be oral or in writing; however, documentation is required. Category II: Sponsor solicits at least three vendors. Solicitations must be in writing. Category III: Sponsor posts solicitation on eMaryland Marketplace Advantage (eMMA) for a minimum of three working days before the bids are due and opened. CSB: Sponsor posts solicitations on eMMA for a minimum of 28 days before bids are due and opened. | Category I or II: 2 weeks Category III or CSB: 1 month
Concurrence in Award (CIA) | Sponsor | The Sponsor selects a vendor based on the lowest responsive and responsible bid. The Sponsor submits a request to SHA for CIA. | 1 week
Notice to Proceed (NTP) | SHA | After bid evaluation and SHA approval, the Sponsor receives NTP from SHA. | 1 week
Active Construction and Submitting Reimbursement Requests | Sponsor | Active construction timeline varies by project scope. SHA completes inspections of the work throughout the construction phase. Sponsor submits reimbursement requests on a monthly or quarterly basis throughout the construction completion. | Varies
Final Inspection | SHA | SHA conducts a site inspection to verify that the project was completed according to approved plans and specifications. Required prior to processing the final invoice and project closeout. | 1 to 2 weeks
Project Closeout | SHA and Sponsor | The Sponsor should submit invoices regularly. The invoices should be processed within 2 months of project completion. | Within 2 months of project completion
|  | Total time for the Construction phase: | Varies depending on the active construction duration
End of worksheet