## Directions
Directions for Using the RTP Trail Maintenance Project Schedule Template
This schedule template is designed for Recreational Trails Program (RTP) Trail Maintenance Projects. Additional guidance for each task is organized by project phase on the Program and Trail Maintenance tabs.
How to Complete the Schedule
Enter the Month and Year the Project Sponsor expects each task to be completed.
Use the Notes column to explain any factors that could affect the timeline (Seasonal constraints, County specific requirements, etc.).
Customize the schedule to reflect the specific scope and circumstances of the proposed project.
Schedule Review Criteria
The most competitive applications include a realistic and comprehensive schedule that accounts for all phases of work and considers project-specific challenges.
Important Reminders
This schedule will serve as the baseline for the project after award. All dates are subject to change as the project progresses.
For more information please refer to the Recreational Trails Program Manual.

## Schedule Template
RTP Trail Maintenance Schedule Template
Phase | Task | Schedule (Month, Year) | Notes
Application | Submit Application | April 2026
Program | Project Awarded | October 2026
Program | Kickoff Meeting
Program | Drafting MOU
Program | Sponsor Signs MOU
Program | SHA Signs and Executes MOU
Program | National Environmental Policy Act (NEPA) Approval
Program | Right of Way (ROW) Certification
Program | Receive Other Approvals as Needed
Program | Confirm Accuracy of Project Scope and Cost Estimate
Program | Federal Authorization
Trail Maintenance | Trail Maintenance Schedule
Trail Maintenance | Trail Maintenance Schedule Review and Approval
Trail Maintenance | Request DBE goal
Trail Maintenance | Procurement Package
Trail Maintenance | SHA Review and Approval
Trail Maintenance | Notice to Advertise (NTA)
Trail Maintenance | Advertise for Maintenance
Trail Maintenance | Concurrence in Award (CIA)
Trail Maintenance | Notice to Proceed (NTP)
Trail Maintenance | Active Trail Maintenance and Submitting Reimbursement Requests
Trail Maintenance | Submitting Reimbursement Requests
Trail Maintenance | Final Inspection
Trail Maintenance | Project Closeout

## Program
Program Phase Schedule Template Explanation
Task | Responsibility | Explanation | Estimated Time Range | Notes
Project Awarded | SHA | The Notice of Award serves as the starting date from which subsequent milestones are measured. The Notice of Award is sent to the Sponsor in the Fall. | Fall
Kickoff Meeting | SHA | Scheduled within one month of the Notice of Award. The Sponsor meets with the assigned SHA Program Liaison to review project scope, Federal/State requirements, and next steps. | Within 1 month after the Project Award
Drafting MOU | SHA | SHA prepares draft MOU and sponsor reviews and comments. | 1 week after the kickoff meeting
Sponsor Signs MOU | Sponsor | SHA provides electronic copies of the MOU for signature. The Sponsor returns a signed copy to SHA. | 2-4 weeks
SHA Signs and Executes MOU | SHA | SHA circulates the MOU to various signatories and returns the executed MOU to the Sponsor | 2-3 weeks after receiving the sponsor-signed MOU
National Environmental Policy Act (NEPA) Approval | Sponsor | The SHA NEPA Liaison will work with the Sponsor to navigate the NEPA Approval process. The timeline varies by project scope and will not be fully known until NEPA is initiated. To initiate NEPA, the Sponsor must have: - Project location map showing the site and limits of disturbance. - Scope of work - Area of Potential Effect (APE), including direct physical impacts and indirect impacts such as noise or visual intrusions. - List of potentially significant historic structures or archaeological resources. - List of effects on historic resources eligible or listed on the National Register of Historic Places. These details allow SHA and FHWA to determine the level of NEPA documentation required (Categorical Exclusion, Programmatic CE, Environmental Assessment) and begin coordination with resource agencies. | Consider if the project has any of the elements listed in the Notes column. If the project does not have any of those considerations, write 3 months into the schedule. If the project has many elements listed in the Notes column, write 4 to 5 months in the schedule. | Does the project scope contain or impact any of the following? The presence or impact of these items may add time to the NEPA Approval process. -Sensitive resources such as wetlands, waterways, floodplains, rare/threatened/endangered species, or critical areas (e.g., Chesapeake Bay Critical Area). - Historic properties requiring Maryland Historical Trust (MHT) review and Section 106 compliance. - Section 4(f) resources (parks, recreation areas, wildlife refuges), specifically negative impacts or impeded access to Section 4(f) resources that may require avoidance analysis or mitigation. - Permitting needs (e.g., U.S. Army Corps of Engineers, Maryland Department of Environment). - Public involvement requirements if the project has significant community impacts. ***Agency response times, which typically take 30–60 days per coordination cycle, can be longer if additional studies or mitigation plans are needed.
Right of Way (ROW) Certification | Sponsor | The SHA Local Public Agency (LPA) ROW Coordinators will work with the Project Sponsor to navigate the ROW process. If the Project Sponsor owns all of the land, estimate two weeks to complete the ROW Certification Letter. If the Project Sponsor does not own the land, estimate six to nine months minimum to coordinate with the landowner(s) and the SHA Office of Real Estate. | Varies
Receive Other Approvals as Needed | Sponsor | The timing varies depending on the necessary permits and reviews. (e.g. location specific permits) | The applicant should identify potential approvals needed in the notes section and estimate the time range.
Confirm Accuracy of Project Scope and Cost Estimate | Sponsor | The Project Sponsor will confirm the accuracy of the scope and cost estimate before the procurement request. Any changes in the project scope and/or ROW will require a NEPA reevaluation and/or ROW re-certification. | As needed
Federal Authorization | SHA | SHA is required to request authorization from FHWA to obligate funds towards a specific project. Trail Maintenance work cannot begin before the project receives federal authorization. | 1 to 3 months
|  | Total time for the Program phase: | 7 - 18 months

## Trail Maintenance
Trail Maintenance Phase Schedule Template Explanation
Task | Responsibility | Explanation | Estimated Time Range
Trail Maintenance Schedule | Sponsor | The Project Sponsor will develop a schedule that plans the location and dates for the trail maintenance. Projects that include a completed trail maintenance schedule at the time of application will be viewed more favorably. If the trail maintenance schedule was provided at the time of application, then exclude this step in the template. | 2 to 4 weeks
Trail Maintenance Schedule Review and Approval | SHA | Submit the Trail Maintenance Plan for review and final approval. The timeline depends on the number of comments and rounds of revision. | 2 weeks
Request DBE goal | SHA | If the RTP project is over $50,000, determine the Disadvantaged Business Enterprise (DBE) requirements by submitting the RFP materials to the SHA Procurement Review Group who will identify a DBE goal. On October 3, 2025, the US Secretary of Transportation issued an Internal Final Rule that makes significant changes to the DBE program. At this time, all DBE goals are set at 0% while business are re-certified according to the Rule. However, once re-certification is complete, DBE goals will once again be identified for TAP projects. For now, no time needs to be added for 0% DBE goals. Once DBE goals are reestablished, 1-2 months should be added to the project schedule | 0 weeks
Procurement Package | Sponsor | The Project Sponsor should identify the type of procurement that fits the project's cost estimate. Record the procurement type in the notes section. Small procurement includes three cost categories, Category I: <$5,000 Category II: $5,000 to $14,999 Category III: $15,000 to $50,000 Projects over $50,000 are required to complete Competitive Sealed Bidding (CSB). Project Sponsors interested in utilizing the Conservation Corps for trail maintenance should write this in the Schedule Template Notes column. | Category I or II: 2 weeks to develop the procurement package. Category III or CSB: 1 month to develop the procurement package.
SHA Review and Approval | SHA | Submit procurement package to SHA for review and approval. The timeline depends on the number of comments and rounds of revision. | Category I, II: 2 weeks Category III or CSB: 4 to 6 weeks
Notice to Advertise (NTA) | SHA | The NTA is issued when the Procurement Package completes all Federal and State requirements. | 1 week
Advertise for Maintenance | Sponsor | Category I: Sponsor solicits at least two vendors. Offers can be oral or in writing; however, documentation is required. Category II: Sponsor solicits at least three vendors. Solicitations must be in writing. Category III: Sponsor posts solicitation on eMaryland Marketplace Advantage (eMMA) for a minimum of three working days before the bids are due and opened. CSB: Sponsor posts solicitations on eMMA for a minimum of 28 days before bids are due and opened. | Category I or II: 2 weeks Category III or CSB: 1 month
Concurrence in Award (CIA) | Sponsor | The Project Sponsor selects a vendor based on the lowest responsive and responsible bid. The Project Sponsor submits a request to SHA for CIA. | 1 week
Notice to Proceed (NTP) | SHA | After bid evaluation and SHA approval, the Project Sponsor receives NTP from SHA. | 1 week
Active Trail Maintenance and Submitting Reimbursement Requests | Sponsor | Varies by project scope. SHA completes inspections of the work through out the maintenance phase. | Varies
Submitting Reimbursement Requests | Sponsor | On a monthly or quarterly basis throughout the maintenance completion. | n/a
Final Inspection | SHA | SHA conducts a site inspection to verify that the project was completed according to approved plans and specifications. Required prior to processing the final invoice and project closeout. | 1 to 2 weeks
Project Closeout | SHA and Sponsor | The Project Sponsor should submit invoices regularly. The invoices should be processed within 2 months of project completion. | Within 2 months of project completion
|  | Total time for the Trail Maintenance phase: | 3 - 6 months, or longer depending on the active trail maintenance duration
End of worksheet