## Directions
Directions for Using the TA Construction Project Schedule Template
This schedule template is designed for Transportation Alternatives (TA) Construction Projects. Additional guidance for each task is organized by project phase on the Program, Design, Procurement, Construction, and Reimbursement & Closeout tabs.
How to Complete the Schedule
Enter the Month and Year the Project Sponsor expects each task to be completed.
Use the Notes column to explain any factors that could affect the timeline (Seasonal constraints, County specific requirements, etc.).
Customize the schedule to reflect the specific scope and circumstances of the proposed project.
Schedule Review Criteria
The most competitive applications include a realistic and comprehensive schedule that accounts for all phases of work and considers project-specific challenges.
Important Reminders
This schedule will serve as the baseline for the project after award. All dates are subject to change as the project progresses.
For more information please refer to the Transportation Alternatives Program Manual.

## TA Construction Schedule
Transportation Alternatives Construction Schedule Template
Phase | Task | Schedule (Month, Year) | Notes
Application | Submit Application | April 2026
Program | Project Awarded | October 2026
Program | Kickoff Meeting
Program | Drafting MOU
Program | Sponsor Signs MOU
Program | SHA Signs and Executes MOU
Program | National Environmental Policy Act (NEPA) Approval
Program | Right of Way (ROW) Certification
Program | Receive Other Approvals as Needed
Program | Confirm Accuracy of Project Scope and Cost Estimate
Design | SHA 30% Design Review (if applicable)
Design | Second National Environmental Policy Act (NEPA) Approval
Design | 60% Design Development and Submission
Design | SHA 60% Design Review
Design | Submit Final Review Package (90% Design)
Design | SHA 90% Design Review
Design | Request DBE goal
Design | Submit PS&E Package (100% Design)
Design | SHA PS&E Package Review
Procurement | Federal Authorization Request
Procurement | Approval to Advertise Construction Bid Documents
Procurement | Open Bid Proposals and Select Contractor
Procurement | Request SHA's Concurrence In Award (CIA)
Procurement | Review and Provide Written CIA
Procurement | Provide Notice to Proceed (NTP)
Construction | Pre-Construction Meeting
Construction | Materials Testing and Certification
Construction | Active Construction
Construction | Punchlist Walk Thru/Inspection
Construction | Final Material Certification
Construction | Final Acceptance
Reimbursement & Closeout | Submit Final Reimbursement Requests
Reimbursement & Closeout | Audit
Reimbursement & Closeout | Releasing Retainage
Reimbursement & Closeout | Landscaping and Historic Structure Requirements (As needed)
Reimbursement & Closeout | Project Closeout Letter

## Program
Program Schedule Template Explanation
Task | Responsibility | Explanation | Estimated Time Range
Project Awarded | SHA | The Notice of Award serves as the starting date from which subsequent milestones are measured. The Notice of Award is sent to the Sponsor in the Fall. | Fall
Kickoff Meeting | SHA | Scheduled within one month of the Notice of Award. The Sponsor meets with the assigned SHA Program Liaison to review project scope, Federal/State requirements, and next steps. | Within 1 month after the Project Award
Drafting MOU | SHA | SHA prepares draft MOU and sponsor reviews and comments. | 1 week after the kickoff meeting
Sponsor Signs MOU | Sponsor | SHA provides electronic copies of the MOU for signature. The Sponsor returns a signed copy to SHA. | 2-4 weeks
SHA Signs and Executes MOU | SHA | SHA circulates the MOU to various signatories and returns the executed MOU to the Sponsor | 2-3 weeks after receiving the sponsor-signed MOU
National Environmental Policy Act (NEPA) Approval | Sponsor | The Sponsor will work with the SHA NEPA Liaison to obtain a Minor Programmatic Categorical Exclusion (PCE) for the design phase. A second NEPA approval for construction will be required during desgin and included in the PS&E Package. | 1 week
Right of Way (ROW) Certification | Sponsor | The SHA Local Public Agency (LPA) ROW Coordinators will work with the Sponsor to navigate the ROW process. If the Sponsor owns all of the land, estimate two weeks to complete the ROW Certification Letter. If the Sponsor does not own the land, estimate six to nine months minimum to coordinate with the landowner(s) and the SHA Office of Real Estate. | Varies
Receive Other Approvals as Needed | Sponsor | Concurrent with NEPA. The timing varies depending on the necessary permits and reviews (e.g., utility coordination, historic preservation). | The applicant should identify potential approvals needed in the notes section and estimate the time range.
Confirm Accuracy of Project Scope and Cost Estimate | Sponsor | The Sponsor will confirm the accuracy of the scope and cost estimate before the procurement request. Any changes in the project scope and/or ROW will require a NEPA reevaluation and/or ROW re-certification. | As needed
|  | Total time for the Program Phase (once Award Letter is Received): | 3-6 months

## Design
Design Schedule Template Explanation
Task | Responsibility | Explanation | Estimated Time Range | Notes
SHA 30% Design Review (if applicable) | SHA | TA construction projects should apply with completed 30% Design plans. Unless previously approved, these design plans should be submitted for SHA's review and approval. Items that must be submitted with a 30% review are Design Plans and Quantity/Cost Estimate. Various SHA offices will review the design plans, and comments will be returned to the Sponsor to address with the next design submission. | 4 to 6 weeks
Second National Environmental Policy Act (NEPA) Approval | Sponsor | The SHA NEPA Liaison will work with the Sponsor to navigate the NEPA Approval process. The timeline varies by project scope and will not be fully known until NEPA is initiated. To initiate NEPA, the Sponsor must have: - Project location map showing the site and limits of disturbance. - Scope of work - Area of Potential Effect (APE), including direct physical impacts and indirect impacts such as noise or visual intrusions. - List of potentially significant historic structures or archaeological resources. - List of effects on historic resources eligible or listed on the National Register of Historic Places. These details allow SHA and FHWA to determine the level of NEPA documentation required (Categorical Exclusion, Programmatic CE, Environmental Assessment) and begin coordination with resource agencies. | Consider if the project has any of the elements listed in the Notes column. If the project does not have any of those considerations, write 3 months into the schedule. If the project has many elements listed in the Notes column, write 4 to 5 months in the schedule. | Does the project scope contain or impact any of the following? The presence or impact of these items may add time to the NEPA Approval process. -Sensitive resources such as wetlands, waterways, floodplains, rare/threatened/endangered species, or critical areas (e.g., Chesapeake Bay Critical Area). - Historic properties requiring Maryland Historical Trust (MHT) review and Section 106 compliance. - Section 4(f) resources (parks, recreation areas, wildlife refuges), specifically negative impacts or impeded access to Section 4(f) resources that may require avoidance analysis or mitigation. - Permitting needs (e.g., U.S. Army Corps of Engineers, Maryland Department of Environment). - Public involvement requirements if the project has significant community impacts. ***Agency response times, which typically take 30–60 days per coordination cycle, can be longer if additional studies or mitigation plans are needed.
60% Design Development and Submission | Sponsor/Consultant | The Sponsor/Consultant develops the plans to 60% design. Timeline may vary and depends on complexity of project scope. Items that must be submitted with a 60% review are a Point-by-Point letter demonstrating how previous review comments have been addressed, Design Plans, Quantity/Cost Estimate along with additional item that may have been requested (report, permits, critical area, scour analysis, etc.). | 1 month
SHA 60% Design Review | Sponsor | Various SHA offices will complete the design review and comments will be returned to the Sponsor to address with the next design submission. | 4 to 6 weeks
Submit Final Review Package (90% Design) | Sponsor/Consultant | The Sponsor/Consultant develops the plans to 90% design. Timeline may vary and depends on complexity of project scope. Items that must be submitted with a 90% review are a Point-by-Point letter demonstrating how previous review comments have been addressed Design Plans, Quantity/Cost Estimate, Invitation for Bid (IFB) along with additional item that may have been requested (report, permits, critical area, scour analysis, etc.) | 1 month
SHA 90% Design Review | Sponsor | Various SHA offices will review the design plans, and comments will be returned to the Sponsor to address with the next design submission. | 4 to 6 weeks
Request DBE goal | SHA | If the project is over $50,000, determine the Disadvantaged Business Enterprise (DBE) requirements by submitting the RFP materials to the SHA Procurement Review Group who will identify a DBE goal. On October 3, 2025, the US Secretary of Transportation issued an Internal Final Rule that makes significant changes to the DBE program. At this time, all DBE goals are set at 0% while business are re-certified according to the Rule. However, once re-certification is complete, DBE goals will once again be identified for TAP projects. For now, no time needs to be added for 0% DBE goals. Once DBE goals are reestablished, 1-2 months should be added to the project schedule | 0 weeks
Submit PS&E Package (100% Design) | Sponsor | The consultant develops the final PS&E package. Timeline may vary and depends on complexity of project scope. Items that must be submitted with a 100% review are a Point-by-Point letter demonstrating how previous review comments have been addressed Design Plans, Quantity/Cost Estimate, Invitation for Bid (IFB), full PS&E Checklist Items along with additional item that may have been requested (report, permits, critical area, scour analysis, etc.) | 1 month
SHA PS&E Package Review | SHA | SHA reviews the 100% design plan submission and comments will be returned to the Sponsor to address and resubmit the package. | 4 to 6 weeks
|  | Total time for the Design Phase: | 10-14 months

## Procurement
Procurement Schedule Template Explanation
Task | Responsibility | Explanation | Estimated Time Range
Federal Authorization Request | SHA | SHA is required to request authorization from Federal Highway Administration (FHWA) to obligate awarded funds towards a specific project. In order to request and receive federal authorization for construction, SHA must provide the final, approved PS&E package. Construction procurement cannot begin before receiving federal authorization. Any work done before federal authorization is received is not eligible for reimbursement. Once SHA receives federal authorization for the project, an Approval to Advertise letter will be sent for the Sponsor to begin procurement activities. | 1-3 months
Approval to Advertise Construction Bid Documents | Sponsor | All advertisements must be listed in eMaryland Marketplace Advantage (eMMA) for a minimum of 21 continuous days with the bid opening held on the 22nd day. | 3 weeks
Open Bid Proposals and Select Contractor | Sponsor | Sponsor will review proposals and select the lowest responsive and responsible bidder for award. If the lowest bidder is accepted the Sponsor should seek Concurrence In Award (CIA). If all bids are rejected, the project must be re-advertised (with SHA's approval). | 2 weeks
Request SHA's Concurrence In Award (CIA) | Sponsor | The Sponsor requests SHA's Concurrence In Award (CIA) before the contract is awarded and Notice to Proceed (NTP) is issued to the contractor. A CIA package should be sent to the SHA for review. | 2 weeks
Review and Provide Written CIA | SHA | SHA will provide a written CIA letter after reviewing the bid proposals. The CIA is reviewed by the SHA Office of Construction. | 6 weeks
Provide Notice to Proceed (NTP) | SHA | After providing written CIA, SHA will issue the NTP to the Sponsor and contractor. | 1-2 weeks
|  | Total time for the Procurement Phase: | 4-7 months

## Construction
Construction Schedule Template Explanation
Task | Responsibility | Explanation | Estimated Time Range
Pre-Construction Meeting | SHA and Sponsor | A pre-construction meeting is a required step to ensure all relevant parties are up-to-date and aware of the next steps in the construction process. | 2-3 weeks after Concurrence In Award (CIA) Letter is received
Materials Testing and Certification | Sponsor | All source submissions must be submitted and receive approval PRIOR to use. Project sponsors must submit a list of materials for approval 30 days in advance of the construction schedule. Sponsor should follow the testing processes outlined in the source approval provided by SHA Office of Materials Technology (OMT) and SHA Materials Management System (MMS), as well as the procedures outlined in the State Quality Assurance Manual. Some materials require quality assurance tasks to be performed before the material is delivered to the project site. Other materials may require action once the material arrives on site (such as material sampling, inspection, and verification). This direction will be provided on the Source Submission Approval under Quality Assurance. | Minimum 1 month in advance of construction
Active Construction | Sponsor | Active construction timeline varies by project scope. Sponsor submits reimbursement requests on a monthly or quarterly basis throughout the construction completion. Once monthly or quarterly reimbursements are submitted, they must consistently be submitted in this manner until the end of the project. Sponsor must submit monthly reports for OMT to review and ensure the material assurance processes are being followed. Audits can occur periodically through out the construction process. | The active construction timeline varies depending on the project scope. This timeline includes: - Monthly Material Clearance Submissions - Monthly/Quarterly Reimbursement Requests - First Reimbursement should be request 90 days after NTP
Punchlist Walk Thru/Inspection | SHA and Sponsor | The Sponsor will coordinate with the SHA District Office to schedule a Punchlist Walk Thru/ Inspection and invite the local jurisdiction or others conducting a inspection. If all work completed is satisfactory, the project can be accepted for partial acceptance. Final Acceptance for Maintenance is granted if there are no remaining work items at the time of the walk thru. Additionally, the project goes through an audit to review records kept throughout the process before the retainage can be released. | 1 week
Final Material Certification | SHA | All materials must be cleared as discussed in Materials Testing and Certification. If materials have been reported regularly, final material certification will be easier. The Sponsor will complete the 30 Day Material Clearance at the completion of the project. Final material certification will be issued by SHA OMT with a Material Clearance letter. | 1 month at the completion of the construction project
Final Acceptance | SHA | The Final Acceptance for Maintenance is granted if there are no remaining work items. The final inspection will ensure the project was constructed according to the MOU and the final advertised plan, and the SHA ADA and Bicycle Compliance team will verify that the project was built to be ADA compliant. Final Inspection compliance will be confirmed via letter from the SHA District. | 1 week
|  | Total time for the Construction Phase: | Varies depending on the active construction duration

## Reimbursement and Closeout
Reimbursement and Closeout Schedule Template Explanation
Task | Responsibility | Explanation | Estimated Time Range
Submit Final Reimbursement Requests | Sponsor | Occurs after all construction deliverables are complete and SHA concurrence is received. Allow up to 30 days for SHA to process payment once the request is approved. | 1 month
Audit | SHA District Office | The SHA District Office will need to validate that all the work has been completed per plans and complete an audit to review the records kept through the process before the retainage can be released. The District Sketchbook Reviewer conducts an audit to check for estimates, IDRs, pay quantities and other applicable close out records. If there are any discrepancies, they must be addressed prior to close out. The outcome of the audit will be a District Engineer Certification, signifying that the retainage can be released and the project can close out. | 4-6 weeks
Releasing Retainage | SHA | For construction projects, a retainage will be withheld from the contractor’s monthly invoice. The Sponsor will request concurrence from SHA that the Punchlist Walk Thru/Inspection, Audit, and Final Materials Clearance are complete. When SHA approves the request for concurrence, then the Sponsor will submit an invoice for payment of retainage. | 1 month
Landscaping and Historic Structure Requirements (As needed) | SHA and Sponsor | Landscaping – The project sponsor must wait to ensure that any landscaping work has been maintained under the 1-year warranty. SHA will hold project sponsor’s retainage until the warranty deadline has been met. Historic Structure – The project sponsor may be required to further coordinate with the Maryland Historic Trust for projects involving renovations or archaeology. | Varies
Project Closeout Letter | SHA | When the final milestones have been met and final reimbursement has been processed, the project sponsor will receive a closeout letter as a formal acknowledgment that the project has successfully been closed. | 1-2 weeks
|  | Total time for the Reimbursement and Closeout Phase: | 3-4 months
End of worksheet.