## Directions
Directions for Using the TA Design Project Schedule Template
This schedule template is designed for Transportation Alternatives (TA) Design Projects. Additional guidance for each task is organized by project phase on the Program, Procurement, Design, and Closeout tabs.
How to Complete the Schedule
Enter the Month and Year the Sponsor expects each task to be completed.
Use the Notes column to explain any factors that could affect the timeline (Seasonal constraints, County specific requirements, etc.).
Customize the schedule to reflect the specific scope and circumstances of the proposed project.
Schedule Review Criteria
The most competitive applications include a realistic and comprehensive schedule that accounts for all phases of work and considers project-specific challenges.
Important Reminders
This schedule will serve as the baseline for the project after award. All dates are subject to change as the project progresses.
For more information please refer to the Transportation Alternatives Program Manual.

## TA Design Schedule
Transportation Alternatives Design Schedule Template
Phase | Task | Schedule (Month Year) | Notes
Application | Submit Application | April 2026
Program | Project Awarded | October 2026
Program | Kickoff Meeting
Program | Drafting MOU
Program | Sponsor Signs MOU
Program | SHA Signs and Executes MOU
Program | National Environmental Policy Act (NEPA) Approval
Program | Confirm Accuracy of Project Scope and Cost Estimate
Procurement | Complete Draft RFP
Procurement | Request DBE goal
Procurement | RFP Review and Revision
Procurement | Notice to Advertise (NTA)
Procurement | Advertise on eMMA
Procurement | Review Proposals and Select Consultant
Procurement | Approval to Request Price Proposal
Procurement | Cost Proposal Development and Review
Procurement | Negotiations with Consultant (if applicable)
Procurement | Request SHA's Concurrence in Award (CIA)
Procurement | Federal Authorization Request
Procurement | Notice to Proceed
Procurement | Execute Contract with Consultant
Design | Design Kick Off Meeting
Design | Reimbursement Requests
Design | 30% Design Development and Submission
Design | SHA Design Review
Design | Second National Environmental Policy Act (NEPA) Approval (if applicable)
Design | Federal Authorization Modification (if applicable)
Design | Receive Other Approvals as Needed
Design | 60% Design Development and Submission
Design | SHA Design Review
Design | 90% Design
Design | SHA Design Review
Design | 100% Design
Design | SHA Design Review
Design | Address Comments (as needed)
Closeout | Submit Final Reimbursement Requests
Closeout | Project Closeout

## Program
Program Schedule Template Explanation
Task | Responsibility | Explanation | Estimated Time Range | Notes
Project Awarded | SHA | The Notice of Award serves as the starting date from which subsequent milestones are measured. The Notice of Award is sent to the Sponsor in the Fall. | Fall
Kickoff Meeting | SHA | Scheduled within one month of the Notice of Award. The Sponsor meets with the assigned SHA Program Liaison to review project scope, federal/state requirements, and next steps. | Within 1 month after the Project Award
Drafting MOU | SHA | SHA prepares draft MOU and sponsor reviews and comments. | 1 week after the kickoff meeting
Sponsor Signs MOU | Sponsor | SHA provides electronic copies of the MOU for signature. The Sponsor returns a signed copy to SHA. | 2-4 weeks
SHA Signs and Executes MOU | SHA | SHA circulates the MOU to various signatories and returns the executed MOU to the Sponsor | 2-3 weeks after receiving the sponsor-signed MOU
National Environmental Policy Act (NEPA) Approval | Sponsor | If the project is at 0% Design, SHA will provide a Programmatic Categorical Exclusion (PCE) Appendix A, which takes up to 1 week. If the project is at 30% design (or higher), the following process below must be followed at this stage. The SHA NEPA Liaison will work with the Sponsor to navigate the NEPA Approval process. The timeline varies by project scope and will not be fully known until NEPA is initiated. To initiate NEPA, the Sponsor must have: - Project location map showing the site and limits of disturbance. - Scope of work - Area of Potential Effect (APE), including direct physical impacts and indirect impacts such as noise or visual intrusions. - List of potentially significant historic structures or archaeological resources. - List of effects on historic resources eligible or listed on the National Register of Historic Places. These details allow SHA and FHWA to determine the level of NEPA documentation required (Categorical Exclusion, Programmatic CE, Environmental Assessment) and begin coordination with resource agencies. | For projects at 0% Design: 1 week For projects with 30% Design completed: Consider if the project has any of the elements listed in the Notes column. If the project does not have any of those considerations, write 3 months into the schedule. If the project has many elements listed in the Notes column, write 4 to 5 months in the schedule. | Does the project scope contain or impact any of the following? The presence or impact of these items may add time to the NEPA Approval process. -Sensitive resources such as wetlands, waterways, floodplains, rare/threatened/endangered species, or critical areas (e.g., Chesapeake Bay Critical Area). - Historic properties requiring Maryland Historical Trust (MHT) review and Section 106 compliance. - Section 4(f) resources (parks, recreation areas, wildlife refuges), specifically negative impacts or impeded access to Section 4(f) resources that may require avoidance analysis or mitigation. - Permitting needs (e.g., U.S. Army Corps of Engineers, Maryland Department of Environment). - Public involvement requirements if the project has significant community impacts. ***Agency response times, which typically take 30–60 days per coordination cycle, can be longer if additional studies or mitigation plans are needed.
Confirm Accuracy of Project Scope and Cost Estimate | Sponsor | The Sponsor will confirm the accuracy of the scope and cost estimate before the procurement request. Any changes in the project scope may require a NEPA reevaluation. | As needed
|  | Total time for Program Phase (once Award Letter is Received): | 3-6 months

## Procurement
Procurement Schedule Template Explanation
Task | Responsibility | Explanation | Estimated Time Range
Complete Draft RFP | Sponsor | The duration of drafting the RFP varies by scope. The Sponsor will complete SHA’s RFP template, A&E Checklist, and a detailed engineer's estimate. | 1-2 months
Request DBE goal | SHA | If the project is over $50,000, determine the Disadvantaged Business Enterprise (DBE) requirements by submitting the RFP materials to the SHA Procurement Review Group who will identify a DBE goal. On October 3, 2025, the US Secretary of Transportation issued an Internal Final Rule that makes significant changes to the DBE program. At this time, all DBE goals are set at 0% while business are re-certified according to the Rule. However, once re-certification is complete, DBE goals will once again be identified for TAP projects. For now, no time needs to be added for 0% DBE goals. Once DBE goals are reestablished, 1-2 months should be added to the project schedule | 0 weeks
RFP Review and Revision | Sponsor and SHA | SHA's Office of Procurement and Contract Management (OPCM) will review the RFP materials for federal-aid and state compliance, and return comments to the Sponsor for revision. The Sponsor must send the revised draft back to SHA for approval. The draft materials may go through this process once or multiple times until OPCM has approved the RFP for advertising. | 1-2 months
Notice to Advertise (NTA) | SHA | Once the RFP is approved by OPCM, SHA will send a Notice to Advertise (NTA) to the Sponsor, at which point the Sponsor can begin advertising. | 1 week
Advertise on eMMA | Sponsor | Projects are required to post on eMaryland Marketplace Advantage (eMMA) for a minimum of 28 calendar days. Advertisement must occur within 24 months of the Kickoff Meeting. | 1 month
Review Proposals and Select Consultant | Sponsor | Once the advertisement window has closed, the Sponsor will read and rank all proposals per RFP criteria, and submit score sheets and tabulation to SHA for review. | 1-2 month
Approval to Request Price Proposal | SHA | The Program Liaison will review the Sponsor's tabulations/score sheets, and then provide an Approval to Request Price Proposal email. Sponsor may then request a cost proposal from the highest rated consultant. | 1 week
Cost Proposal Development and Review | Sponsor and Consultant | The highest rated consultant will develop a cost proposal and the Sponsor will review it, compare the cost with the initial cost estimate, and send a copy for SHA to review. | 2-4 weeks
Negotiations with Consultant (if applicable) | Sponsor and Consultant | If the cost proposal is over 10% of the cost estimate created by the Sponsor, the Sponsor must enter negotiations with the highest ranked consultant. Negotiation timelines may vary widely. At the end of this process, the Sponsor will have a Best and Final Offer Cost Proposal from the consultant. | 2-4 weeks
Request SHA's Concurrence in Award (CIA) | Sponsor | SHA will provide a package of materials for the Sponsor to complete and send back to request a concurrence in award (CIA). The CIA request is required to request federal authorization. | 2 weeks
Federal Authorization Request | SHA | SHA is required to request authorization from FHWA to obligate awarded funds towards a specific project. In order to request and receive federal authorization for a TAP design project, SHA must include a final cost proposal from a consultant, obtained following the federal procurement process. Design work cannot begin before the project receives federal authorization. Any work done before federal authorization is received is not eligible for reimbursement. | 1-3 months
Notice to Proceed | SHA | Once SHA receives federal authorization for the project, a Notice to Proceed letter will be sent out to notify the Sponsor that they may begin work with the consultant. IMPORTANT: No design work may begin before receiving a Notice to Proceed letter from SHA. Any work that happens before a Notice to Proceed letter is not eligible for reimbursement. | 1 week
Execute Contract with Consultant | Sponsor | Once the Sponsor received the Notice to Proceed letter, the Sponsor and consultant may sign a contract. The signed contract must be sent to the Program Liaison (for record). | 1 week
|  | Total time for Procurement Phase | 8-14 months

## Design
Design Schedule Template Explanation
Task | Responsibility | Explanation | Estimated Time Range | Notes
Design Kick Off Meeting | Sponsor | Scheduled within 1 month of Notice to Proceed with the Sponsor, Consultant & SHA to begin the design process. SHA should be invited to the design meeting discuss grant requirements for this phase. | Within 1 month of NTP
Reimbursement Requests | Sponsor | Must be submitted on a monthly or quarterly basis throughout the design phase. | n/a
30% Design Development and Submission | Sponsor and Consultant | Typically the first major milestone after NTP. Consultant will develop design plans to 30% design. Timeline may vary and depends on complexity of project scope. If the project began with 30% design already completed, the plans must be submitted to SHA for review, but no additional development time is needed. | 2 -3 months (1 week if 30% plans already complete)
SHA Design Review | SHA | Various SHA offices will review the design plans, and comments will be returned to the Sponsor to address with the next design submission. SHA must review 30% design plans, even if the design was completed prior to award. | 4 to 6 weeks
Second National Environmental Policy Act (NEPA) Approval (if applicable) | Sponsor | If the full NEPA step was completed in the Program phase, then this can be skipped (applicable to projects who applied with 30% design already completed). The SHA NEPA Liaison will work with the Sponsor to navigate the NEPA Approval process. The timeline varies by project scope and will not be fully known until NEPA is initiated. To initiate NEPA, the Sponsor must have: - Project location map showing the site and limits of disturbance. - Scope of work - Area of Potential Effect (APE), including direct physical impacts and indirect impacts such as noise or visual intrusions. - List of potentially significant historic structures or archaeological resources. - List of effects on historic resources eligible or listed on the National Register of Historic Places. These details allow SHA and FHWA to determine the level of NEPA documentation required (Categorical Exclusion, Programmatic CE, Environmental Assessment) and begin coordination with resource agencies. | Consider if the project has any of the elements listed in the Notes column. If the project does not have any of those considerations, write 3 months into the schedule. If the project has many elements listed in the Notes column, write 4 to 5 months in the schedule. | Does the project scope contain or impact any of the following? The presence or impact of these items may add time to the NEPA Approval process. -Sensitive resources such as wetlands, waterways, floodplains, rare/threatened/endangered species, or critical areas (e.g., Chesapeake Bay Critical Area). - Historic properties requiring Maryland Historical Trust (MHT) review and Section 106 compliance. - Section 4(f) resources (parks, recreation areas, wildlife refuges), specifically negative impacts or impeded access to Section 4(f) resources that may require avoidance analysis or mitigation. - Permitting needs (e.g., U.S. Army Corps of Engineers, Maryland Department of Environment). - Public involvement requirements if the project has significant community impacts. ***Agency response times, which typically take 30–60 days per coordination cycle, can be longer if additional studies or mitigation plans are needed.
Federal Authorization Modification (if applicable) | SHA | If the project began from 0% design, then federal authorization is required twice. The first was under the Procurement phase, to authorize funding for preliminary design. Once the project receives full NEPA approval, federal authorization must be requested again for final design (100%). The Sponsor and consultant must not do any final design work until federal authorization is received. Any final design work that is done before federal authorization is received is not eligible for reimbursement. | 1 to 3 months
Receive Other Approvals as Needed | Sponsor | The timing varies depending on the necessary permits and reviews. (e.g. Stormwater and location specific permits) | The applicant should identify potential approvals needed in the notes section and estimate the time range.
60% Design Development and Submission | Sponsor and Consultant | The consultant further develops the plans to 60% design. Timeline may vary and depends on complexity of project scope. | 1 month
SHA Design Review | SHA | Various SHA offices will review the design plans, and comments will be returned to the Sponsor to address with the next design submission. | 4 to 6 weeks
90% Design | Sponsor and Consultant | The consultant further develops the plans to 90% design. Timeline may vary and depends on complexity of project scope. | 1 month
SHA Design Review | SHA | Various SHA offices will review the design plans, and comments will be returned to the Sponsor to address with the next design submission. | 4 to 6 weeks
100% Design | Sponsor and Consultant | The consultant further develops the plans to 100% design. Timeline may vary and depends on complexity of project scope. | 1 month
SHA Design Review | SHA | SHA reviews the 100% design plan submission and comments will be returned to the Sponsor to address and resubmit the package. | 4 to 6 weeks
Address Comments (as needed) | Sponsor and Consultant | Any outstanding SHA comments must be addressed before a design project can be closed. Allow time to finalize edits before SHA concurrence. | 1 month
|  | Total time for Design Phase | 15 - 22 months

## Closeout
Closeout Schedule Template Explanation
Task | Responsibility | Explanation | Estimated Time Range
Submit Final Reimbursement Request | Sponsor | Occurs after all design deliverables are complete and SHA concurrence is received. Allow up to 30 days for SHA to process payment once the request is approved. | 1 month
Project Closeout | SHA | Final closeout occurs after SHA review and issuance of a closeout letter once all requirements are met. | 1-2 weeks
|  | Total time for Closeout Phase | 1 - 1.5 months
End of worksheet