## Directions
Directions for Using the TA Feasibility Study Project Schedule Template
This schedule template is designed for Transportation Alternatives (TA) Feasibility Projects. Additional guidance for each task is organized by project phase on the Program, Procurement, Feasibility Study, and Closeout tabs.
How to Complete the Schedule
Enter the Month and Year the Sponsor expects each task to be completed.
Use the Notes column to explain any factors that could affect the timeline (Seasonal constraints, County specific requirements, etc.).
Customize the schedule to reflect the specific scope and circumstances of the proposed project.
Schedule Review Criteria
The most competitive applications include a realistic and comprehensive schedule that accounts for all phases of work and considers project-specific challenges.
Important Reminders
This schedule will serve as the baseline for the project after award. All dates are subject to change as the project progresses.
For more information please refer to the Transportation Alternatives Program Manual.

## TA Feasibility Study Schedule
Transportation Alternatives Feasibility Study Schedule Template
Phase | Task | Schedule (Month Year) | Notes
Application | Submit Application | April 2026
Program | Project Awarded | October 2026
Program | Kickoff Meeting
Program | Drafting MOU
Program | Sponsor Signs MOU
Program | SHA Signs and Executes MOU
Program | National Environmental Policy Act Programmatic Categorical Exclusion Appendix A (NEPA PCE Appendix A)
Program | Confirm Accuracy of Project Scope and Cost Estimate
Procurement | Complete Draft RFP
Procurement | Request DBE goal
Procurement | RFP Review and Revision
Procurement | Notice to Advertise (NTA)
Procurement | Advertise on eMMA
Procurement | Review Proposals and Select Consultant
Procurement | Approval to Request Price Proposal
Procurement | Cost Proposal Development and Review
Procurement | Negotiations with Consultant (if applicable)
Procurement | Request SHA's Concurrence in Award (CIA)
Procurement | Federal Authorization Request
Procurement | Notice to Proceed
Procurement | Execute Contract with Consultant
Feasibility Study | Feasibility Study Kick Off Meeting
Feasibility Study | Reimbursement Requests
Feasibility Study | Feasibility Study Development and Submission
Feasibility Study | SHA Feasibility Study Review
Feasibility Study | Address Comments
Closeout | Submit Final Reimbursement Requests
Closeout | Project Closeout

## Program
Program Schedule Template Explanation
Task | Responsibility | Explanation | Estimated Time Range
Project Awarded | SHA | The Notice of Award serves as the starting date from which subsequent milestones are measured. The Notice of Award is sent to the Sponsor in the Fall. | Fall
Kickoff Meeting | SHA | Scheduled within one month of the Notice of Award. The Sponsor meets with the assigned SHA Program Liaison to review project scope, federal/state requirements, and next steps. | Within 1 month after the Project Award
Drafting MOU | SHA | SHA prepares draft MOU and sponsor reviews and comments. | 1 weeks after the kickoff meeting
Sponsor Signs MOU | Sponsor | SHA provides electronic copies of the MOU for signature. The Sponsor returns a signed copy to SHA. | 2-4 weeks
SHA Signs and Executes MOU | SHA | SHA circulates the MOU to various signatories and returns the executed MOU to the Sponsor | 2-3 weeks after receiving the sponsor-signed MOU
National Environmental Policy Act Programmatic Categorical Exclusion Appendix A (NEPA PCE Appendix A) | SHA | SHA will provide a NEPA PCE Appendix A, which takes up to 1 week. No action will be needed on the Sponsor's side. This document is required to request federal authorization (see Procurement tab). | 1 week
Confirm Accuracy of Project Scope and Cost Estimate | Sponsor | The Sponsor will confirm the accuracy of the scope and cost estimate before the procurement process begins. | As needed
|  | Total time for Program Phase (once Award Letter is Received): | 3 months

## Procurement
Procurement Schedule Template Explanation
Task | Responsibility | Explanation | Estimated Time Range
Complete Draft RFP | Sponsor | The duration of drafting the RFP varies by scope. The Sponsor will complete SHA’s RFP template, A&E Checklist, and a detailed engineer's estimate. | 1-2 months
Request DBE goal | SHA | If the project is over $50,000, determine the Disadvantaged Business Enterprise (DBE) requirements by submitting the RFP materials to the SHA Procurement Review Group who will identify a DBE goal. On October 3, 2025, the US Secretary of Transportation issued an Internal Final Rule that makes significant changes to the DBE program. At this time, all DBE goals are set at 0% while business are re-certified according to the Rule. However, once re-certification is complete, DBE goals will once again be identified for TAP projects. For now, no time needs to be added for 0% DBE goals. Once DBE goals are reestablished, 1-2 months should be added to the project schedule | 0 weeks
RFP Review and Revision | Sponsor and SHA | SHA's Office of Procurement and Contract Management (OPCM) will review the RFP materials for federal-aid and state compliance, and return comments to the Sponsor for revision. The Sponsor must send the revised draft back to SHA for approval. The draft materials may go through this process once or multiple times until OPCM has approved the RFP for advertising. | 1-2 months
Notice to Advertise (NTA) | SHA | Once the RFP is approved by OPCM, SHA will send a Notice to Advertise (NTA) to the Sponsor, at which point the Sponsor can begin advertising. | 1 week
Advertise on eMMA | Sponsor | Projects are required to post on eMaryland Marketplace Advantage (eMMA) for a minimum of 28 calendar days. Advertisement must occur within 24 months of the Kickoff Meeting. | 1 month
Review Proposals and Select Consultant | Sponsor | Once the advertisement window has closed, the Sponsor will read and rank all proposals per RFP criteria, and submit score sheets and tabulation to SHA for review. | 1-2 month
Approval to Request Price Proposal | SHA | SHA will review the Sponsor's tabulations/score sheets, and then provide an Approval to Request Price Proposal email. Sponsor may then request a cost proposal from the highest ranked consultant. | 1 week
Cost Proposal Development and Review | Sponsor and Consultant | The highest ranked consultant will develop a cost proposal and the Sponsor will review it, compare the cost with the initial cost estimate, and send a copy for SHA to review. | 2-4 weeks
Negotiations with Consultant (if applicable) | Sponsor and Consultant | If the cost proposal is over 10% of the cost estimate created by the Sponsor, the Sponsor must enter negotiations with the highest ranked consultant. Negotiation timelines may vary widely. At the end of this process, the Sponsor will have a Best and Final Offer Cost Proposal from the consultant. | 2-4 weeks
Request SHA's Concurrence in Award (CIA) | Sponsor | SHA will provide a package of materials for the Sponsor to complete and send back to request a concurrence in award (CIA). The CIA request is required to request federal authorization. | 2 weeks
Federal Authorization Request | SHA | SHA is required to request authorization from FHWA to obligate awarded funds towards a specific project. In order to request and receive federal authorization for a TAP feasibility study project, SHA must include a final cost proposal from a consultant, obtained following the federal procurement process. Work cannot begin before the project receives federal authorization. Any work done before federal authorization is received is not eligible for reimbursement. | 1-3 months
Notice to Proceed | SHA | Once SHA receives federal authorization for the project, a Notice to Proceed letter will be sent to notify the Sponsor that they may begin work with the consultant. IMPORTANT: No work may begin before receiving a Notice to Proceed letter from SHA. Any work that happens before a Notice to Proceed letter is not eligible for reimbursement. | 1 week
Execute Contract with Consultant | Sponsor | Once the Sponsor received the Notice to Proceed letter, the Sponsor and consultant may sign a contract. The signed contract must be sent to SHA (for record). | 1 week
|  | Total time for Procurement Phase | 8-14 months

## Feasibility Study
Feasibility Study Schedule Template Explanation
Task | Responsibility | Explanation | Estimated Time Range
Feasibility Study Kick Off Meeting | Sponsor | Scheduled within 1 month of Notice to Proceed with the Sponsor, Consultant & SHA to begin the feasibility study process. SHA should be invited to the feasibility study meeting discuss grant requirements for this phase. | Within 1 month of NTP
Reimbursement Requests | Sponsor | Must be submitted on a monthly or quarterly basis throughout this phase. | n/a
Feasibility Study Development and Submission | Sponsor and Consultant | Timeline for the development of the feasibility study will vary depending on scope and complexity of the project. Provide an estimated timeframe for completing the study. | Varies
SHA Feasibility Study Review | SHA | SHA Bicycle and Pedestrian Safety team will review the feasibility study and give comments for the Sponsor and Consultant to address. | 2 weeks
Address Comments | Sponsor and Consultant | The consultant will address the comments received and submit the final feasibility study to SHA. | 2 weeks
|  | Total time for Feasibility Phase | Varies

## Closeout
Reimbursement and Closeout Schedule Template Explanation
Task | Responsibility | Explanation | Estimated Time Range
Submit Final Reimbursement Request | Sponsor | Occurs after feasibility study is complete and SHA concurrence is received. Allow up to 30 days for SHA to process payment once the request is approved. | 1 month
Project Closeout | SHA | Final closeout occurs after SHA review and issuance of a closeout letter once all requirements are met. | 1-2 weeks
|  | Total time for Closeout Phase | 1 - 1.5 months
End of worksheet