## Directions
Directions for Using the TA Non-Infrastructure Project Schedule Template
This schedule template is designed for Transportation Alternatives (TA) Non-Infrastructure Projects. Additional guidance for each task is organized by project phase on the Program, Procurement, and Project tabs.
How to Complete the Schedule
Enter the Month and Year the Sponsor expects each task to be completed.
Use the Notes column to explain any factors that could affect the timeline (Seasonal constraints, County specific requirements, etc.).
Customize the schedule to reflect the specific scope and circumstances of the proposed project.
Schedule Review Criteria
The most competitive applications include a realistic and comprehensive schedule that accounts for all phases of work and considers project-specific challenges.
Important Reminders
This schedule will serve as the baseline for the project after award. All dates are subject to change as the project progresses.
For more information please refer to the Transportation Alternatives Program Manual.

## TA Non-Infrastructure Schedule
Transportation Alternatives Non-Infrastructure Schedule Template
Phase | Task | Schedule (Month Year) | Notes
Application | Submit Application | April 2026
Program | Project Awarded | October 2026
Program | Kickoff Meeting
Program | Drafting MOU
Program | Sponsor Signs MOU
Program | SHA Signs and Executes MOU
Program | National Environmental Policy Act Programmatic Categorical Exclusion Appendix A (NEPA PCE Appendix A)
Program | Confirm Accuracy of Project Scope and Cost Estimate
Program | Federal Authorization
Procurement | Procurement Package
Procurement | Request DBE goal
Procurement | SHA Review and Approval
Procurement | Request DBE goal
Procurement | Notice to Advertise (NTA)
Procurement | Advertise
Procurement | Concurrence in Award (CIA)
Procurement | Notice to Proceed (NTP)
Project | Project timeline
Project | Reimbursement Requests
Project | Project Closeout

## Program
Program Schedule Template Explanation
Task | Responsibility | Explanation | Estimated Time Range
Project Awarded | SHA | The Notice of Award serves as the starting date from which subsequent milestones are measured. The Notice of Award is sent to the Sponsor in the Fall. | Fall
Kickoff Meeting | SHA | Scheduled within one month of the Notice of Award. The Sponsor meets with the assigned SHA Program Liaison to review project scope, federal/state requirements, and next steps. | Within 1 month after the Project Award
Drafting MOU | SHA | SHA prepares draft MOU and sponsor reviews and comments. | 1 weeks after the kickoff meeting
Sponsor Signs MOU | Sponsor | SHA provides electronic copies of the MOU for signature. The Sponsor returns a signed copy to SHA. | 2-4 weeks
SHA Signs and Executes MOU | SHA | SHA circulates the MOU to various signatories and returns the executed MOU to the Sponsor | 2-3 weeks after receiving the sponsor-signed MOU
National Environmental Policy Act Programmatic Categorical Exclusion Appendix A (NEPA PCE Appendix A) | SHA | SHA will provide a NEPA PCE Appendix A, which takes up to 1 week. No action will be needed on the Sponsor's side. This document is required to request federal authorization (see the Federal Authorization task in this tab). | 1 week
Confirm Accuracy of Project Scope and Cost Estimate | Sponsor | The Sponsor will confirm the accuracy of the scope and cost estimate before the procurement request. | As needed
Federal Authorization | SHA | SHA is required to request authorization from FHWA to obligate awarded funds towards a specific project. Procurement cannot begin before the project receives federal authorization. | 1 to 3 months
|  | Total time for Program Phase (once Award Letter is Received): | 3-6 months

## Procurement
Procurement Schedule Template Explanation
Task | Responsibility | Explanation | Estimated Time Range
Procurement Package | Sponsor | The Project Sponsor should identify the type of procurement that fits the project's cost estimate. Record the procurement type in the notes section. Small procurement includes three cost categories, Category I: <$5,000 Category II: $5,000 to $14,999 Category III: $15,000 to $50,000 Projects over $50,000 are required to complete Competitive Sealed Bidding (CSB). | Category I or II: 2 weeks to develop the procurement package. Category III or CSB: 1 month to develop the procurement package.
Request DBE goal | SHA | If the project is over $50,000, determine the Disadvantaged Business Enterprise (DBE) requirements by submitting the RFP materials to the SHA Procurement Review Group who will identify a DBE goal. On October 3, 2025, the US Secretary of Transportation issued an Internal Final Rule that makes significant changes to the DBE program. At this time, all DBE goals are set at 0% while business are re-certified according to the Rule. However, once re-certification is complete, DBE goals will once again be identified for TAP projects. For now, no time needs to be added for 0% DBE goals. Once DBE goals are reestablished, 1-2 months should be added to the project schedule | 0 weeks
SHA Review and Approval | SHA | Submit procurement package to SHA for review and approval. The timeline depends on the number of comments and rounds of revision. | Category I, II: 2 weeks Category III or CSB: 4 to 6 weeks
Request DBE goal | SHA | Determine the Disadvantaged Business Enterprise (DBE) requirements by submitting the procurement materials to the SHA Procurement Review Group who will identify a DBE goal. On October 3, 2025, the US Secretary of Transportation issued an Internal Final Rule that makes significant changes to the DBE program. At this time, all DBE goals are set at 0% while business are re-certified according to the Rule. However, once re-certification is complete, DBE goals will once again be identified for TAP projects. For now, no time needs to be added for 0% DBE goals. Once DBE goals are reestablished, 1-2 months should be added to the project schedule | 0 weeks
Notice to Advertise (NTA) | SHA | The NTA is issued when the Procurement Package completes all Federal and State requirements. | 1 week
Advertise | Sponsor | Category I: Sponsor solicits at least two vendors. Offers can be oral or in writing; however, documentation is required. Category II: Sponsor solicits at least three vendors. Solicitations must be in writing. Category III: Sponsor posts solicitation on eMaryland Marketplace Advantage (eMMA) for a minimum of three working days before the bids are due and opened. CSB: Sponsor posts solicitations on eMMA for a minimum of 28 days before bids are due and opened. | Category I or II: 2 weeks Category III or CSB: 1 month
Concurrence in Award (CIA) | Sponsor | The Project Sponsor selects a vendor based on the lowest responsive and responsible bid. The Project Sponsor submits a request to SHA for CIA. | 1 week
Notice to Proceed (NTP) | SHA | After bid evaluation and SHA approval, the Project Sponsor receives NTP from SHA. | 1 week
|  | Total time for Procurement Phase | 2-4 months

## Project
Project Schedule Template Explanation
Task | Responsibility | Explanation | Estimated Time Range
Project timeline | Sponsor | Project timeline varies widely. Estimate the total project time after procurement until closeout. | Varies
Reimbursement Requests | Sponsor | Must be submitted on a monthly or quarterly basis throughout this phase. | n/a
Project Closeout | SHA | Final closeout occurs after SHA review and issuance of a closeout letter once all requirements are met. | 1-2 weeks
|  | Total time for Project Phase | Varies
End of worksheet